## Read me
Spec §8.4 hand benchmark (CE725 Team 2, module M4 cash flow)
MANUAL CHECK REQUIRED. The course requires this hand benchmark to be checked by a person.
Open the 'Benchmark 8.4' sheet, redo each line by hand or calculator, and sign below.
Checked by: ____________________ Date: ____________ Result (all MATCH / differences): ______________
What this file is
Every number in 'Monthly' and in column D of 'Benchmark 8.4' is a live Excel formula that reads the
yellow cells in 'Inputs'. Nothing is pasted from Python. Change an input and Excel recalculates.
Column C of 'Benchmark 8.4' is the spec table typed by hand. Column E is the Python engine's value,
written when the file was generated (python -m analyser.cashflow.benchmark, from backend/).
Columns F and G say MATCH when Excel and Python agree with the spec to 4 decimals.
Conventions (same as the Python engine, see backend/analyser/cashflow/FORMULAS.md)
Units: Rs crore. Row = end of month. Month 0 = signing. Work of month m is billed at the end of month m.
Retention = r x bill until cumulative retention reaches Rmax x V.
Advance recovery = rho x bill until the advance received so far is repaid; any balance is recovered in
full in month floor(0.8 x T) = 19 and in the final bill (month T).
Net certified is paid after the payment lag (30 days = 1 month). Advances arrive in their months.
Delay D moves completion to month T + D/30; damages are deducted then; retention is released
'RelMonths' after completion. Cash out = cost share x gross work, paid the same month.
Values not given in spec §8.4 are [ASSUMPTION]s and are marked in 'Inputs'.

## Inputs
Name | Input | Value | Unit / note
ContractValue | Contract value V | 100 | Rs crore
Months | Duration T | 24 | months (even progress, 1/T each month)
RetRate | Retention rate r | 0.06 | share of each gross bill
RetCap | Retention cap Rmax | 0.05 | share of V
AdvFirst | Advance instalment 1 | 0.05 | share of V
AdvFirstMonth | Instalment 1 arrives in month | 0 | month [ASSUMPTION]
AdvSecond | Advance instalment 2 | 0.05 | share of V
AdvSecondMonth | Instalment 2 arrives in month | 2 | month [ASSUMPTION]
RecRate | Advance recovery rate rho | 0.15 | share of each gross bill
RecDeadline | Recovery deadline | 0.8 | share of T
LDRate | Delay damages rate l | 0.0005 | share of V per day
LDCap | Delay damages cap Lmax | 0.1 | share of V
DelayDays | Delay D | 60 | days
CostShare | Cost share c | 0.85 | share of gross work [ASSUMPTION]
PayLagDays | Payment lag | 30 | days; whole months only in this sheet (30, 60, ...)
RelMonths | Retention released after completion | 1 | months; whole months only [ASSUMPTION]
ODRate | Overdraft rate | 0.1 | per year [ASSUMPTION]

## Benchmark 8.4
Item | Hand calculation | Spec §8.4 result (typed) | Excel formula result | Python engine | Excel = spec? | Python = spec?
Gross work each month (Rs crore) | 100 / 24 | 4.1667 |  | 4.1667
Retention each month (Rs crore) | 6% of 4.1667 | 0.25 |  | 0.25
Month in which retention reaches its 5% cap (Rs 5 crore) | 5 / 0.25 | 20 |  | 20
Advance recovery each month (Rs crore) | 15% of 4.1667 | 0.625 |  | 0.625
Month in which a Rs 10 crore advance is fully recovered | 10 / 0.625 | 16 |  | 16
80% recovery limit (month) | 0.8 x 24 | 19.2 |  | 19.2
Net certified in month 1 (Rs crore) | 4.1667 - 0.25 - 0.625 | 3.2917 |  | 3.2917
Delay damages for 60 days (Rs crore) | 60 x 0.05% of 100 | 3 |  | 3
Days of delay to reach the cap | 10% / 0.05% | 200 |  | 200
Delay damages at the cap (Rs crore) | 10% of 100 | 10 |  | 10
Beyond the spec table (Excel vs Python only; no spec value)
Item |  |  | Excel formula result | Python engine | Excel = Python?
Peak funding need = largest positive gap, 0 if none (Rs crore) |  |  |  | 0
Month of peak funding (0 if never short of cash) |  |  |  | 0
Overdraft interest = sum of positive gaps x rate / 12 (Rs crore) |  |  |  | 0
Total cash in = V - delay damages (Rs crore) |  |  |  | 97
Total cash out = c x V (Rs crore) |  |  |  | 85
Largest monthly difference, Excel gap vs Python gap (Rs crore) |  |  |  | 0

## Monthly
Month | Gross work B | Retention Ret | Cum retention | Advance received | Cum advance received | Advance recovery Rec | Cum recovered | Advance outstanding | Net certified | Retention released | Delay damages deducted | Cash in | Cash out | Cum in | Cum out | Gap (out - in) | Retention held | Cap reached? (month or 999) | Advance repaid? (month or 999)
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Python monthly
Month | Python cash in | Python cash out | Python gap | Excel gap - Python gap
0 | 5 | 0 | -5
1 | 0 | 3.5417 | -1.4583
2 | 8.2917 | 3.5417 | -6.2083
3 | 3.2917 | 3.5417 | -5.9583
4 | 3.2917 | 3.5417 | -5.7083
5 | 3.2917 | 3.5417 | -5.4583
6 | 3.2917 | 3.5417 | -5.2083
7 | 3.2917 | 3.5417 | -4.9583
8 | 3.2917 | 3.5417 | -4.7083
9 | 3.2917 | 3.5417 | -4.4583
10 | 3.2917 | 3.5417 | -4.2083
11 | 3.2917 | 3.5417 | -3.9583
12 | 3.2917 | 3.5417 | -3.7083
13 | 3.2917 | 3.5417 | -3.4583
14 | 3.2917 | 3.5417 | -3.2083
15 | 3.2917 | 3.5417 | -2.9583
16 | 3.2917 | 3.5417 | -2.7083
17 | 3.2917 | 3.5417 | -2.4583
18 | 3.9167 | 3.5417 | -2.8333
19 | 3.9167 | 3.5417 | -3.2083
20 | 3.9167 | 3.5417 | -3.5833
21 | 3.9167 | 3.5417 | -3.9583
22 | 4.1667 | 3.5417 | -4.5833
23 | 4.1667 | 3.5417 | -5.2083
24 | 4.1667 | 3.5417 | -5.8333
25 | 4.1667 | 0 | -10
26 | -3 | 0 | -7
27 | 5 | 0 | -12