## Read Me
Contract Answer Key (draft, machine-checked)
CE725 Team 2, Topic 12. Built 22 October 2026 from the questionnaire in Contract_Extraction_Questionnaire_v0.1.md.
What this is
A first-pass answer key for the best four contracts. Each question has a status, the answer, the clause, the PDF page and a verbatim quote copied from the contract text.
Status values: FOUND (stated in the document), NOT_STATED (nothing said), NOT_APPLICABLE (the clause exists but is switched off), POINTS_ELSEWHERE (the document defers to another document or a blank schedule).
How the quotes were checked
A script searched every quote in the extracted text of the PDF and compared the page number. 'Verified exact' means the quote was found word for word on the stated page. Anything else needs a human look at the PDF page.
A verified quote proves the text exists on that page. It does not prove the answer reads it correctly. For multi-part answers the quote may show only the trigger (for example the 30-day grace period in NHAI clause 10.3) and the number sits in the next sentence. A human has to confirm each one.
What you still have to do
1. Open each PDF page for a sample of answers and confirm the quote and number with your own eyes. The course says every number must be verified manually.
2. Pay special attention to rows marked NOT_STATED. A value could sit in a table that the text extraction dropped.
3. The answer key is the team's benchmark. Argue with it. If you disagree with an answer, change it and note why.
Limits
PDF page numbers are positions in the file, not printed page numbers. Text was extracted by machine, so scanned tables or pictures are not included.

## Best 4
Rank | ID | Contract | Type | Pages | Why it is in the top four | What it tests | Weakness | Link
1 | BM1 | NHAI Makhu Town EPC Agreement (NH-54, Punjab) | Real project agreement | 250 | Best overall. Every one of the six clause types is present with specific numbers, in a long, realistic document. The text is clean and machine-readable. | Rate against cap that disagree (retention 6% deducted, 5% cap). Two layers of security. Interest-bearing advance with a bank guarantee at 110%. Index-formula price adjustment. Delay damages per day with a cap. | Highway-specific. Same template as other NHAI agreements, so little variety. Payments are by stage, not monthly bills. | https://nhai.gov.in/nhai/sites/default/files/2020/EPC_Agreement_Schedules-Makhu_Town.pdf
2 | BM2 | IIT Bombay tender: MEP and interior works, Chemistry Research Lab | Real tender | 114 | Your own institute's real tender, so it makes the strongest demo story. Filled Schedules E and F, base prices, advance with interest, escalation clauses, and delay compensation. | Schedule values that complete the general clauses. 'Applicable / not applicable' switches. Noise: labour regulations, registers and a consultancy-style table that looks out of place. | A lot of boilerplate. Several schedule fields are blank. | https://www.iitb.ac.in/deanpl/tenders/chemlabr/gc.pdf
3 | BM3 | MP Agro tender: composite building, Gwalior | Real tender | 93 | Best for honest failure tests. Short, real, and built around a data sheet that overrides the general text. It switches several clauses off and hides the delay-damages rate two references deep. | Schedule overrides the general text. 'No advance' answers. Damages rate reached through GCC 15.4, Contract Data and Annexure P. Price adjustment switched off by contract size, with weights that disagree between two places. 'No interest payable' on late payment. | Small project. PDF extraction splits some words and digits. Pages 87 to 93 are scanned images with no text, and the Hindi special conditions are in a legacy font. | https://mpagro.org/assets/tenderfiles/2a2d879c-6e8f-451f-976a-d7d1de78ae90.pdf
4 | BM4 | MoEF&CC e-NIT: water bubbler, National Zoological Park | Real tender | 38 | The common central-government CPWD format in a short, real tender with filled schedules. It points to CPWD GCC 2023 for most conditions. | Cross-document references: the right answer is often 'defined in GCC 2023'. Four milestones with money withheld. Clause 10CC marked not applicable. | Few financial values. Small contract (Rs 7.25 lakh). No advance or escalation. | https://moef.gov.in/storage/tender/1739175875.pdf
Left out, and why
NHAI Vijayawada to Machilipatnam EPC: same template and same values as BM1. Use it only as a consistency check.
CPWD GCC 2023: a blank standard form. Use it as the reference text that BM4 points to.
Dr PDKV Akola tenders: real but tiny repair jobs with little financial content.
NHAI RFP 625: bid-stage document. Retention and damages sit in a separate agreement.
IIT Hyderabad, NIT Meghalaya, CPWD EPC 2024 forms: standard forms with no filled-in values.
How to use the four
Headline accuracy for the presentation: BM1 and BM2. Stress tests where failures go in the AI error log: BM3 and BM4. Score all four the same way.

## Answer Key
Contract | Clause | Q | Question | Status | Answer | Unit | Section | PDF page | Verbatim quote | Notes (traps for the AI) | Quote check
BM1 | C0 | 0.1 | Contract type, form and version | FOUND | NHAI draft EPC agreement for four-laning of Makhu Town, NH-54 Punjab; cover dated July 2024 |  | Cover page | 1 | Draft Engineering Procurement and Construction (EPC) Agreement For Widening and Reconstruction of existing Two Lane Carriageway to Four Lane with Paved Shoulder in Makhu Town | Draft, not an executed contract. Cover also names NHAI and July 2024 on the same page. Template shared with other NHAI EPC agreements. | Verified exact
BM1 | C0 | 0.2 | Employer and contractor | FOUND | Employer: President of India through MoRTH, represented by Chairman NHAI (Chandigarh regional office); Contractor: not named (placeholder) |  | Parties clause | 14 | The President of India through the Ministry of Road Transport & Highways, Government of India represented by: The Chairman, National Highways Authority of India, Regional office, Chandigarh | Contractor is a blank placeholder (<insert name of party>). An LLM may invent a contractor name. | Verified exact
BM1 | C0 | 0.3 | Contract value / price | POINTS_ELSEWHERE | Lump sum Contract Price left blank (INR ... ) to be filled with the accepted bid price | INR | Cl. 19.1(i) | 102 | the lump sum price accepted by the Authority in consideration of the obligations specified in this Agreement for an amount of INR … … … … (INR … … … … … … … …) (the “Contract Price”) | Amount is blank in this draft. Price excludes maintenance cost and GST (same clause). Do not accept any figure from the tool. | Verified exact
BM1 | C0 | 0.4 | Completion period and start trigger | FOUND | 730 days from the Appointed Date | days | Cl. 10.3(i) | 64 | The 730th (seven hundred and thirtieth) day from the Appointed Date shall be the scheduled completion date | Appointed Date is declared by the Authority with contractor consent (Art. 3 and 8). Schedule J milestone days must agree with 730. | Verified exact
BM1 | C0 | 0.5 | Defects liability / maintenance period | FOUND | 5 years (flexible pavement); 10 years (rigid pavement, perpetual-design flexible, stand-alone structures), from completion | years | Cl. 17.1(i) | 95 | (a) 5 (five) years from the date of completion in case of a road being constructed with flexible pavement; (b) 10 (ten) years from the date of completion in case of road being constructed with rigid pavement; | Which limb applies depends on the pavement type chosen in the specifications; not decided in this clause. Separate Maintenance Period exists under Art. 14. | Verified exact
BM1 | C0 | 0.6 | Milestones | FOUND | Milestone I day 145 (statements >=10% of price); II day 320 (>=35%, all bridges started); III day 520 (>=70%); Scheduled Completion day 730 | days / % of Contract Price | Sch. J paras 2-5 | 219 | Project Milestone-I shall occur on the date falling on the 145th (one hundred and forty fifth first) day from the Appointed Date | Trap: Cl. 10.3(ii) example mentions Milestone-I on the 180th day with 10%, but Schedule J says 145th day. Quote is the Schedule J wording. | Verified exact
BM1 | C1 | 1.1 | Billing basis and frequency | FOUND | Stage payments for completed stages valued per Schedule-H; contractor submits one Stage Payment Statement a month by the 7th | monthly | Cl. 19.3 and 19.4 | 105 | The Contractor shall submit a statement (the “Stage Payment Statement”), in 3 (three) copies, by the 7th (seventh) day of the month | Not item-rate measurement: no payment for incomplete stages (same clause). LLM may describe it as monthly measured running bills. | Verified exact
BM1 | C1 | 1.2 | Days to certify a bill | FOUND | Authority's Engineer issues the Interim Payment Certificate within 15 days of receiving the statement; within 10 days he recommends a 90% part payment | days | Cl. 19.5(i) and (ii) | 105 | Within 15 (fifteen) days of the receipt of the Stage Payment Statement referred to in Clause 19.4, the Authority’s Engineer shall determine and shall deliver | Two different periods (10 and 15 days) sit in the same clause. Certification is not the same as payment. | Verified exact
BM1 | C1 | 1.3 | Days to pay after certification | FOUND | Payment no later than 30 days from submission of the Stage Payment Statement; if no IPC in 30 days the Authority pays the amount claimed and adjusts later | days | Cl. 19.9(i)(a) | 107 | payment shall be made no later than 30 (thirty) days from the date of submission of the Stage Payment Statement by the Contractor | The 30 days run from submission of the statement, not from certification. Part payment of 90% is separately due within 10 days of the Engineer's recommendation (19.5(i)). | Verified exact
BM1 | C1 | 1.4 | Interest on delayed payment | FOUND | Bank Rate + 3% per annum on all unpaid sums | % p.a. | Cl. 19.9(ii) | 108 | the Authority shall be liable to pay to the Contractor interest @ Bank Rate + 3% per annum, on all sums remaining unpaid | Bank Rate is the RBI rate (footnote in 19.2(i)); the current value is not in the contract. Base Rate (SBI) is a different defined term. | Verified exact
BM1 | C1 | 1.5 | Deductions from each bill | FOUND | Retention 6% of every payment (cap 5% of Contract Price); advance recovery 15% of each Stage Payment Statement; withholding for unperformed or defective work (19.5(iv)) | % | Cl. 7.5(i); 19.2(vi); 19.5(iv) | 50 | deduct 6% (six per cent) thereof as guarantee money for performance of the obligations of the Contractor during the Construction Period | Deductions are spread across three clauses. Taxes at source are mentioned only in the termination valuation (23.5), not as a bill deduction. | Verified exact
BM1 | C1 | 1.6 | Minimum bill or cap before certification | FOUND | No minimum bill value stated; before the IPC only 90% of the amount broadly determined is released as part payment | % of determined amount | Cl. 19.5(i) | 105 | recommend the release of 90 (ninety) percent of the amount so determined as part payment against the Stage Payment Statement, pending issue of the Interim Payment Certificate | No minimum bill amount found. The 90% interim release is the only cap before certification. Contractor cannot claim incomplete stages (19.4). | Verified exact
BM1 | C1 | 1.7 | Final bill and final payment | FOUND | Final Payment Statement within 60 days of Completion Certificate; Final Payment Certificate within 30 days of statement and discharge; payment per 19.9 | days | Cl. 19.13(i); 19.15; 19.9 | 111 | Within 60 (sixty) days after receiving the Completion Certificate under Clause 12.2, the Contractor shall submit | Two further periods (30 days) come from other clauses. Maintenance has its own final statement (19.16). | Verified exact
BM1 | C1 | 1.8 | Pay-when-paid or conditional payment | NOT_STATED | None found |  |  | 0 |  | Searched Art. 19 and whole text for pay-when-paid, back-to-back, subject to receipt of funds, availability of funds: no hits. Payment is unconditional but subject to certification. | No quote
BM1 | C2 | 2.1 | Retention deducted? | FOUND | Yes |  | Cl. 7.5(i) | 50 | From every payment for Works due to the Contractor in accordance with the provisions of Clause 19.5, the Authority shall deduct 6% (six per cent) thereof | Retention is in Art. 7 (Performance Security), not in Art. 19 where payments sit. | Verified exact
BM1 | C2 | 2.2 | Rate and base | FOUND | 6% of every payment for Works (stage payments under Cl. 19.5) | % of each payment | Cl. 7.5(i) | 50 | deduct 6% (six per cent) thereof as guarantee money for performance of the obligations of the Contractor during the Construction Period | Trap: rate is 6% but total is capped at 5% of Contract Price (next row). LLMs often report only 5%. | Verified exact
BM1 | C2 | 2.3 | Cap on total retention | FOUND | 5% of Contract Price | % of Contract Price | Cl. 7.5(i) | 50 | subject to the condition that the maximum amount of Retention Money shall not exceed 5% (five per cent) of the Contract Price. | Cap is lower than the deduction rate, so deductions stop once 5% of the Contract Price is held. | Verified exact
BM1 | C2 | 2.4 | Bid security / earnest money counted against retention | NOT_STATED | No link between bid security and retention |  |  | 0 |  | Searched "Bid Security": only the definition (Bid Security stays until substituted by Performance Security) and 7.1(iv). No conversion into retention. | No quote
BM1 | C2 | 2.5 | When retention is released | FOUND | Balance refunded within 15 days of the Completion Certificate (after set-off of appropriations) | days | Cl. 7.5(iii) | 50 | Within 15 (fifteen) days of the date of issue of the Completion Certificate, the Authority shall refund the balance of Retention Money remaining with the Authority | Released at completion, not at end of the 5 or 10 year defects period. On termination it is treated like Performance Security (7.5(iv)). | Verified exact
BM1 | C2 | 2.6 | Retention replaceable by bank guarantee | NOT_STATED | No substitution mechanism in this agreement |  |  | 0 |  | Searched Cl. 7.5 and the whole text for retention with bank guarantee or substitution forms: none. A retention-withdrawal guarantee form exists in some other NHAI drafts, not here. | No quote
BM1 | C2 | 2.7 | Interest on retention | NOT_STATED | None stated |  |  | 0 |  | Cl. 7.5 has no interest. The 9% interest in 7.4(iii) applies only to late return of Performance Security and Additional Performance Security. | No quote
BM1 | C3 | 3.1 | Mobilisation advance given? | FOUND | Yes, interest-bearing |  | Cl. 19.2(i) | 102 | The Authority shall make an interest-bearing advance payment (the “Advance Payment”) @ “Bank Rate3 + 3%”, equal to 10 % (ten percent) of the Contract Price, | Advance is paid by the Authority to the Contractor, the reverse of retention. It is interest-bearing, not free. | Verified exact
BM1 | C3 | 3.2 | Amount and instalments | FOUND | 10% of Contract Price in two instalments of 5% each | % of Contract Price | Cl. 19.2(i) | 103 | The Advance Payment for mobilisation expenses shall be made in two instalments each equal to 5% (ﬁve percent) of the Contract Price. | Second instalment needs a utilisation certificate for the first. Separate equipment advance is additional (3.6). | Verified exact
BM1 | C3 | 3.3 | Interest-free or interest-bearing | FOUND | Interest-bearing at Bank Rate + 3% per annum | % p.a. | Cl. 19.2(i); 19.2(vii) | 102 | The Authority shall make an interest-bearing advance payment (the “Advance Payment”) @ “Bank Rate3 + 3%”, equal to 10 % (ten percent) of the Contract Price, | On termination for Contractor Default the unrecovered balance carries Bank Rate + 5% (19.2(vii)). Two different spreads in one clause. | Verified exact
BM1 | C3 | 3.4 | Recovery method | FOUND | 15% deducted from each Stage Payment Statement from the first one; fully repaid before 80% of the scheduled construction period | % of each payment | Cl. 19.2(vi) | 104 | deductions shall be made at the rate of 15% (fifteen percent) of each Stage Payment Statement until such time as the advance payment has been repaid; | Also: if certified payments stay at or below 20% of price within half the period, the advance is recovered by encashing the guarantee (19.2(vi)(c)). | Verified exact
BM1 | C3 | 3.5 | Security for the advance | FOUND | Irrevocable unconditional e-Bank Guarantee for 110% of each instalment, valid until full repayment | % of instalment | Cl. 19.2(iii) and (iv) | 103 | for an amount equivalent to 110% (one hundred and ten per cent) of such instalment | Guarantee can be split into parts of at least 2.75% of Contract Price each. Physical BG also accepted till 31.12.2024 per footnote. | Verified exact
BM1 | C3 | 3.6 | Plant and machinery or secured advance | FOUND | Additional advance on newly purchased key equipment up to 5% of Contract Price against e-BG; no advance on materials found | % of Contract Price | Cl. 19.2(ii) | 103 | The maximum of such advance shall be 5% (five per cent) of the Contract Price | Equipment advance needs Engineer verification the equipment is on site. Searched for secured advance on materials: no hits. | Verified exact
BM1 | C3 | 3.7 | Conditions to receive the advance | FOUND | Apply after Appointed Date with 110% e-BG; second instalment after 60 days from Appointed Date, with e-BG and utilisation certificate; paid within 15 days of request | days | Cl. 19.2(iii)-(v) | 103 | The Contractor may apply to the Authority for the first instalment of the Advance Payment at any time after the Appointed Date | First instalment: any time after Appointed Date. Second: after 60 days plus utilisation certificate for the first 5%. | Verified exact
BM1 | C4 | 4.1 | Delay damages imposed? | FOUND | Yes (called "Damages") |  | Cl. 10.3(ii) | 64 | it shall pay Damages to the Authority of a sum calculated at the rate of 0.05% (zero point zero five percent) of the Contract Price for delay of each day | Contract uses the word Damages and says it is not a penalty or liquidated damages (1.2(w)). LLM searching only for "liquidated damages" will miss it. | Verified exact
BM1 | C4 | 4.2 | Rate and base | FOUND | 0.05% of Contract Price per day of delay, counted from the Schedule J date once 30 days have passed | % of Contract Price per day | Cl. 10.3(ii) | 64 | In the event that the Contractor fails to achieve any Project Milestone or the Scheduled Completion Date within a period of 30 (thirty) days from the date set forth in Schedule-J | Trap: a 30-day grace applies before damages start, but the daily count runs from the Schedule J date, not from day 31. | Verified exact
BM1 | C4 | 4.3 | Cap on damages | FOUND | 10% of Contract Price; above that the Contractor is in default and the Authority may terminate | % of Contract Price | Cl. 10.3(iii) | 65 | the total amount of Damages under Clause 10.3 (ii) shall not exceed 10% (ten percent) of the Contract Price | Cap is stated in 10.3(iii), a later paragraph than the rate. Cap reached after 200 days at 0.05% a day. | Verified exact
BM1 | C4 | 4.4 | Completion only or milestones too | FOUND | Both each Project Milestone and the Scheduled Completion Date |  | Cl. 10.3(ii) | 64 | In the event that the Contractor fails to achieve any Project Milestone or the Scheduled Completion Date | Damages paid for a missed milestone are refunded without interest if the project finishes by the Scheduled Completion Date including extensions. | Verified exact
BM1 | C4 | 4.5 | How the date can be extended | FOUND | Time Extension for delayed Right of Way or clearances, Change of Scope, Force Majeure, Authority-caused delay; notice within 15 business days or the right is lost | business days | Cl. 10.5(i)-(iii) | 66 | the Contractor shall be entitled to extension of time in the Project Completion Schedule (the “Time Extension”) to the extent that completion of any Project Milestone is or will be delayed by any of the following, namely: | Extension applies only to the affected works, not the whole project (10.5(ii)). | Verified exact
BM1 | C4 | 4.6 | Pre-estimate of loss; proof of loss | FOUND | Damages are stated to be a genuine pre-estimate of loss and not a penalty; proof of loss not mentioned |  | Cl. 1.2(w) | 26 | mutually agreed genuine pre-estimated loss and damage likely to be suffered and incurred by the Party entitled to receive the same and are not by way of penalty or liquidated damages | No wording on whether actual loss must be proved. Relevant to Section 74 of the Contract Act. | Verified exact
BM1 | C4 | 4.7 | Recovery from bills, retention or guarantee | FOUND | Appropriate from Performance Security and Retention Money on Contractor Default; recoverable from amounts due after 20 days notice |  | Cl. 7.3(i); 7.5(ii); 19.19 | 49 | Upon occurrence of a Contractor’s Default, the Authority shall, without prejudice to its other rights and remedies hereunder or in law, be entitled to encash and appropriate the relevant amounts from the Performance Security as Damages | Damages cannot be deducted without notice and 20 days for a representation (10.3(iii)). | Verified exact
BM1 | C4 | 4.8 | Other damages or penalties | FOUND | 0.01% of Bid Price per day for late security; maintenance non-compliance payment cuts (Sch. M); Authority pays damages for late site handover (8.3); bid ban if >90 days late on projects of Rs 300 crore or more; early completion bonus 0.03% a day, max 5% | various | Cl. 7.1(iii); 8.3; 10.3(iv); 19.20; Sch. M | 49 | The Damages shall be the sum calculated at the rate of 0.01% (zero point zero one per cent) of the Bid Price offered by the Selected Bidder | Several different "Damages" run both ways. Do not merge the 0.01% (security delay) with the 0.05% (construction delay). | Verified exact
BM1 | C5 | 5.1 | Fixed price or price variation | FOUND | Price variation clause applies (index-based adjustment) |  | Cl. 19.10(iv) | 108 | The Contract Price shall be adjusted for increase or decrease in rates and price of labour, cement, steel, Plant, machinery and spares, bitumen, fuel and lubricants, and other material inputs | Contract Price is lump sum but adjusted by formula (19.1(i)). Not fixed price. | Verified exact
BM1 | C5 | 5.2 | Formula | FOUND | Two formulae, VRW for road/other works and VBR for bridges and structures, applied stage by stage |  | Cl. 19.10(iv)(d) | 108 | Price adjustment for changes in cost shall be paid in accordance with the following formulae: | The equations are images, so the extracted text has only the variable definitions (VRW, VBR, AO/AI, CO/CI and others). A tool must not invent the algebra. | Verified exact
BM1 | C5 | 5.3 | Components and weights | FOUND | Labour 20/20/20/15/15%; cement 5/nil/20/15/15%; steel nil/nil/nil/15/20%; bitumen nil/15/nil/nil/nil%; fuel 10% each; other materials 50/40/35/30/25%; plant 15% each (five work types) | % by work type | Cl. 19.10(iv)(e) | 110 | Labour (PL) 20% 20% 20% 15% 15% Cement (PC) 5% Nil 20% 15% 15% Steel (PS) Nil Nil Nil 15% 20% Bitumen (PB) Nil 15% Nil Nil Nil | Five columns by work type; table text is split across lines and continues on the next page (plant row). | Verified exact
BM1 | C5 | 5.4 | Index and source | FOUND | WPI machinery; WPI cement (OPC); WPI mild steel long products; WPI all commodities; CPI-IW Bathinda (Labour Bureau); bitumen price at Bathinda (HMEL) refinery; HSD price at IOC pumps in Punjab |  | Cl. 19.10(iv)(d) definitions | 110 | SO = The WPI for Mild Steel –Long Products for the month of the Base Date. SI = The WPI for Mild Steel –Long Products for the month three months prior to the month to which the IPC relates. | Current index is for the month three months before the IPC month. Bitumen and diesel use price points, not WPI. | Verified exact
BM1 | C5 | 5.5 | Base date | FOUND | Last day of the calendar month at least 28 days before the Bid Due Date |  | Cl. 1.1 (Base Date) | 17 | means the last date of the calendar month, which precedes the Bid Due Date by at least 28 (twenty eight) days | Index comparison point is the Base Date (not the contract signing date). | Verified exact
BM1 | C5 | 5.6 | Threshold or cap on escalation | NOT_STATED | No threshold or ceiling stated |  |  | 0 |  | Searched Cl. 19.10 and 19.11: no deductible threshold, ceiling or percentage cap. 19.10(iii) says costs not otherwise covered are deemed included in the price. | No quote
BM1 | C5 | 5.7 | Escalation after original completion date | FOUND | Payable only for stages billed within 30 days of the applicable milestone or Scheduled Completion Date (including extensions) | days | Cl. 19.11 | 111 | Price adjustment shall be due and payable only in respect of the stages of Works for which the Stage Payment Statement has been submitted by the Contractor no later than 30 (thirty) days | Late billing cuts off price adjustment after that milestone or completion date; it is not a blanket stop at original completion. | Verified exact
BM1 | C5 | 5.8 | Escalation on employer-supplied materials | NOT_STATED | No such provision found |  |  | 0 |  | Searched for supplied by or issued by the Authority and free issue of materials: no material-supply clause tied to escalation. | No quote
BM1 | C6 | 6.1 | Securities required | FOUND | Bid Security (RFP stage); Performance Security; Additional Performance Security for low bids; Retention Money; e-BG for each advance (mobilisation and equipment) |  | Cl. 7.1; 7.5; 19.2 | 48 | Within 30 (thirty) days of receipt of Letter of Acceptance, the selected Bidder shall furnish to the Authority in the form of Insurance Surety Bond | Retention and advance guarantees are not in the same clause as Performance Security. LLMs often list only the first. | Verified exact
BM1 | C6 | 6.2 | Amount and base | FOUND | Performance Security 3% of Bid Price; Additional Performance Security up to 3% of Bid Price; advance e-BG 110% of each instalment; equipment advance up to 5% of Contract Price | % | Cl. 7.1(i); 19.2 | 48 | for an amount equal to 3% (three percent) of its Bid Price | Base is Bid Price for security but Contract Price for the advance. Retention is separate (2.3). | Verified exact
BM1 | C6 | 6.3 | Accepted forms | FOUND | Insurance Surety Bond, Account Payee Demand Draft, Banker's Cheque, irrevocable e-Bank Guarantee; physical BG also acceptable till 31.12.2024 |  | Cl. 7.1(i)(A) and footnote | 48 | Account Payee Demand Draft, Banker’s Cheque or an irrevocable and unconditional e-Bank Guaranteeα from a Bank | The footnote with the 31.12.2024 date sits below the clause on the same page. The date has already passed. | Verified exact
BM1 | C6 | 6.4 | Acceptable issuers | FOUND | A bank incorporated in India and recognised by the Reserve Bank of India |  | Cl. 1.1 (Bank) | 17 | a bank incorporated in India and recognized by the Reserve Bank of India | Definition of Bank does not say scheduled or nationalised. | Verified exact
BM1 | C6 | 6.5 | Validity and extension | FOUND | Performance Security valid until 60 days after the Defects Liability Period (may be furnished for 2 years and extended 2 months before expiry); Additional Performance Security valid until 28 days after Project Completion Date | days | Cl. 7.1(i)(B); 7.2 | 48 | The Performance Security shall be valid until 60(sixty) days after the Defects Liability Period. The Additional Performance Security shall be valid until 28 (twenty eight) days after Project Completion Date. | Two validity rules: initial 2-year term with rolling extension, and the final end date. 28 vs 60 days differ by security type. | Verified exact
BM1 | C6 | 6.6 | Encashment grounds | FOUND | On Contractor Default; on termination for Contractor Default; advance guarantee if advance not recovered |  | Cl. 7.3(i); 23.6(i); 19.2(vi)(c) | 49 | Upon occurrence of a Contractor’s Default, the Authority shall, without prejudice to its other rights and remedies hereunder or in law, be entitled to encash and appropriate the relevant amounts from the Performance Security as Damages | After encashment the Contractor must replenish within 30 days or the Authority may terminate (7.3(ii)). | Verified exact
BM1 | C6 | 6.7 | When released | FOUND | Performance Security within 60 days of the end of the Maintenance Period or Defects Liability Period, whichever is later; Additional Performance Security within 28 days of Completion Certificate | days | Cl. 7.4(i) and (ii) | 50 | The Authority shall return the Performance Security to the Contractor within 60 (sixty) days of the expiry of the Maintenance Period or the Defects Liability Period, whichever is later | With a 5 or 10 year defects period, Performance Security stays for years. 9% interest applies if returned late (7.4(iii)). | Verified exact
BM1 | C6 | 6.8 | Extra guarantee requirements | FOUND | Additional Performance Security if bid is more than 20% below estimate: 20% of the shortfall, capped at 3% of Bid Price | % of shortfall | Cl. 7.1(i)(A)(a) and (b) | 48 | If the Bid Price offered by the Selected Bidder is lower than 20% of the Estimated Project Cost/ cost put to tender, the Additional Performance Security shall be calculated @20% of the difference | Wording "lower than 20% of the Estimated Project Cost" is loose: it means a bid more than 20% below estimate. Possible misreading by an LLM. | Verified exact
BM2 | C0 | 0.1 | Contract type and version | FOUND | CPWD-7/8 percentage-rate tender and contract for works, IIT Bombay; standard CPWD contract form GCC 2020 as modified and corrected | text | Schedule F, clause 9(ii) | 106 | 9(ii) Standard CPWD contract Form GCC 2020, CPWD Form 7/ 8 as modified & corrected upto AS INCORPORATED | Schedule F names GCC 2020, but the pack carries IITB-specific edits (Dean (IPS), IITB). The cover is only titled General Conditions of Contract. A model may wrongly say GCC 2023. | Verified exact
BM2 | C0 | 0.2 | Employer and contractor | FOUND | Employer: Indian Institute of Technology Bombay (Director, acting through Dean (IPS)); Contractor: not named (blank form) | text | Tender form CPWD-7/8 | 4 | execution of the work specified for the Director of Indian Institute of Technology , Bombay | Contractor name and acceptance amount are blank, so contractor = NOT_STATED. A model might invent a contractor name. | Verified exact
BM2 | C0 | 0.3 | Contract value / estimated cost | FOUND | Estimated cost Rs 2,12,27,336; earnest money Rs 4,24,547; tendered value = estimate adjusted by the quoted percentage (not fixed here) | INR | Schedule E | 105 | Estimated cost of work: Rs. ₹ 2,12,27,336/- | Percentage-rate tender: final contract value depends on the percentage quoted. Do not report the estimate as the contract price. | Verified exact
BM2 | C0 | 0.4 | Completion period and start basis | FOUND | 9 months (activity table 'Time for assignment'); start reckoned 15 days from date of issue of letter of acceptance | months | Schedule F, clause 5 (pp.106-108) | 107 | TIME FOR ASSIGNMENT 09 (Nine) Months (From 0 to 9) – (in months) | Schedule F line Time allowed for execution of work is left blank (p.108). The only number is in an activity table headed Consultancy/Assignment, which looks pasted from a consultancy document. Start: p.106 says 15day after letter of acceptance. Clause 5: start = Schedule F period or site handover, whichever later. | Verified exact
BM2 | C0 | 0.5 | Defect liability period | FOUND | 12 months after completion certificate (6 months if work costs Rs 10 lacs or less, except road work) | months | Clause 17 | 41 | if any defect, shrinkage or other faults appear in the work within twelve months (six months in the case of work costing Rs. Ten lacs and below except road work) | Printed Rs. Ten lacs here; the deposit refund line says Ten lakhs. At the Rs 2.12 crore estimate the 12-month limb applies. | Verified exact
BM2 | C0 | 0.6 | Milestones | FOUND | Activity periods only: shop drawings 1 month; execution drawings 15 days; planning, procurement and execution 7 months; post-construction 15 days; total 9 months. No work-percentage or withholding amounts stated | months | Schedule F, clause 5 (pp.106-108) | 107 | C Project Planning: Preparation/Submission of CPM/PERT Chart for Procurement, Material delivery, Installation, testing & Commissioning activities 07 (Seven) months | Clause 2 says the amount shown against that milestone is withheld, but no amounts appear anywhere in Schedule F. The table is not a financial milestone table. A model may fabricate percentages. | Verified exact
BM2 | C1 | 1.1 | Billing basis and frequency | FOUND | Monthly running account bills on measured work for works estimated above Rs 20 lac; no payment before completion for works of Rs 20 lac or less | text | Clause 7 | 24 | For works estimated to cost over Rs, Twenty lac the interim or running account bills shall be submitted by the contractor | Estimate is Rs 2.12 crore, so monthly running bills apply, on a date fixed each month by the Engineer-in-Charge. | Verified exact
BM2 | C1 | 1.2 | Days for employer to certify or measure a bill | NOT_STATED | No separate certification period stated |  | Clause 7 | 0 |  | Searched clauses 6, 7 and 7A. The only deadline is the combined payment deadline (see 1.3). A model may split it into certification and payment periods. | No quote
BM2 | C1 | 1.3 | Days to pay certified amount | FOUND | 10 working days after presentation of the bill (15 working days for works outside the Engineer-in-Charge's headquarters) | working days | Clause 7 | 25 | The amount admissible shall be paid by 10th working day after the day of presentation of the bill by the Contractor to the Engineer-in-Charge or his Authorized Engineer | The 15-working-day extension is in the following sentence. Do not confuse with the 45-day interest trigger in 1.4. | Verified exact
BM2 | C1 | 1.4 | Interest on delayed payment | FOUND | Simple interest 5% a year on interim bills unpaid 45 days after submission (if bill in order); final bill delay also 5% simple. Delay by contractor in submitting a bill after an advance on materials: 10% a year payable to IITB | % a year | Clause 7 and clause 9 | 25 | after 45 days of submission of bill by the contractor pr ovided the bill submitted by the contractor found to be in order, a simple interest @ 5% (five percent) per annum | Text says simple interest compounded on yearly basis, which contradicts itself. The 45-day trigger is later than the 10-working-day payment date. Final bill interest 5% is on p.26. | Verified exact
BM2 | C1 | 1.5 | Deductions from each bill | FOUND | Security deposit 5% of gross running and final bill; recovery of mobilisation advance (clause 10B); recovery of secured advance when materials are used; compensation and milestone amounts withheld (clause 2) | text | Clause 1A and others | 16 | to deduct a sum at the rate of 5 % of the gross amount of each running and final bill till the sum deducted will amount to security deposit of 5% of the tendered value of the work | GST on inputs is the contractor's cost (General Rules 13, p.9). No TDS clause found. Only the retention quote is cited; other deductions come from clauses 2 and 10B. | Verified exact
BM2 | C1 | 1.6 | Minimum bill value or interim payment cap | FOUND | Minimum gross work Rs 30 lakhs (net of advances) before an interim payment is due | INR | Schedule F, clause 7 | 109 | Clause 7 Gross work to be done together with net payment /adjustment of advances for material collected, if any, since the last such payment for being eligible to interim payment 30 lakhs | Two thresholds: Rs 20 lac (clause 7 text) and Rs 30 lakhs (Schedule F minimum bill). A model may mix them up. | Verified exact
BM2 | C1 | 1.7 | Final bill timeline | FOUND | Final bill within 3 months of physical completion or 1 month of final completion certificate, whichever earlier; payment within 2 / 3 / 6 months of receipt by tendered value (up to Rs 1 Cr / Rs 1-10 Cr / above Rs 10 Cr); 5% simple interest if late | months | Clause 9 | 26 | within three months of physical completion of the work or within one month of the date of the final certificate of completion furnished by the Engineer-in-Charge whichever is earlier | For a Rs 2.12 crore estimate the 3-month payment limb applies. No claims after the final bill. | Verified exact
BM2 | C1 | 1.8 | Conditional payment (pay when paid) | NOT_STATED | No pay-when-paid or funding condition |  | Clauses 7, 9, 9A | 0 |  | Searched pay when paid and back to back. Back to back construction on p.47 is about labour hut layout, and back to back basis on p.4 is about subletting; neither is a payment condition. The composite-contract rule (main contractor pays associates within 15 days, p.25) is not pay-when-paid. | No quote
BM2 | C2 | 2.1 | Is retention / security deposit deducted | FOUND | Yes, security deposit deducted from running and final bills | yes/no | Clause 1A | 16 | to deduct a sum at the rate of 5 % of the gross amount of each running and final bill | Performance guarantee (5%) is a separate item from the security deposit. | Verified exact
BM2 | C2 | 2.2 | Percentage and base | FOUND | 5% of gross amount of each running and final bill (Schedule E: 5% of tendered value) | % | Clause 1A; Schedule E | 105 | (iii) Security Deposit : 5% of tendered value | Other CPWD documents use 2.5%; this IITB pack says 5%. Do not import the 2.5% figure. | Verified exact
BM2 | C2 | 2.3 | Cap on total retention | FOUND | Deductions continue until total reaches 5% of tendered value | % of tendered value | Clause 1A | 16 | till the sum deducted will amount to security deposit of 5% of the tendered value of the work | Cap equals the rate in percent terms, but the rate applies to the bill and the cap to the tendered value. | Verified exact
BM2 | C2 | 2.4 | Earnest money converted into retention | FOUND | No. Earnest money is returned after the performance guarantee is received | yes/no | Schedule E | 105 | (i) Earnest money: Rs. 4,24,547/- (to be returned after receiving performance guarantee) | Some CPWD documents let earnest money count toward the deposit; this pack does not say so. | Verified exact
BM2 | C2 | 2.5 | Release of retention | FOUND | Not before 12 months after completion certificate (6 months for works of Rs 10 lakhs or less, except road work), or until the final bill is prepared and passed, whichever is later; labour clearance certificate also needed (clause 41) | months | Clause 17 (and clause 41) | 41 | shall not be refunded before the expiry of twelve months (six months in the case of work costing Rs. Ten lakhs and below except road work) after the issue of the certificate final or otherwise, | Quote stops before whichever is later (next words). Road works have a half-and-half release; E&M maintenance works refund within one month. | Verified exact
BM2 | C2 | 2.6 | Replacement by bank guarantee | FOUND | Yes, on accumulations of at least Rs 5 lac; each guarantee except the last at least Rs 5 lac; validity per clause 17 and extended with time | text | Clause 1A | 16 | The security deposit as deducted above can be released against bank guarantee issued by a scheduled bank, on its accumulations to a minimum of Rs. 5 lac | The Rs 5 lac floor appears twice in the sentence. | Verified exact
BM2 | C2 | 2.7 | Interest paid on retention | NOT_STATED | No interest on security deposit stated |  | Clause 1A, 17 | 0 |  | Searched interest near security deposit. The only mention is interest arising from deposits held in securities; clause 29A says no interest on sums withheld under lien. A model may assume interest is payable. | No quote
BM2 | C3 | 3.1 | Is a mobilisation advance given | POINTS_ELSEWHERE | Clause 10B(ii) allows it at the Engineer-in-Charge's discretion, but Schedule F leaves Yes/No for applicability unselected | yes/no | Clause 10B(ii); Schedule F | 109 | Clause 10B(ii) Whether Clause 10 B (ii) shall be applicable Yes/No | Schedule F entry is not filled in, so applicability is undecided. A model may say Yes because the general clause exists. | Verified exact
BM2 | C3 | 3.2 | Percentage and instalments | FOUND | Up to 10% of tendered value; in two or more instalments decided by the Engineer-in-Charge | % of tendered value | Clause 10B(ii) | 28 | Mobilization advance not exceeding 10% of the tendered value may be given | Not exceeding means a maximum, not an entitlement. Instalments are in the next sentence of the same clause. | Verified exact
BM2 | C3 | 3.3 | Interest on advance | FOUND | Simple interest 10% a year from date of payment to date of recovery, on the outstanding balance | % a year | Clause 10B(iii) | 28 | bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery | Interest runs on the outstanding advance until each recovery. The sentence continues on p.29. | Verified exact
BM2 | C3 | 3.4 | Recovery method | FOUND | Deducted from bills after the first 10% of gross work is paid, pro rata on work beyond 10%, so the entire advance plus interest is recovered by the time 80% of gross contract value is executed and paid | % of work | Clause 10B(iii) | 29 | on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the contract | Two percentages (10% start, 80% end) in one sentence. The clause starts on p.28 and carries over to p.29. | Verified exact
BM2 | C3 | 3.5 | Security for the advance | FOUND | Bank guarantee bonds, not more than 6, from a scheduled bank for 110% of the advance, valid until recovery and renewed to cover the balance | % of advance | Clause 10B(ii) | 28 | Before any installment of advance is released, the contractor shall execute a Bank Guarantee Bonds not more than 6 in number from Scheduled Bank for the amount equal to 110% of the amount of advance | 110% applies to the advance and later to the balance amount. | Verified exact
BM2 | C3 | 3.6 | Plant and machinery or secured advance on materials | FOUND | Secured advance on materials: up to 75% of assessed value or of material element cost, whichever is lower. No plant and machinery advance | % of material value | Clause 10B(i) | 28 | up to 75% of the assessed value of any materials or an amount not exceeding 75% of the material element cost in the tendered rate of the finished item of the work, whichever is lower | Plant and machinery advance is not provided in this pack. Headings Secured Advance on Materials and Mobilization advance are merged in extraction. | Verified exact
BM2 | C3 | 3.7 | Conditions to receive the advance | FOUND | Written request within one month of order to commence; bank guarantee before each instalment; second and later instalments only after proof of satisfactory utilisation of the earlier one | text | Clause 10B(ii) and (iv) | 28 | if requested by the contractor in writing within one month of the order to commence the work | The Engineer-in-Charge may extend the one-month window (clause 10B(iv), p.29). | Verified exact
BM2 | C4 | 4.1 | Does contract impose delay damages | FOUND | Yes, called compensation for delay | yes/no | Clause 2 | 17 | pay as compensation the amount calculated at the rates stipulated below as the authority specified in schedule 'F' may decide on the amount of accepted Tendered Value of the work | Wording is compensation, not liquidated damages. The words liquidated damages never appear in this pack. | Verified exact
BM2 | C4 | 4.2 | Rate and base | FOUND | Maximum 1% of accepted Tendered Value per month of delay, computed per day; the actual rate is decided by the authority named in Schedule F (Deputy Director (FEA), IITB) | % per month | Clause 2; Schedule F | 17 | with maximum rate @ 1% (one percent) per month of delay to be computed on per day basis based on quantum of damage suffered due to stated delay on the part of Contractor | Schedule F does not state an actual rate, only the authority. The text gives 1% as a maximum based on quantum of damage suffered. | Verified exact
BM2 | C4 | 4.3 | Cap on damages | FOUND | 10% of accepted Tendered Value of work (or of the sectional part if a separate period applies) | % of tendered value | Clause 2 | 17 | shall not exceed 10 % (ten percent) of the accepted Tendered Value of work or of the accepted Tendered Value of the Sectional part of work | Cap is reached after about 10 months at the 1% maximum rate. | Verified exact
BM2 | C4 | 4.4 | Final completion only or milestones too | FOUND | Both: delay at completion and shortfall against progress; amounts shown against missed milestones are withheld automatically and released if the contractor catches up | text | Clause 2, Clause 5 | 18 | In case, the contractor does not achieve a particular milestone mentioned in schedule F, or the re-scheduled milestone(s) in terms of Clause 5.4, the amount shown against that milestone shall be withheld | Milestone amounts are not filled in Schedule F (see 0.6), so the mechanism exists but has no numbers. | Verified exact
BM2 | C4 | 4.5 | Extension of time | FOUND | Events: force majeure, abnormally bad weather, fire, strikes or civil commotion, delay by other contractors, other causes beyond control; Institute-caused hindrance; request within 14 days on the prescribed form; decision within 21 days; extra time for deviations per clause 12.1 | days | Clause 5.2 to 5.4 | 22 | Request for rescheduling of Mile stones or extension of time, to be eligible for consideration, shall be made by the Contractor in writing within fourteen days of the happening of the event causing delay | Events in 5.2 give extension of time only, no money. Deviation extension is clause 12.1 (p.35). | Verified exact
BM2 | C4 | 4.6 | Pre-estimate of loss or proof of loss | FOUND | Not described as a pre-estimate. The 1% is a maximum based on quantum of damage suffered; no express requirement for the employer to prove loss; without prejudice to other legal remedies | text | Clause 2 | 17 | based on quantum of damage suffered due to stated delay on the part of Contractor | Whether loss must be shown is a legal question (Section 74; see register court judgments). A model should not state either answer as fact. | Verified exact
BM2 | C4 | 4.7 | Deductible from bills, retention or guarantee | FOUND | Yes: set off against any sum payable under this or any other contract with IITB; also recoverable from the security deposit | text | Clause 2; Clause 1A | 18 | The amount of compensation may be adjusted or set -off against any sum payable to the Contractor under this or any other contract with the IITB | Cross-contract set-off is notable. Deduction from the security deposit is on p.16. | Verified exact
BM2 | C4 | 4.8 | Other damages or penalties | FOUND | Completion plans not submitted: 0.1% of tendered value or Schedule F limit; late performance guarantee: late fee 0.1% a day of guarantee amount (Schedule F); late progress report and late revised programme: recovery per Schedule F; penalties under clauses 19C, 19D, 19G, 19K set by Dean IPS (amounts blank); technical representative shortfall: Rs 1,00,000 a month (senior) and Rs 60,000 a month | text | Clauses 1, 5.1, 5.4, 8A, 19, 32; Schedule F | 26 | he shall be liable to pay a sum of 0.1 % (zero point one percent) of accepted Tendered Value or limit prescribed in Schedule F whichever is more | Several small charges sit in different places. A model may miss the Schedule F recoveries on pp.106 and 111-112. | Verified exact
BM2 | C5 | 5.1 | Fixed price or price variation | POINTS_ELSEWHERE | Price variation clauses are present (10C statutory changes, 10CA materials, 10CC general escalation), but Schedule F leaves Applicable / Not Applicable unselected for 10CA and 10CC; 10CC applies only if the period exceeds 12 months | text | Clauses 10C, 10CA, 10CC; Schedule F | 110 | Clause 10CC Applicable/ Not Applicable Clause 10 CC to be applicable in contracts with stipulated period of completion exceeding the period shown in next column 12 (Twelve) months | Work period is about 9 months (see 0.4), below the 12-month threshold, so 10CC would not apply if 9 months is the period. A model may say escalation applies from the general text. | Verified exact
BM2 | C5 | 5.2 | Formula | FOUND | 10CA: V = P x Q x (CI - CIo)/CIo per material. 10CC materials: Vm = W x Xm x (MI - MIo)/MIo. 10CC labour: VL = W x Y x (LI - LIo)/LIo. W = 0.85 x cost of work done (M = C + F + I - J) | formula | Clauses 10CA and 10CC | 30 | V= P X Q X CI – CIO CIO V = Variation in material cost i.e. increase or decrease in the amount of rupees to be paid or recovered | Formulas are garbled in text extraction; the 10CC ones are on pp.32-33. Check the layout on the PDF page before copying. | Verified exact
BM2 | C5 | 5.3 | Components and weights | FOUND | 10CA base prices: cement Rs 6295, steel Rs 61045, structural steel Rs 67970 (units not stated); 10CC: materials Xm 40% and labour Y 25% of value of work (balance 35% implied for 10CA materials) | % / INR | Schedule F, clauses 10CA, 10CC | 110 | Component of civil (except materials covered under clause 10CA) /Electrical construction Xm 40 % value of work. - Component of Labour - expressed as percent of total value of work. Y 25 % | Schedule F clause 10C labour component on p.109 is blank (separate from Y = 25%). The 35% balance is derived, not printed. POL has no base price listed. | Verified exact
BM2 | C5 | 5.4 | Index and source | FOUND | Cement, steel reinforcement, structural steel and POL: price indices issued by Director General, CPWD. Other materials: All India Wholesale Price Index (Economic Adviser, Ministry of Commerce and Industry). Labour: minimum daily wage of an unskilled mazdoor under law | text | Clause 10CA, 10CC | 30 | The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices issued by the Director General, CPWD. | Two index sources, plus a wage notification for labour. A model may name only WPI. | Verified exact
BM2 | C5 | 5.5 | Base date | FOUND | 10CC: last stipulated date of receipt of tenders including extensions. 10CA: base price and its period as indicated in Schedule F (periods not stated) | date | Clause 10CC(i) | 31 | (i) The base date for working out such escalation shall be the last stipulated date of receipt of tenders including extension, if any. | Tender due date is 27.04.2023 (p.4). Extensions are unknown. Schedule F base-price periods are blank. | Verified exact
BM2 | C5 | 5.6 | Threshold or cap | FOUND | No payment (and no downward adjustment) if stipulated period is equal to or less than the Schedule F time (12 months); escalation computed on 85% of work value; no percentage absorbed and no cap stated | months | Clause 10CC | 31 | No such compensation shall be payable for a work for which the stipulated period of completion is equal to or less t han the time as specified in Schedule F. | The extracted text has less t han. Escalation is quarterly. The 0.85 factor comes from N = 0.85 M on p.32. | Verified exact
BM2 | C5 | 5.7 | Escalation after original completion date | FOUND | Escalation is paid only for work done during the stipulated period including justified extensions granted without action under clause 2 | text | Clause 10CC | 31 | shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2 | If compensation for delay is levied, the extension is not justified and escalation stops. | Verified exact
BM2 | C5 | 5.8 | Escalation on employer-supplied materials | FOUND | No: materials supplied by the department at fixed prices are excluded | yes/no | Clause 10CC | 31 | (not being materials supplied or services rendered at fixed prices by the department in accordance with clause 10 & 34 thereof) | Clause 10C and 10CA wording on employer materials was not checked in detail. | Verified exact
BM2 | C6 | 6.1 | Securities required | FOUND | Earnest money Rs 4,24,547 (returned after performance guarantee); performance guarantee 5% of tendered value; security deposit 5%; bank guarantees for mobilisation advance (110%) and for replacing the deposit; Schedule F late fee on late performance guarantee | text | Schedule E; Clauses 1, 1A, 10B | 105 | (i) Earnest money: Rs. 4,24,547/- (to be returned after receiving performance guarantee) (ii) Performance Guarantee : 5% of tendered value. | No separate bid security besides earnest money. No additional performance security for low bids. | Verified exact
BM2 | C6 | 6.2 | Amount or percentage and base | FOUND | Performance guarantee 5% of tendered amount; security deposit 5% of tendered value; earnest money Rs 4,24,547; advance guarantee 110% of the advance | % / INR | Clause 1 | 15 | The contractor shall submit an irrevocable Performance Guarantee of 5% (Five percent) of the tendered amount | Earnest money equals 2% of the estimate (Rs 4,24,547 against Rs 2,12,27,336), but the 2% rate is not stated. | Verified exact
BM2 | C6 | 6.3 | Forms accepted | FOUND | Cash (under Rs 10,000), deposit at call receipt, banker's cheque, demand draft or pay order (under Rs 1,00,000), government securities, fixed deposit receipt, guarantee bonds of a scheduled bank or SBI | text | Clause 1 | 15 | This guarantee shall be in the form of Cash (in case guarantee amount is less than Rs. 10,000/-) or Deposit at Call receipt of any scheduled bank/Banker's Cheque of any scheduled bank/Demand Draft of any scheduled bank | No mention of e-bank guarantees or insurance surety bonds, which newer CPWD documents allow. A model may add them from general knowledge. | Verified exact
BM2 | C6 | 6.4 | Acceptable issuers | FOUND | Any scheduled bank or the State Bank of India | text | Clause 1 | 15 | Guarantee Bonds of any Scheduled Bank or the State Bank of India | A fixed deposit receipt of any bank: loss from a failed bank falls on the contractor. | Verified exact
BM2 | C6 | 6.5 | Validity and extension | FOUND | Performance guarantee valid to stipulated completion date plus 60 days (Format I) or plus 6 months (Format II), and extended if time is extended; guarantee against deposit follows clause 17 and is extended with time | days / months | Clause 1(ii) | 15 | The Performance Guarantee shall be initially valid up to the stipulated date of completion plus minimum 60 days beyond that, if the same is submitted by the agency on scheduled format I as per GCC. | Two bond formats (pp.103-104) give two different validity periods. A model may state only one. | Verified exact
BM2 | C6 | 6.6 | Grounds for encashment | FOUND | Failure to extend validity (full amount claimable); failure to pay amounts due within 30 days of notice; forfeited in full if contract is determined or rescinded; forfeited if contractor fails to start work | text | Clause 1(iii), (iv); Clause 5 | 15 | (b) Failure by the contractor to pay Director of Indian Institute of Technology Bombay any amount due | Guarantee is payable on demand without regard to disputes (bond format, p.103). The 30-day notice period follows in the same sentence. | Verified exact
BM2 | C6 | 6.7 | Release | FOUND | Returned without interest after completion certificate; 80% returned after provisional completion certificate (40% if the contract includes maintenance); in maintenance contracts 50% is retained as security deposit and returned year by year | % / text | Clause 1(ii), (v) | 16 | After recording of the provisional Completion Certificate for the work by the competent authority, the 80 % of performance guarantee shall be returned to the contractor, without any interest. | Page 15 says the guarantee is returned after the completion certificate; p.16 adds the 80% release at provisional completion. A model may report only one. | Verified exact
BM2 | C6 | 6.8 | Extra guarantee requirements | NOT_STATED | No additional performance security for abnormally low bids |  | Clause 1 | 0 |  | Searched additional performance, abnormally low, below the estimated. Not found. The 0.1% a day late fee on the guarantee amount (Schedule F, p.106) is a charge, not an extra guarantee. | No quote
BM3 | C0 | 0.1 | Type and version of contract | FOUND | Percentage-rate works tender, Appendix 2.10 (MP works departments), effective 23.07.2014; NIT No. 03 dated 05.08.2021 |  | Cover page | 1 | APPENDIX 2.10 For Percentage Rate only in works departments and other Departments similar to work departments (EFFECTIVE FROM 23.07.2014) OFFICE | State-government percentage-rate form with GCC, Contract Data and Annexures. Contract Data (pp. 61-65) overrides general text. | Verified exact
BM3 | C0 | 0.2 | Employer and contractor | FOUND | Employer: Managing Director, M.P. State Agro Industries Development Corp., Bhopal; Engineer-in-Charge: Executive Engineer H.O. Bhopal; contractor: not named (blank) |  | Contract Data 1.14-1.16 | 61 | 1.14 Employer Managing Director M.P.State Agro Ind. Dev. Corpn. Bhopal 1.15 Engineer Executive Engineer | Contractor name is blank because this is the issued tender, not the signed contract. | Verified exact
BM3 | C0 | 0.3 | Contract value | FOUND | Probable amount of contract Rs 188.65 lakh; contract amount blank | Rs lakh | Cover page | 1 | 188.65 Lacs One Crore Eighty Eight Lacs Sixty Five Thousand Only | Earnest money Rs 188,650 is a separate figure (p. 16). Do not confuse the EMD digits with the contract value. | Verified exact
BM3 | C0 | 0.4 | Stipulated completion period and start basis | FOUND | 12 months including rainy season; time runs from date of signing the agreement | months | Contract Data 1.22; GCC 15.2 | 49 | 15.2 The time allowed for execution of the contr act shall commence from the da te of signing of the agreemen t. | Period (12 months) is on pp. 1, 4 and 61; start basis is in GCC 15.2. Two different pages. | Verified exact
BM3 | C0 | 0.5 | Defect liability period | FOUND | Building works 3 years; new bituminous or concrete road 5 years; bridge works 3 years; building maintenance 1 year | years | Contract Data 12 | 62 | (C) FOR BUILDING WORKS — 3 (THREE) YEARS | Work mixes building and road items, so more than one period could apply. Quote gives the building period only. | Verified exact
BM3 | C0 | 0.6 | Milestones | FOUND | Milestone 1: 1/8 of work before 1/4 of time; Milestone 2: 3/8 before 1/2 of time; Milestone 3: 3/4 before 3/4 of time; Milestone 4: complete within stipulated time |  | Contract Data 10; Annexure O | 62 | Mile Stone 1:- 1/8th of the whole work before 1/4th of the whole time allowed has elapsed, Mile Stone 2:- 3/8th of the whole work before 1/2th of the whole time allowed has elapsed Mile Stone | Annexure O says milestones are "As per Contract Data", so the real list sits on p. 62. | Verified exact
BM3 | C1 | 1.1 | Billing basis and frequency | FOUND | Monthly statements of value of work executed, based on measurements | monthly | GCC 34(a) | 56 | (a) The Contractor shall submit to the Engineer monthly statements of the value of the work e xecuted less t he cumulative | Price adjustment would be worked out quarterly (GCC 31.2) but is not applicable here. | Verified exact
BM3 | C1 | 1.2 | Days for employer to certify an interim bill | NOT_STATED |  | days |  | 0 |  | Searched GCC 34, Contract Data pp. 61-65, Annexure-1, Bid Data Sheet. The only time limits are for the final account (21 and 45 days) and dispute decisions. A model that supplies 30 days has invented it. | No quote
BM3 | C1 | 1.3 | Days for employer to pay a certified bill | NOT_STATED |  | days |  | 0 |  | Same search as 1.2. No payment period for interim bills in the English text. Pages 87-93 hold circulars as images with no readable text, so they could not be searched. | No quote
BM3 | C1 | 1.4 | Interest on delayed payment | FOUND | No interest payable on any payment due or awarded |  | GCC 23 | 52 | 23. No Interest Payable No interest shall be payable to the Contractor on any payment due or awarded by | The answer is a negative. A model may wrongly import a standard interest rate. | Verified exact
BM3 | C1 | 1.5 | Deductions from each bill | FOUND | Advance payment recovery, security deposit, other contract recoveries, taxes deducted at source |  | GCC 34(f) | 57 | (f) All payment s shall be adjusted for d eductions for ad vance payment, security deposit, other recoveries in terms of c ontract and taxes at sou | Security deposit rate is 5% (Contract Data 17). Hindi special conditions mention GST and a 3.5% PF-related deduction (legacy font, not machine-readable). | Verified exact
BM3 | C1 | 1.6 | Minimum bill value or cap on interim payment | NOT_STATED |  |  |  | 0 |  | Searched GCC 34 and Contract Data. None found. | No quote
BM3 | C1 | 1.7 | Final bill and final payment timeline | FOUND | Contractor submits final account within 21 days of physical completion certificate; Engineer certifies payment within 45 days of receiving a correct and complete account | days | GCC 36.1 | 58 | The Engineer s hall issue a Defects Li ability Certi ficate and certify any pa yment that is due to th e Contractor within 45 d ays of r eceiving | The 21-day figure is in the sentence just before the quote. If the contractor is late, the Engineer finalises and issues a payment certificate within 28 days (36.2). | Verified exact
BM3 | C1 | 1.8 | Conditional payment (pay when paid) | NOT_STATED |  |  |  | 0 |  | Searched GCC 34 and 23. No pay-when-paid term. GCC 34(h) says interim payments are advances against final payment, which is a different point. | No quote
BM3 | C2 | 2.1 | Is retention or security deposit deducted | FOUND | Yes, security deposit deducted from each running bill |  | Annexure-1 GCC 30 | 2 | GCC Clause 30 — SECURITY DEPOSIT to be deducted from each running bill @ | Retention is called "Security Deposit" in this form. A model searching only for the word "retention" will miss it. | Verified exact
BM3 | C2 | 2.2 | Percentage and base | FOUND | 5% of gross amount of each running bill | % of gross running bill | Contract Data 17 | 64 | 17 Security Deposit to be deducted from each running bill At the rate of 5% of Gross | Annexure-1 gives 5% too. Both agree. | Verified exact
BM3 | C2 | 2.3 | Cap on total retention | FOUND | Up to 5% of final contract amount | % of final contract amount | Contract Data 17 | 64 | Maximum limit of deduction of Security Deposit Up to 5% of |  | Verified exact
BM3 | C2 | 2.4 | Earnest money converted or counted into retention | NOT_STATED |  |  |  | 0 |  | Searched ITB pp. 6-13, Bid Data Sheet, Annexure L. EMD is forfeited in some cases but nothing says it is returned or counted toward security deposit. | No quote
BM3 | C2 | 2.5 | Release timing | FOUND | Refunded on completion of defect liability period |  | GCC 30.3 | 54 | 30.3 The Security deposits shall be refunded of completion of defect liability period. The | Defect liability period for buildings is 3 years, so release is late. Link to 0.5. | Verified exact
BM3 | C2 | 2.6 | Replacement by bank guarantee | FOUND | Yes, by equivalent bank guarantee or fixed deposit receipt valid up to 3 months beyond defect liability period |  | GCC 30.2 | 54 | 30.2 The security deposit may be replaced b y equ ivalent amount o f bank guarantee or fixed deposit r eceipt assigned to the Em ployer, w ith validity up |  | Verified exact
BM3 | C2 | 2.7 | Interest on retention | NOT_STATED |  |  |  | 0 |  | No clause on interest for security deposit. GCC 23 says no interest on any payment due, which a reader may apply by implication. | No quote
BM3 | C3 | 3.1 | Mobilisation advance given | NOT_APPLICABLE | No mobilisation and construction machinery advance is payable |  | Contract Data 19; GCC 32.1 | 64 | Clause 32.1 Mobilization and Construction Machinery Advance Applicable No Mobilization and Construction Machinery | GCC 32 describes the advance as a general clause, then Contract Data switches it off. A model reading only GCC 32 will report an advance. | Verified exact
BM3 | C3 | 3.2 | Percentage or amount and instalments | NOT_APPLICABLE | Not applicable |  | Contract Data 32.4 | 64 | Clause 32.4 If yes, Type & Amount of Advance payment that can be paid Not Applicable |  | Verified exact
BM3 | C3 | 3.3 | Interest-free or interest-bearing | NOT_APPLICABLE | Not applicable |  | Contract Data 32.3 | 64 | Clause 32.3 If yes, Rate of interest chargeable on advances Not Applicable Clause | GCC 32.2 says interest-bearing if an advance were given. | Verified exact
BM3 | C3 | 3.4 | Recovery of advance | NOT_APPLICABLE | Not applicable |  | Contract Data 32.5 | 64 | Clause 32.5 If yes, Recovery of advance payment Not Applicable 20 Clause |  | Verified exact
BM3 | C3 | 3.5 | Security for advance | NOT_APPLICABLE | Not applicable. A bank guarantee form for advances is attached (Annexure S) but unused |  | Contract Data 32.2 | 64 | Clause 32.2If yes, Unconditional Bank Guarantee Not Applicable Clause | Annexure S (p. 72) is a blank guarantee form for the mobilisation advance. Its presence does not mean an advance is given. | Verified exact
BM3 | C3 | 3.6 | Plant and machinery or secured advance | NOT_APPLICABLE | No secured advance; no construction machinery advance |  | Contract Data 20; Annexure-1 GCC 33 | 64 | Clause 33.1 Secured Advance Applicable Not Applicable Clause | Annexure T (secured advance indenture, 12% interest on default) is also a blank form only. | Verified exact
BM3 | C3 | 3.7 | Conditions to receive an advance | NOT_APPLICABLE | Not applicable |  | Contract Data 33.3 | 65 | Clause 33.3 if yes, Conditions for secured advance Not Applicable Clause |  | Verified exact
BM3 | C4 | 4.1 | LD for delay | FOUND | Yes. Contract Data points to Annexure P for the scale |  | GCC 15.4; Contract Data 10 | 49 | 15.4 Failure of the Contr actor to adhere to the tim elines and/or milestones shall attract such liquidated damages as is laid down in the Contract Data. 15.5 | GCC 15.4 alone says "as laid down in the Contract Data", which points on to Annexure P (p. 68). The rate is stated there, not missing. | Verified exact
BM3 | C4 | 4.2 | Rate and base | FOUND | Milestone slippage: amount retained of 2.5%, 5%, 7.5% or 10% of the work remaining unexecuted (by slippage band); final delay: 0.05% of contract price per day | % per day of contract price | Annexure P | 68 | the compensation shall b e levied on the con tractor at t he rate of 0 .05% pe r day of delay limited to a maximum o f 1 0% | Extracted text splits digits ("0 .05%", "1 0%"). Confirm 0.05% and 10% on the PDF page. Two mechanisms: milestone retention and final-delay compensation. | Verified exact
BM3 | C4 | 4.3 | Maximum cap | FOUND | 10% of contract price | % of contract price | Annexure P | 68 | the compensation shall b e levied on the con tractor at t he rate of 0 .05% pe r day of delay limited to a maximum o f 1 0% | Cap applies to the per-day compensation after the stipulated completion. Milestone retention is refundable if slippage is made good. See also 4.2. | Verified exact
BM3 | C4 | 4.4 | Final completion only or also milestones | FOUND | Both. Milestone slippage leads to retention that is refunded if made good; delay beyond final completion leads to per-day compensation |  | Annexure P | 68 | i. Slippage up to 25% in financial target during the milestone under consideration - 2.5% of the work remained unexecuted in the related time | Termination trigger in Contract Data 14: less than 50% progress in a milestone or less than 75% in two consecutive milestones. | Verified exact
BM3 | C4 | 4.5 | Extension of time | FOUND | Competent authority grants extension within 30 days of application; up to 30 days by Executive Engineer, beyond 30 days by Managing Director | days | GCC 14.2; Contract Data 9 | 49 | 14.2 The compet ent auth ority shall grant such extension at each such occasion within a period of 30 days of r eceipt of application from | Delays not attributable to the contractor are excluded when counting milestone slippage (Annexure P note). | Verified exact
BM3 | C4 | 4.6 | Pre-estimate of loss or proof of loss | NOT_STATED |  |  |  | 0 |  | Searched GCC 15, Annexure P. No genuine pre-estimate wording and no requirement to prove loss. GCC 15.6 only corrects overpaid LD after an extension. | No quote
BM3 | C4 | 4.7 | Deduction from bills, retention or guarantee | FOUND | Engineer retains the LD amount from the contractor bills; bankable security accepted instead; recovery from performance security and security deposit also allowed |  | GCC 15.5; GCC 24 | 49 | 15.5 In the event of delay in e xecution of the Works as per the timelines mentioned in the Contract Data the En gineer-in-charge shall r etain from the bills of the Contractor amount eq ual to the liquidated d | GCC 24 (p. 52) separately allows recovery from performance security, additional performance security and security deposit. | Verified exact
BM3 | C4 | 4.8 | Other LD or penalties | FOUND | Field laboratory not set up: 1% of contract amount per month, max Rs 50,000 per month; technical personnel missing: Rs 30,000 a month per graduate engineer and Rs 18,000 per diploma engineer; construction programme not submitted: 1% of contract amount, max Rs 50,000; termination penalty adds 20% of value of work not completed |  | Contract Data 5, 8, 11, 15 | 62 | Penalty for not establishing field Laboratory 1% of Contract Amount per month, subject to a maximum of Rs. 50,000/- per month of | Several penalties spread over pp. 61-63. A model often reports only the delay compensation. | Verified exact
BM3 | C5 | 5.1 | Fixed price or price variation clause | FOUND | Fixed price for this tender. Price adjustment applies only if the amount in the NIT is more than Rs 10 crore; this tender is Rs 1.89 crore |  | Annexure-1 GCC 31; Contract Data 18 | 2 | Price Adjustment shall be applicable only in case where the Amount in N.I.T. is more than Rs. 10 (Ten) Crores. This clause | Needs reasoning: the clause and formulas exist in the document but are inactive for this contract. A model that lists the formulas as active is wrong. Hindi special conditions (item 3, legacy font) also say the price escalation condition is not part of the agreement even if time is extended. | Verified exact
BM3 | C5 | 5.2 | Formula | FOUND | Cement: Vc = 0.85 x Pc/100 x R x (C1 - C0)/C0; similar formulas for steel, bitumen and POL. Inactive for this contract |  | Annexure R | 70 | Vc= 0.85 x pc/100 x R x | Formula is in the document but not applicable. The steel and POL formulas in the extracted text have character errors. | Verified exact
BM3 | C5 | 5.3 | Components and weights | FOUND | Contract Data: cement 18%, steel 13%. Annexure R: cement 20%, steel 20%. Bitumen and POL components named but no weights given | % of work | Contract Data 31.2.4; Annexure R | 64 | Clause 31.2.4 Weight ages of Component in the work Component Percentage of Component in the work Cement 18% Steel | The two places disagree (18/13 against 20/20). The Contract Data is the one the form says to use. Annexure R text is on p. 70. Only matters if price adjustment applied. | Verified exact
BM3 | C5 | 5.4 | Index and source | FOUND | Cement: all-India WPI for grey cement; steel: all-India WPI for bars and rods; bitumen: IOC depot retail price; POL: IOC retail price of high speed diesel; WPI from the Ministry of Industrial Development site (eaindustry.nic.in) |  | Annexure R | 70 | The all I ndia wholesale price i ndex for Grey cement on the date of o pening o f Bids a s published by the M inistry | Bitumen and POL use IOC retail prices, not WPI. Text in Annexure R has stray spaces. | Verified exact
BM3 | C5 | 5.5 | Base date | FOUND | Date of opening of bids |  | Annexure R | 70 | The all I ndia wholesale price i ndex for Grey cement on the date of o pening o f Bids a s published by the M inistry | Same passage as 5.4 for cement. Bitumen and POL base prices are also taken at bid opening. | Verified exact
BM3 | C5 | 5.6 | Threshold or cap on adjustment | NOT_STATED |  | % |  | 0 |  | No percentage threshold or ceiling in GCC 31, Contract Data 18 or Annexure R. The Rs 10 crore figure is an applicability limit (see 5.1), not an absorption threshold. | No quote
BM3 | C5 | 5.7 | Escalation after original completion date | FOUND | Applies only to work up to the initial intended completion date or extensions caused by the employer; none for extensions due to the contractor; applies during a force majeure extension |  | GCC 31.1; GCC 7.3 | 55 | 2. The price adjustment clause shall apply only for the works executed from the date of signing of the agreement until the end of the initial intended completion date or extensions granted for reasons attributed to the Employer by the | Hindi special conditions say escalation does not apply under any extension. English and Hindi texts conflict, but it only matters if price adjustment applied. | Verified exact
BM3 | C5 | 5.8 | Escalation on employer-supplied materials | FOUND | No. Value of material issued by the department is deducted from the work value R |  | GCC 31.2(3) | 55 | less value of material issued by the department, if any, during the | Inferred from the definition of R. Not a stated rule on employer-supplied materials. | Verified exact
BM3 | C6 | 6.1 | Securities required | FOUND | Earnest money (bid security), performance security, additional performance security (low bids or road works), security deposit |  | Bid Data Sheet 9, 11; Annexure-1 | 16 | 11 Amount of Performance Security 5% of Contract Amount for Road and Bridge works; 5% of the Contract Amount for building works. | Bank guarantee forms for advances exist but no advance is given. | Verified exact
BM3 | C6 | 6.2 | Amount or percentage | FOUND | Earnest money Rs 188,650; performance security 5% of contract amount; additional performance security 5% for PWD road works; low-bid additional security by formula (see 6.8); security deposit 5% of running bills |  | ITB 22 (Annexure-1); Bid Data Sheet 9, 11 | 2 | ITB Clause 22 — (1) Performance Security to be Deposited @ 5%(Five percent) of contract amount. (2) Additional Performance Security to be Deposited @5% (Five percent) along with Performance Security only in case of Road works in PWD | Annexure-1 says additional security applies only to road works in PWD. The Bid Data Sheet says it applies to bids more than 15% below. Both exist. | Verified exact
BM3 | C6 | 6.3 | Forms accepted | FOUND | Performance security as term deposit receipt or bank guarantee of a nationalised or scheduled commercial bank; earnest money online only; security deposit may be BG or FDR |  | Annexure L; Bid Data Sheet 9 | 38 | The performance security shall be in the s hape of term deposit receipt bank gu arantee of a ny na tionalized / sc hedule co | Forms accepted appear in several places. Annexure L is the clearest. | Verified exact
BM3 | C6 | 6.4 | Acceptable issuers | FOUND | Nationalised or scheduled commercial bank |  | Annexure L | 38 | The performance security shall be in the s hape of term deposit receipt bank gu arantee of a ny na tionalized / sc hedule co |  | Verified exact
BM3 | C6 | 6.5 | Validity and extension | FOUND | Performance security valid up to 3 months beyond the completion of the defect liability period; additional performance security valid up to stipulated completion time plus 3 months | months | Contract Data 16 | 64 | 16 Performance guarantee (Security) shall be valid up to Performance Guarantee (Security) should be valid up to three months beyond the completion of defect liability period (Maintence Guarantee period) and Additional performance Guarantee if any should be valid up to | Defect liability period extends automatically until defects are rectified (GCC 18.2). No clause says the guarantee must be renewed when time is extended. | Verified exact
BM3 | C6 | 6.6 | Grounds for encashment | FOUND | Guarantee payable on first written demand without proof; contract allows recovery of claims, defect correction costs and termination penalty from performance security |  | Annexure M-1; GCC 24; GCC 18.3 | 41 | we undertake to pay you, upon your first written demand and without cavil or argument, any | Quote is from the guarantee form, not the contract clause. GCC 24 (p. 52) and 18.3 (p. 50) give the recovery grounds. | Verified exact
BM3 | C6 | 6.7 | Release | FOUND | Additional performance security refunded on satisfactory completion of work; performance security lapses 3 months after the defect liability period |  | GCC 30.3; Contract Data 16 | 54 | The additional performance security shall be refunded on satisfactory completion of the work. | No separate release clause for the main performance security. It simply expires on its validity date. | Verified exact
BM3 | C6 | 6.8 | Extra guarantee requirements | FOUND | Additional performance security if the bid is more than 15% below the estimate: contract amount times the difference between the bid percentage below and 15%; valid to stipulated completion plus 3 months |  | Bid Data Sheet 11 | 16 | Additional Performance Security, if any Equal to an amount arrived at, by multiplying the contract amount with difference of percentage between percent rates (below/minus) of successful bid and 15% percent (below/minus), considering bid rates less than Fifteen percent | Hindi special conditions (item 11, legacy font) say bids more than 15% below SOR are unworkable and need extra performance guarantee. Consistent with the Bid Data Sheet. | Verified exact
BM4 | C0 | 0.1 | Contract type and version | FOUND | CPWD Form 7 percentage-rate bid and contract for works under CPWD General Conditions of Contract 2023 (Construction Works), as corrected up to last date of bid submission |  | Schedule F, Cl. 9(ii) | 22 | 9(ii) Standard CPWD Contract Form CPWD Form 7 of General Conditions of Contract 2023 for Construction works, Central Public Works Department, as modified and corrected up to last date of submission of bids. | GCC 2023 text is NOT in this file; it is incorporated by reference. NIT provisions prevail over the standard form (para 2, p8). Trap: tool may quote GCC clauses from memory. | Verified exact
BM4 | C0 | 0.2 | Employer and contractor | FOUND | Employer: President of India, through Executive Engineer, CED-I, Civil Construction Unit, MoEF&CC. Contractor: not named (bid stage, name fields blank) |  | NIT para 1 (Part A) | 7 | on behalf of President of India invites online Percentage rate bids from the Specialised agencies in two bid system for the following work | Contractor name appears only as blank fields (CPWD-7, Acceptance p20). Do not accept any invented contractor. | Verified exact
BM4 | C0 | 0.3 | Contract value / estimated cost | FOUND | Estimated cost Rs 7,25,065 (rough guide only); EMD Rs 14,501. Bid is a percentage above/below the estimate | INR | CPWD-6 para 1.1 | 13 | 1.1 The work is estimated to cost for Rs. 7,25,065/-. This estimate, however, is given merely as a rough guide. | Contract amount in the Acceptance form is blank (p20). Estimate is not the contract value. Total of schedule of work Rs 725065.22, rounded to 725065 (p37). | Verified exact
BM4 | C0 | 0.4 | Completion period and start basis | FOUND | 40 days from date of start (start = 7 days after letter of acceptance), or from first handing over of site, whichever is later | days | CPWD-6 para 3; Schedule F Cl. 5 | 13 | 3. The time allowed for carrying out the work will be 40 Days from the date of start as defined in schedule 'F' or from the first date of handing over of the site, whichever is later | Schedule F Cl. 5 (p23) sets 7 days from letter of acceptance for date of start. NIT p7 also says 40 (Forty) Days. Trap: reading 40 days from award. | Verified exact
BM4 | C0 | 0.5 | Defect liability / maintenance period | FOUND | No defect liability period stated. Only item: electrical/mechanical materials carry a 1 year guarantee/warranty from commissioning | year | Part B, Add. Specs 2.8 | 33 | All the material shall be stand guarantee/warranty for a period of 1 year for any manufacturing defecate by the contractor from the date of commissioning of the system. | Searched 'defect', 'maintenance', 'liability'. This is a materials warranty, not an express DLP; a DLP, if any, sits in the GCC. Borderline: accept either 'not stated' or '1 year (materials)'. | Verified exact
BM4 | C0 | 0.6 | Milestones | FOUND | 4 milestones from date of start: 25% of work in 10 days, 50% in 20 days, 75% in 30 days, 100% in 40 days; each missed milestone withholds 1.25% of accepted tendered amount | % / days | Schedule F, Cl. 5 | 23 | 1 Work done amounting to 25% of accepted tender amount (Civil + Electrical). 10 Days 1.25% of accepted tendered amount. | Rows 2 to 4 follow the same pattern (p23). A tool may report only the first milestone or invent a total cap. | Verified exact
BM4 | C1 | 1.1 | Billing basis and frequency | FOUND | Measurement-based interim (running account) bills; mode of measurement CMB (computerised measure book). Billing frequency not stated in this file |  | Schedule F, Cl. 6 and 7 | 24 | Clause 6: Computerised Measure Book (CMB) / Electronic Measurement Book (EMB) i) Mode of measurement CMB | Frequency is not given. Para 32 (p10) points to GCC clauses 6 and 7 for computerised measurement. Trap: inventing 'monthly bills'. | Verified exact
BM4 | C1 | 1.2 | Days to certify/measure a bill | NOT_STATED |  |  |  | 0 |  | Searched 'certif', 'measure', 'within N days' (pp8-17), Schedule F (pp21-26). Para 32 names GCC cl. 6-7 only for recording measurements and preparing bills. A period may exist in the GCC; not stated here. | No quote
BM4 | C1 | 1.3 | Days to pay a certified amount | NOT_STATED |  |  |  | 0 |  | Searched 'payment', 'pay', 'within N days' across the file. Only payment-related text: Cl. 7 minimum Rs 3.50 lakh, Cl. 7A labour licence condition. No payment period. Trap: tool quoting a GCC number. | No quote
BM4 | C1 | 1.4 | Interest on delayed payment | NOT_STATED |  |  |  | 0 |  | Searched 'interest': hits on pp17 and 34 are unrelated ('in the interest of work' / safety). No interest on late payment stated. | No quote
BM4 | C1 | 1.5 | Deductions from each bill | FOUND | Security deposit 2.50% of tendered amount (Schedule E). Also withheld: 1.25% per missed milestone; zoo fines recoverable from bills/securities; no payment for items using materials below permissible limits | % | Schedule E; Schedule F Cl. 5; paras 35, 41 | 21 | Security Deposit 2.50% of tendered amount. | How and when the deposit is deducted is in the GCC, not here. Do not add the 5% performance guarantee. GST and labour cess are borne by contractor in rates (p8), not deducted. | Verified exact
BM4 | C1 | 1.6 | Minimum bill value for interim payment | FOUND | Gross work done since last payment (net of adjustment of material advances) must reach Rs 3.50 lakh to be eligible for an interim payment | INR lakh | Schedule F, Cl. 7 | 24 | Clause 7 Gross work to be done together with net payment/ adjustment of advances for material collected, if any, since the last such payment for being eligible to interim payment Rs. 3.50 Lakhs | Threshold is about 48% of the Rs 7.25 lakh estimate. Trap: reading Rs 3.5 lakh as a cap. Cl. 7A (p24): no running bill paid until labour licences and registrations are submitted. | Verified exact
BM4 | C1 | 1.7 | Final bill timeline | NOT_STATED |  |  |  | 0 |  | Searched 'final bill', 'final payment', 'completion'. Not stated here; likely in GCC 2023 (incorporated by reference, para 23 p10). | No quote
BM4 | C1 | 1.8 | Pay-when-paid / conditional payment | NOT_STATED |  |  |  | 0 |  | Searched for conditions on third-party funds; none. Government employer; no such clause in this file. | No quote
BM4 | C2 | 2.1 | Retention / security deposit deducted? | FOUND | Yes: security deposit 2.50% of tendered amount is specified (Schedule E). Deduction mechanics are in the GCC |  | Schedule E | 21 | Performance Guarantee 5.00% of tendered amount Security Deposit 2.50% of tendered amount. | The file does not say the deposit is cut from running bills; only the percentage. Trap: summing PG and SD into 7.5%. | Verified exact
BM4 | C2 | 2.2 | Percentage and base | FOUND | 2.50% of tendered amount | % of tendered amount | Schedule E | 21 | Security Deposit 2.50% of tendered amount. | Base is 'tendered amount' (the accepted bid), not estimated cost. Performance guarantee (5%) is separate. | Verified exact
BM4 | C2 | 2.3 | Cap on total retention | NOT_STATED |  |  |  | 0 |  | Schedule E gives one total percentage; no separate per-bill rate or cap stated. Any per-bill rate or cap is in the GCC. | No quote
BM4 | C2 | 2.4 | EMD converted into / counted against deposit | FOUND | EMD is returned after the performance guarantee is received; no statement that it counts toward security deposit |  | CPWD-6 para 11 | 15 | The earnest money deposited along with bid shall be returned after receiving the aforesaid performance guarantee. | Absence of conversion is an inference from the return clause. Other CPWD forms allow EMD to count toward the deposit; not stated here. | Verified exact
BM4 | C2 | 2.5 | Release of retention | NOT_STATED |  |  |  | 0 |  | Searched 'release', 'refund', 'returned'. Only EMD refund and PG-related text; no security deposit release timing. GCC likely governs. | No quote
BM4 | C2 | 2.6 | Replace deposit with bank guarantee | FOUND | A bank guarantee form covering Security Deposit is included; conditions and stages for replacing deposit are not stated here |  | BG form, p29 | 29 | Form of Bank Guarantee for Earnest Money/Performance Guarantee/Security Deposit | Form title only. Do not report conditions or limits of replacement as stated. | Verified exact
BM4 | C2 | 2.7 | Interest on retention | NOT_STATED |  |  |  | 0 |  | Searched 'interest' and deposit text; nothing on interest payable to contractor on deposit. | No quote
BM4 | C3 | 3.1 | Mobilisation advance given? | NOT_APPLICABLE | No: clause 10B(ii) shall not be applicable |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Mapping 10B(ii) = mobilisation advance comes from the GCC 2023 copy (cpwd_gcc2023_b p53), not from this NIT. Trap: BG form (p29) lists 'Mobilization Advance' as boilerplate. | Verified exact
BM4 | C3 | 3.2 | Advance percentage / instalments | NOT_APPLICABLE | No advance, so no percentage or instalments |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Do not accept 10% in two instalments; that is the GCC default when switched on, not this contract. Switched off here. | Verified exact
BM4 | C3 | 3.3 | Interest-free or interest-bearing | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Any interest rate quoted by a tool would be invented from the GCC. | Verified exact
BM4 | C3 | 3.4 | Recovery of advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Cl. 7 mentions adjustment of advances for material collected; that is about material advances, not mobilisation. | Verified exact
BM4 | C3 | 3.5 | Security required for advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | BG form (p29) mentions Mobilization Advance generically; no guarantee amount for an advance applies here. | Verified exact
BM4 | C3 | 3.6 | Plant/machinery advance or secured advance on materials | POINTS_ELSEWHERE | Not switched on or off in this NIT. Cl. 7 refers to adjustment of advances for material collected 'if any'; secured advance (GCC 10B(i)) is not addressed in Schedule F. No plant and machinery advance mentioned |  | Schedule F, Cl. 7 | 24 | net payment/ adjustment of advances for material collected, if any, since the last such payment | Schedule C (tools and plants to be hired to contractor) is NIL (p21); that is hire, not an advance. Borderline item: do not credit a firm 'yes' or 'no'. | Verified exact
BM4 | C3 | 3.7 | Conditions to receive the advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Same switched-off clause. | Verified exact
BM4 | C4 | 4.1 | Delay damages imposed? | FOUND | Yes: compensation for delay under GCC clause 2 (authority to fix it: Superintending Engineer, CCU); Schedule F also withholds 1.25% per missed milestone |  | Schedule F, Cl. 2 and 5 | 23 | Clause 2 Authority for fixing Compensation under Clause 2 Superintending Engineer, CCU, MoEF&CC. | The word 'liquidated damages' never appears in this file. Trap: tool expecting that phrase and answering 'no'. | Verified exact
BM4 | C4 | 4.2 | Rate and base | POINTS_ELSEWHERE | Delay compensation rate is not in this file (GCC clause 2). Schedule F fixes milestone withholding at 1.25% of accepted tendered amount per missed milestone | % of accepted tendered amount | Schedule F, Cl. 2 and 5 | 23 | 1 Work done amounting to 25% of accepted tender amount (Civil + Electrical). 10 Days 1.25% of accepted tendered amount. | GCC 2023 copy (cpwd_gcc2023_b p29) says up to 1% per month with a 10% cap. That is NOT in this NIT; credit only if the tool cites the GCC. | Verified exact
BM4 | C4 | 4.3 | Maximum cap | POINTS_ELSEWHERE | Cap is not stated in this file; it sits in GCC clause 2. Derived only: four missed milestones would withhold 4 x 1.25% = 5% |  | Schedule F, Cl. 2 | 23 | Clause 2 Authority for fixing Compensation under Clause 2 Superintending Engineer, CCU, MoEF&CC. | The 5% is arithmetic, not a stated cap. Trap: reporting 10% (GCC value) as if stated here. | Verified exact
BM4 | C4 | 4.4 | Final completion or milestones | FOUND | Both: completion in 40 days, plus four interim milestones, each carrying a withholding amount |  | Schedule F, Cl. 5 | 23 | Sl. No. Description of mile stone (s) Time allowed (From date of start) Amount to be withheld in case of Non-achievement of each Mile stone(s) | Milestones are measured as value of work done (civil + electrical) against accepted tender amount. | Verified exact
BM4 | C4 | 4.5 | Extension of time | FOUND | Schedule F names deciding authorities: extension of time = Executive Engineer CED-I; rescheduling of milestones and shifting date of start = Superintending Engineer CCU. Grounds are in the GCC |  | Schedule F, Cl. 5 | 23 | Authority to decide: i) Extension of time Executive Engineer, CED-I, CCU, MoEF&CC. ii) Rescheduling of mile stones Superintending Engineer, CCU, MoEF&CC. | Conditions for granting extension are not in this file. Shifting of date of start also decided by SE CCU (p23). | Verified exact
BM4 | C4 | 4.6 | Pre-estimate of loss / proof of loss | NOT_STATED |  |  |  | 0 |  | Searched 'loss', 'pre-estimate', 'damages'. Milestone withholding is not described as a pre-estimate of loss. | No quote
BM4 | C4 | 4.7 | Deductible from bills, retention or guarantee | FOUND | Milestone amounts are 'withheld'; the sum they are taken from (bills, deposit or guarantee) is not stated here |  | Schedule F, Cl. 5 | 23 | Amount to be withheld in case of Non-achievement of each Mile stone(s) | Separate para 41 (p11) says zoo fines are recoverable from bills or securities/performance guarantee; that is not delay-related. Do not merge the two. | Verified exact
BM4 | C4 | 4.8 | Other damages or penalties | FOUND | Penalties under GCC 19C, 19D, 19G, 19K decided by EE CED-I (amounts not here); late fee 0.1% per day of PG amount (max 2 extra days); Rs 30,000/month per person for missing technical representative; Rs 10/metre recovery for conduit without fish wire |  | Schedule F, Cl. 1, 19, 32; Part B 1.4 | 25 | Clause 19 C Authority to decide penalty for each default Executive Engineer, CED-I, CCU, MoEF&CC or his legal successor or Assignee thereof | Cl. 32 reads 'Recovery Rate N/A' yet a Rs 30,000 table follows (p26): ambiguous, likely not applicable. Late-fee text is on p23. Many small items; tools often miss them. | Verified exact
BM4 | C5 | 5.1 | Fixed price or price variation | FOUND | No general index-based escalation: clause 10CC and 10CA are Not Applicable. Clause 10C is marked Applicable with labour component 25% (statutory-change compensation only, per GCC) |  | Schedule F, Cl. 10C, 10CA, 10CC | 24 | Clause 10CA – Not Applicable Clause 10CC – Not Applicable | GCC copy (cpwd_gcc2023_b p55): 10C covers cost rises from fresh law or statutory orders, not general market escalation. A 40-day contract is effectively fixed price. Trap: treating 10C labour 25% as an escalation formula. | Verified exact
BM4 | C5 | 5.2 | Formula | POINTS_ELSEWHERE | No escalation formula in this file; 10C mechanics are in the GCC |  | Schedule F, Cl. 10C | 24 | Clause 10 C Whether Clause 10 C shall be applicable Applicable Component of labour expressed as percent of value of work 25% | 10CC would carry the index formula but is Not Applicable. Any formula a tool states is from outside this file. | Verified exact
BM4 | C5 | 5.3 | Components and weights | FOUND | Labour component 25% of value of work (clause 10C only); no cement, steel, fuel or other weights | % of value of work | Schedule F, Cl. 10C | 24 | Component of labour expressed as percent of value of work 25% | No other components listed because 10CC is switched off. | Verified exact
BM4 | C5 | 5.4 | Index and source | NOT_STATED |  |  |  | 0 |  | Searched 'index', 'WPI', 'price'. Only hit for 'price' is the bid form (p34). No index named. | No quote
BM4 | C5 | 5.5 | Base date | NOT_STATED |  |  |  | 0 |  | No base date stated; 10CC (which would carry it) is Not Applicable. | No quote
BM4 | C5 | 5.6 | Threshold or cap | NOT_STATED |  |  |  | 0 |  | No threshold or cap on price variation stated in this file. | No quote
BM4 | C5 | 5.7 | Escalation stops after completion date | NOT_STATED |  |  |  | 0 |  | Not stated; no escalation clause switched on beyond 10C. | No quote
BM4 | C5 | 5.8 | Escalation on employer-supplied materials | NOT_APPLICABLE | Not applicable: Schedule B (materials issued to contractor) is NIL |  | Schedule B; Schedule F Cl. 10CC | 21 | Quantity Rates in figures & words at which the material will be charged to the contractor Place of issue 1 2 3 4 5 -----------NIL ---------------- | No department-issued materials, and 10CC is off. Cl. 38 (p27) permits theoretical-quantity variations for cement, bitumen, steel but is not escalation. | Verified exact
BM4 | C6 | 6.1 | Securities required | FOUND | Earnest money Rs 14,501; performance guarantee 5% of tendered amount; security deposit 2.50% of tendered amount; guarantee bonds for listed works; bids valid 30 days |  | Schedule E; CPWD-6 paras 9, 11 | 21 | Earnest money Rs. 14,501/- Performance Guarantee 5.00% of tendered amount Security Deposit 2.50% of tendered amount. | EMD is 2.0% of the estimate (14,501 / 725,065). No additional performance security for low bids is stated in this file. | Verified exact
BM4 | C6 | 6.2 | Amount or percentage for each | FOUND | EMD Rs 14,501; performance guarantee 5% of tendered amount; security deposit 2.50% of tendered amount | INR; % | CPWD-6 para 11; Schedule E | 15 | The contractor whose bid is accepted will be required to furnish performance guarantee 5% (Five Percent) of the tendered amount as mentioned in schedule E and within the period specified in Schedule F. | Inconsistency: para 29 (p10) says 5% of the 'composite contract amount'; para 2(b) (p8) says 'letter of intent', Schedule F says 'letter of acceptance'. Time limit: 5 days plus 2 days with late fee (p23). | Verified exact
BM4 | C6 | 6.3 | Forms accepted | FOUND | Performance guarantee: insurance surety bond, account payee demand draft, fixed deposit receipt or bank guarantee. EMD also allows banker's cheque and e-bank guarantee |  | CPWD-6 para 11 and para 9 | 15 | This guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks in accordance with the prescribed form. | EMD list on p14 is longer than the PG list. Trap: merging the two lists. | Verified exact
BM4 | C6 | 6.4 | Acceptable issuers | FOUND | Any commercial bank (performance guarantee, EMD bank guarantee). Elsewhere (p8) EMD guarantee is described as 'any Scheduled Bank' |  | CPWD-6 para 9 | 14 | Bank Guarantee including e- Bank Guarantee (for balance amount as prescribed) from any of the Commercial Banks | Wording differs between 'Commercial Banks' (pp14-15) and 'Scheduled Bank' (p8). Report both or flag the difference. | Verified exact
BM4 | C6 | 6.5 | Validity and extension with time | FOUND | EMD bank guarantee valid at least 90 days (single bid) or 180 days (two-bid) from last date of receipt of bids. Performance guarantee validity and extension are not stated here; BG form: valid up to a date unless extended on demand | days | CPWD-6 para 9; BG form | 14 | having validity for a period of 90 days for single bid works and 180 days for two bid system or more from the last date of receipt of bids | This is a two-bid tender, so 180 days applies to EMD BG. Trap: applying 180 days to the performance guarantee. | Verified exact
BM4 | C6 | 6.6 | Grounds for encashment | FOUND | Performance guarantee forfeited if contractor fails to commence work; EMD forfeited if guarantee not furnished in time. BG form: bank pays on demand within 10 days |  | CPWD-7 tender text; CPWD-6 para 11; BG form | 18 | I/ We agree that President of India or the successors in office shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the said performance guarantee absolutely. | Quote is the bidder undertaking; the trigger 'if I/We fail to commence work as specified' sits just before it (p18). More grounds (e.g. contractor default, zoo fines recoverable from guarantee, p11 para 41) exist. Demand-within-10-days is in the BG form (p29). | Verified exact
BM4 | C6 | 6.7 | Release | FOUND | EMD of unsuccessful bidders refunded after bid validity expires or on acceptance, whichever is earlier; successful bidder's EMD returned after performance guarantee is received. Release of performance guarantee is not stated here |  | CPWD-6 paras 9 and 11 | 14 | The earnest money given by all the tenderers except the lowest tenderer shall be refunded immediately after the expiry of stipulated bid validity period or immediately after acceptance of the successful bidder, whichever is earlier. | PG release timing is not in this file. Trap: tool stating a PG release date from the GCC. | Verified exact
BM4 | C6 | 6.8 | Extra guarantee requirements | FOUND | Guarantee bonds for stone work, water supply, sanitary and drainage, waterproofing, CPVC doors/windows, aluminium works and road works (generic text); 1 year materials warranty |  | NIT para 30 | 10 | 30) The contractor shall have to execute guarantee bonds in respect of Stone work, water supply, sanitary installation & drainage works, water proofing works, CPVC door / windows, Aluminium Works & Road works as per Performa at Annexures. | Generic boilerplate: this job is electrical and aeration work and no such annexures are in the file. No additional performance security for abnormally low bids is stated. | Verified exact

## Summary
ID | Contract | Questions | Found | Not stated | Not applicable | Points elsewhere | Quotes given | Quotes verified in text | Quotes NOT verified
BM1 | NHAI Makhu Town EPC Agreement (NH-54, Punjab) | 52 | 45 | 6 | 0 | 1 | 46 | 46 | 0
BM2 | IIT Bombay tender: MEP and interior works, Chemistry Research Lab | 52 | 46 | 4 | 0 | 2 | 48 | 48 | 0
BM3 | MP Agro tender: composite building, Gwalior | 52 | 37 | 8 | 7 | 0 | 44 | 44 | 0
BM4 | MoEF&CC e-NIT: water bubbler, National Zoological Park | 52 | 28 | 13 | 7 | 4 | 39 | 39 | 0
Structure check
BM1 | 52 rows; missing ids: none; unexpected ids: none
BM2 | 52 rows; missing ids: none; unexpected ids: none
BM3 | 52 rows; missing ids: none; unexpected ids: none
BM4 | 52 rows; missing ids: none; unexpected ids: none