## Read Me
Contract Answer Key v2 (verified in four ways)
CE725 Team 2, Topic 12. Built 22 October 2026. Replaces the first draft, which had known errors.
What this workbook holds
Raw File Info: fingerprints and sources for the four raw PDFs. Best 4: why these four. Answer Key: 208 answers, each with a status, the clause, the PDF page, a quote and four check columns. Review Log: every difference found and how it was settled. Eye-check Log: what the page images showed. Summary: counts.
The four checks
Check 1: a script searched each quote in the text extracted by pypdf and compared the page.
Check 2: a second script did the same with a different PDF engine (PyMuPDF).
Check 3: four fresh readers answered all 52 questions per contract without seeing the key. Differences were reviewed one by one (Review Log).
Check 4: the schedule pages and every page with no readable text were looked at as images. This found errors that checks 1 to 3 all missed, because text extraction cannot see strike-throughs, images or scans.
Status values
FOUND: stated in the document. NOT_STATED: nothing said. NOT_APPLICABLE: the clause exists but is switched off for this contract. POINTS_ELSEWHERE: the document defers to another document or a blank schedule.
What 'verified' does and does not mean
A quote found on the stated page proves the text exists there. It does not prove the answer reads it correctly. Two readers agreeing is not proof either: both text readers got the BM2 strike-through fields wrong. A person still has to confirm each answer against the page image.
PDF page numbers are positions in the file, not printed page numbers. Scanned Hindi pages were read by the key author from images and need a Hindi reader. Rows marked 'Corrected after viewing the page image' have no text-layer proof by design.

## Raw File Info
ID | File | Source address | Downloaded | Pages | Size (bytes) | SHA-256 fingerprint | Identical to a fresh download from the source? | PDF pages with no readable text | Notes
BM1 | BM1_NHAI_Makhu_Town_EPC_Agreement.pdf | https://nhai.gov.in/nhai/sites/default/files/2020/EPC_Agreement_Schedules-Makhu_Town.pdf | 22 Oct 2026 | 250 | 3389664 | 90d6c58c9f2d2ca9ab8d28892134a3fc77525f78874d52524f60a41c52ba7d5e | Yes: a fresh download matched byte for byte | none | 5 pages carry images, including the price-adjustment formulas (PDF pages 109 to 111).
BM2 | BM2_IIT_Bombay_Chemistry_Lab_Tender.pdf | https://www.iitb.ac.in/deanpl/tenders/chemlabr/gc.pdf | 22 Oct 2026 | 114 | 3829519 | 38ad2465c261d41764469ccfeee3c7be10d6577a96a85882b6226b24cad89d1a | Yes: a fresh download matched byte for byte | 1 | Page 1 is a cover. Schedules E and F on PDF pages 105 to 111 use strike-throughs that text extraction cannot see.
BM3 | BM3_MP_Agro_Gwalior_Tender.pdf | https://mpagro.org/assets/tenderfiles/2a2d879c-6e8f-451f-976a-d7d1de78ae90.pdf | 22 Oct 2026 | 93 | 2591249 | cbe070fa7bfeeab2677993c77015cea5e9cdd8279fe06ccf9d560421f9ffc76b | Yes: a fresh download matched byte for byte | 87, 88, 89, 90, 91, 92, 93 | PDF pages 87 to 93 are scanned Hindi circulars with no text layer.
BM4 | BM4_MoEF_Zoological_Park_NIT.pdf | https://moef.gov.in/storage/tender/1739175875.pdf | 22 Oct 2026 | 38 | 1898854 | b65ac5b896e79a24c1d88d993b20cf90a758e13f9455461ea5c9ba625e5a012b | Yes: a fresh download matched byte for byte | 1, 2, 3 | PDF pages 1 to 3 are an image printout of the e-tender portal. The full CPWD GCC 2023 is NOT included.
REF | Reference_CPWD_GCC_2023.pdf | https://iitk.ac.in/iwd/file/2026/18-Civil-D2-2026-27/GCC-2023.pdf | 22 Oct 2026 | 208 | 2272920 | 69c6d25c50aaf4775c3c3f37be6c501b0098dd5a6baa4beeca32beda2a4b25ef | Yes: a fresh download matched byte for byte | 2, 3, 207, 208 | Not one of the four. It is the General Conditions that BM4 refers to.

## Best 4
Rank | ID | Contract | Type | Pages | Why it is in the top four | What it tests | Weakness
1 | BM1 | NHAI Makhu Town EPC Agreement (NH-54, Punjab) | Real project agreement | 250 | Best overall. All six clause types with specific numbers, in a long realistic document with clean text. | Rate against cap that disagree (6% deducted, 5% cap). Layered securities. Interest-bearing advance with 110% guarantee. Index-formula price adjustment (formulas are images). Delay damages per day with a cap. | Highway-specific. Same template as other NHAI agreements. Stage payments, not monthly bills.
2 | BM2 | IIT Bombay tender: MEP and interior works, Chemistry Research Lab | Real tender | 114 | Your own institute's real tender. Filled schedules, advance with interest, escalation clauses and delay compensation. | Schedule values that complete the general clauses. Struck-through Yes/No and Applicable/Not Applicable fields that text readers cannot see. Payment terms and minimum bill value stated twice with different numbers. | Much boilerplate. Several schedule fields are blank.
3 | BM3 | MP Agro tender: composite building, Gwalior | Real tender | 93 | Best for honest failure tests. Short, real, and built around a data sheet that overrides the general text. | Delay damages rate two references deep (GCC 15.4, Contract Data, Annexure P). Advances switched off. Price adjustment switched off by contract size, with two disagreeing weight tables. No interest on late payment. Scanned Hindi circulars. | Small project. Extraction splits some words and digits. Pages 87 to 93 are images.
4 | BM4 | MoEF&CC e-NIT: water bubbler, National Zoological Park | Real tender | 38 | The common central-government CPWD format in a short real tender with filled schedules. Defers to CPWD GCC 2023. | Cross-document references: the right answer is often 'defined in GCC 2023'. Four milestones with money withheld. Clause 10CC and 10CA not applicable. Image pages at the front. | Few financial values. Small contract. The GCC text is not included.

## Answer Key
Contract | Clause | Q | Question | Status | Answer | Unit | Section | PDF page | Verbatim quote | Notes (traps for the AI) | Check 1: quote on stated page (pypdf) | Check 2: quote on stated page (PyMuPDF) | Check 3: blind re-read | Check 4: page image
BM1 | C0 | 0.1 | Contract type, form and version | FOUND | NHAI draft EPC agreement for four-laning of Makhu Town, NH-54 Punjab; cover dated July 2024 |  | Cover page | 1 | Draft Engineering Procurement and Construction (EPC) Agreement For Widening and Reconstruction of existing Two Lane Carriageway to Four Lane with Paved Shoulder in Makhu Town | Draft, not an executed contract. Cover also names NHAI and July 2024 on the same page. Template shared with other NHAI EPC agreements. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM1 | C0 | 0.2 | Employer and contractor | FOUND | Employer: President of India through MoRTH, represented by Chairman NHAI (Chandigarh regional office); Contractor: not named (placeholder) |  | Parties clause | 14 | The President of India through the Ministry of Road Transport & Highways, Government of India represented by: The Chairman, National Highways Authority of India, Regional office, Chandigarh | Contractor is a blank placeholder (<insert name of party>). An LLM may invent a contractor name. | Found on stated page | Found on stated page | Agrees
BM1 | C0 | 0.3 | Contract value / price | POINTS_ELSEWHERE | Lump sum Contract Price left blank (INR ... ) to be filled with the accepted bid price | INR | Cl. 19.1(i) | 102 | the lump sum price accepted by the Authority in consideration of the obligations specified in this Agreement for an amount of INR … … … … (INR … … … … … … … …) (the “Contract Price”) | Amount is blank in this draft. Price excludes maintenance cost and GST (same clause). Do not accept any figure from the tool. | Found on stated page | Found on stated page | Agrees
BM1 | C0 | 0.4 | Completion period and start trigger | FOUND | 730 days from the Appointed Date | days | Cl. 10.3(i) | 64 | The 730th (seven hundred and thirtieth) day from the Appointed Date shall be the scheduled completion date | Appointed Date is declared by the Authority with contractor consent (Art. 3 and 8). Schedule J milestone days must agree with 730. | Found on stated page | Found on stated page | Agrees
BM1 | C0 | 0.5 | Defects liability / maintenance period | FOUND | 5 years (flexible pavement); 10 years (rigid pavement, perpetual-design flexible, stand-alone structures), from completion | years | Cl. 17.1(i) | 95 | (a) 5 (five) years from the date of completion in case of a road being constructed with flexible pavement; (b) 10 (ten) years from the date of completion in case of road being constructed with rigid pavement; | Which limb applies depends on the pavement type chosen in the specifications; not decided in this clause. Separate Maintenance Period exists under Art. 14. | Found on stated page | Found on stated page | Agrees
BM1 | C0 | 0.6 | Milestones | FOUND | Milestone I day 145 (statements >=10% of price); II day 320 (>=35%, all bridges started); III day 520 (>=70%); Scheduled Completion day 730 | days / % of Contract Price | Sch. J paras 2-5 | 219 | Project Milestone-I shall occur on the date falling on the 145th (one hundred and forty fifth first) day from the Appointed Date | Trap: Cl. 10.3(ii) example mentions Milestone-I on the 180th day with 10%, but Schedule J says 145th day. Quote is the Schedule J wording. | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.1 | Billing basis and frequency | FOUND | Stage payments for completed stages valued per Schedule-H; contractor submits one Stage Payment Statement a month by the 7th | monthly | Cl. 19.3 and 19.4 | 105 | The Contractor shall submit a statement (the “Stage Payment Statement”), in 3 (three) copies, by the 7th (seventh) day of the month | Not item-rate measurement: no payment for incomplete stages (same clause). LLM may describe it as monthly measured running bills. | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.2 | Days to certify a bill | FOUND | Authority's Engineer issues the Interim Payment Certificate within 15 days of receiving the statement; within 10 days he recommends a 90% part payment | days | Cl. 19.5(i) and (ii) | 105 | Within 15 (fifteen) days of the receipt of the Stage Payment Statement referred to in Clause 19.4, the Authority’s Engineer shall determine and shall deliver | Two different periods (10 and 15 days) sit in the same clause. Certification is not the same as payment. | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.3 | Days to pay after certification | FOUND | Payment no later than 30 days from submission of the Stage Payment Statement; if no IPC in 30 days the Authority pays the amount claimed and adjusts later | days | Cl. 19.9(i)(a) | 107 | payment shall be made no later than 30 (thirty) days from the date of submission of the Stage Payment Statement by the Contractor | The 30 days run from submission of the statement, not from certification. Part payment of 90% is separately due within 10 days of the Engineer's recommendation (19.5(i)). | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.4 | Interest on delayed payment | FOUND | Bank Rate + 3% per annum on all unpaid sums | % p.a. | Cl. 19.9(ii) | 108 | the Authority shall be liable to pay to the Contractor interest @ Bank Rate + 3% per annum, on all sums remaining unpaid | Bank Rate is the RBI rate (footnote in 19.2(i)); the current value is not in the contract. Base Rate (SBI) is a different defined term. | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.5 | Deductions from each bill | FOUND | Retention 6% of every payment (cap 5% of Contract Price); advance recovery 15% of each Stage Payment Statement; withholding for unperformed or defective work (19.5(iv)) | % | Cl. 7.5(i); 19.2(vi); 19.5(iv) | 50 | deduct 6% (six per cent) thereof as guarantee money for performance of the obligations of the Contractor during the Construction Period | Deductions are spread across three clauses. Taxes at source are mentioned only in the termination valuation (23.5), not as a bill deduction. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM1 | C1 | 1.6 | Minimum bill or cap before certification | FOUND | No minimum bill value stated; before the IPC only 90% of the amount broadly determined is released as part payment | % of determined amount | Cl. 19.5(i) | 105 | recommend the release of 90 (ninety) percent of the amount so determined as part payment against the Stage Payment Statement, pending issue of the Interim Payment Certificate | No minimum bill amount found. The 90% interim release is the only cap before certification. Contractor cannot claim incomplete stages (19.4). | Found on stated page | Found on stated page | Agrees
BM1 | C1 | 1.7 | Final bill and final payment | FOUND | Final Payment Statement within 60 days of Completion Certificate; Final Payment Certificate within 30 days of statement and discharge; payment per 19.9 | days | Cl. 19.13(i); 19.15; 19.9 | 111 | Within 60 (sixty) days after receiving the Completion Certificate under Clause 12.2, the Contractor shall submit | Two further periods (30 days) come from other clauses. Maintenance has its own final statement (19.16). | Found on stated page | Found on stated page | Agrees | Page image viewed
BM1 | C1 | 1.8 | Pay-when-paid or conditional payment | NOT_STATED | None found |  |  | 0 |  | Searched Art. 19 and whole text for pay-when-paid, back-to-back, subject to receipt of funds, availability of funds: no hits. Payment is unconditional but subject to certification. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM1 | C2 | 2.1 | Retention deducted? | FOUND | Yes |  | Cl. 7.5(i) | 50 | From every payment for Works due to the Contractor in accordance with the provisions of Clause 19.5, the Authority shall deduct 6% (six per cent) thereof | Retention is in Art. 7 (Performance Security), not in Art. 19 where payments sit. | Found on stated page | Found on stated page | Agrees
BM1 | C2 | 2.2 | Rate and base | FOUND | 6% of every payment for Works (stage payments under Cl. 19.5) | % of each payment | Cl. 7.5(i) | 50 | deduct 6% (six per cent) thereof as guarantee money for performance of the obligations of the Contractor during the Construction Period | Trap: rate is 6% but total is capped at 5% of Contract Price (next row). LLMs often report only 5%. | Found on stated page | Found on stated page | Agrees
BM1 | C2 | 2.3 | Cap on total retention | FOUND | 5% of Contract Price | % of Contract Price | Cl. 7.5(i) | 50 | subject to the condition that the maximum amount of Retention Money shall not exceed 5% (five per cent) of the Contract Price. | Cap is lower than the deduction rate, so deductions stop once 5% of the Contract Price is held. | Found on stated page | Found on stated page | Agrees
BM1 | C2 | 2.4 | Bid security / earnest money counted against retention | FOUND | No link to retention: Bid Security stays in force until substituted by the Performance Security; it is not converted into retention money |  | 1.1 definition of Bid Security; 7.1(iv) | 17 | “Bid Security” means the bid security provided by the Contractor to the Authority in accordance with the Request for Proposal, and which is to remain in force until substituted by the Performance Security; | Judgement call: the text defines Bid Security but never says it is converted into retention. Both readers agree there is no link. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind FOUND). Blind reader supplied a supporting definition on page 17. Key changed from NOT_STATED to FOUND.
BM1 | C2 | 2.5 | When retention is released | FOUND | Balance refunded within 15 days of the Completion Certificate (after set-off of appropriations) | days | Cl. 7.5(iii) | 50 | Within 15 (fifteen) days of the date of issue of the Completion Certificate, the Authority shall refund the balance of Retention Money remaining with the Authority | Released at completion, not at end of the 5 or 10 year defects period. On termination it is treated like Performance Security (7.5(iv)). | Found on stated page | Found on stated page | Agrees
BM1 | C2 | 2.6 | Retention replaceable by bank guarantee | NOT_STATED | No substitution mechanism in this agreement |  |  | 0 |  | Searched Cl. 7.5 and the whole text for retention with bank guarantee or substitution forms: none. A retention-withdrawal guarantee form exists in some other NHAI drafts, not here. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM1 | C2 | 2.7 | Interest on retention | NOT_STATED | None stated |  |  | 0 |  | Cl. 7.5 has no interest. The 9% interest in 7.4(iii) applies only to late return of Performance Security and Additional Performance Security. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM1 | C3 | 3.1 | Mobilisation advance given? | FOUND | Yes, interest-bearing |  | Cl. 19.2(i) | 102 | The Authority shall make an interest-bearing advance payment (the “Advance Payment”) @ “Bank Rate3 + 3%”, equal to 10 % (ten percent) of the Contract Price, | Advance is paid by the Authority to the Contractor, the reverse of retention. It is interest-bearing, not free. | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.2 | Amount and instalments | FOUND | 10% of Contract Price in two instalments of 5% each | % of Contract Price | Cl. 19.2(i) | 103 | The Advance Payment for mobilisation expenses shall be made in two instalments each equal to 5% (ﬁve percent) of the Contract Price. | Second instalment needs a utilisation certificate for the first. Separate equipment advance is additional (3.6). | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.3 | Interest-free or interest-bearing | FOUND | Interest-bearing at Bank Rate + 3% per annum | % p.a. | Cl. 19.2(i); 19.2(vii) | 102 | The Authority shall make an interest-bearing advance payment (the “Advance Payment”) @ “Bank Rate3 + 3%”, equal to 10 % (ten percent) of the Contract Price, | On termination for Contractor Default the unrecovered balance carries Bank Rate + 5% (19.2(vii)). Two different spreads in one clause. | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.4 | Recovery method | FOUND | 15% deducted from each Stage Payment Statement from the first one; fully repaid before 80% of the scheduled construction period | % of each payment | Cl. 19.2(vi) | 104 | deductions shall be made at the rate of 15% (fifteen percent) of each Stage Payment Statement until such time as the advance payment has been repaid; | Also: if certified payments stay at or below 20% of price within half the period, the advance is recovered by encashing the guarantee (19.2(vi)(c)). | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.5 | Security for the advance | FOUND | Irrevocable unconditional e-Bank Guarantee for 110% of each instalment, valid until full repayment | % of instalment | Cl. 19.2(iii) and (iv) | 103 | for an amount equivalent to 110% (one hundred and ten per cent) of such instalment | Guarantee can be split into parts of at least 2.75% of Contract Price each. Physical BG also accepted till 31.12.2024 per footnote. | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.6 | Plant and machinery or secured advance | FOUND | Additional advance on newly purchased key equipment up to 5% of Contract Price against e-BG; no advance on materials found | % of Contract Price | Cl. 19.2(ii) | 103 | The maximum of such advance shall be 5% (five per cent) of the Contract Price | Equipment advance needs Engineer verification the equipment is on site. Searched for secured advance on materials: no hits. | Found on stated page | Found on stated page | Agrees
BM1 | C3 | 3.7 | Conditions to receive the advance | FOUND | Apply after Appointed Date with 110% e-BG; second instalment after 60 days from Appointed Date, with e-BG and utilisation certificate; paid within 15 days of request | days | Cl. 19.2(iii)-(v) | 103 | The Contractor may apply to the Authority for the first instalment of the Advance Payment at any time after the Appointed Date | First instalment: any time after Appointed Date. Second: after 60 days plus utilisation certificate for the first 5%. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.1 | Delay damages imposed? | FOUND | Yes (called "Damages") |  | Cl. 10.3(ii) | 64 | it shall pay Damages to the Authority of a sum calculated at the rate of 0.05% (zero point zero five percent) of the Contract Price for delay of each day | Contract uses the word Damages and says it is not a penalty or liquidated damages (1.2(w)). LLM searching only for "liquidated damages" will miss it. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.2 | Rate and base | FOUND | 0.05% of Contract Price for each day of delay, reckoned from the date in Schedule J. Payable if the milestone or the Scheduled Completion Date is not achieved within 30 days of that date | % of Contract Price per day | Cl. 10.3(ii) | 64 | In the event that the Contractor fails to achieve any Project Milestone or the Scheduled Completion Date within a period of 30 (thirty) days from the date set forth in Schedule-J | Trap: a 30-day grace applies before damages start, but the daily count runs from the Schedule J date, not from day 31. Wording corrected after review: the 30 days is the window in which the milestone must be achieved; the daily count runs from the Schedule J date. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.3 | Cap on damages | FOUND | 10% of Contract Price; above that the Contractor is in default and the Authority may terminate | % of Contract Price | Cl. 10.3(iii) | 65 | the total amount of Damages under Clause 10.3 (ii) shall not exceed 10% (ten percent) of the Contract Price | Cap is stated in 10.3(iii), a later paragraph than the rate. Cap reached after 200 days at 0.05% a day. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.4 | Completion only or milestones too | FOUND | Both each Project Milestone and the Scheduled Completion Date |  | Cl. 10.3(ii) | 64 | In the event that the Contractor fails to achieve any Project Milestone or the Scheduled Completion Date | Damages paid for a missed milestone are refunded without interest if the project finishes by the Scheduled Completion Date including extensions. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.5 | How the date can be extended | FOUND | Time Extension for delayed Right of Way or clearances, Change of Scope, Force Majeure, Authority-caused delay; notice within 15 business days or the right is lost | business days | Cl. 10.5(i)-(iii) | 66 | the Contractor shall be entitled to extension of time in the Project Completion Schedule (the “Time Extension”) to the extent that completion of any Project Milestone is or will be delayed by any of the following, namely: | Extension applies only to the affected works, not the whole project (10.5(ii)). | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.6 | Pre-estimate of loss; proof of loss | FOUND | Damages are stated to be a genuine pre-estimate of loss and not a penalty; proof of loss not mentioned |  | Cl. 1.2(w) | 26 | mutually agreed genuine pre-estimated loss and damage likely to be suffered and incurred by the Party entitled to receive the same and are not by way of penalty or liquidated damages | No wording on whether actual loss must be proved. Relevant to Section 74 of the Contract Act. | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.7 | Recovery from bills, retention or guarantee | FOUND | Appropriate from Performance Security and Retention Money on Contractor Default; recoverable from amounts due after 20 days notice |  | Cl. 7.3(i); 7.5(ii); 19.19 | 49 | Upon occurrence of a Contractor’s Default, the Authority shall, without prejudice to its other rights and remedies hereunder or in law, be entitled to encash and appropriate the relevant amounts from the Performance Security as Damages | Damages cannot be deducted without notice and 20 days for a representation (10.3(iii)). | Found on stated page | Found on stated page | Agrees
BM1 | C4 | 4.8 | Other damages or penalties | FOUND | 0.01% of Bid Price per day for late security; maintenance non-compliance payment cuts (Sch. M); Authority pays damages for late site handover (8.3); bid ban if >90 days late on projects of Rs 300 crore or more; early completion bonus 0.03% a day, max 5%; also: lane-closure delay damages 0.1% of the monthly maintenance payment for each day per 250 m stretch (page 89); 20% of the cost as Damages for failure to rectify defects (page 96, Art. 17); 120% of the actual removal cost if the contractor fails to remove equipment and debris (page 82) | various | Cl. 7.1(iii); 8.3; 10.3(iv); 19.20; Sch. M | 49 | The Damages shall be the sum calculated at the rate of 0.01% (zero point zero one per cent) of the Bid Price offered by the Selected Bidder | Several different "Damages" run both ways. Do not merge the 0.01% (security delay) with the 0.05% (construction delay). Extra items added after the blind re-read and re-checked in the text. | Found on stated page | Found on stated page | Differs (Numbers differ). Blind reader listed more damages items. Three were re-checked in the text and added. One (aggregate cap on right-of-way delay) could not be re-found and was left out.
BM1 | C5 | 5.1 | Fixed price or price variation | FOUND | Price variation clause applies (index-based adjustment) |  | Cl. 19.10(iv) | 108 | The Contract Price shall be adjusted for increase or decrease in rates and price of labour, cement, steel, Plant, machinery and spares, bitumen, fuel and lubricants, and other material inputs | Contract Price is lump sum but adjusted by formula (19.1(i)). Not fixed price. | Found on stated page | Found on stated page | Agrees
BM1 | C5 | 5.2 | Formula | FOUND | Road and other works: VRW = 0.85 x RW x [PL(LI-L0)/L0 + PA(AI-A0)/A0 + PF(FI-F0)/F0 + PB(BI-B0)/B0 + PM(MI-M0)/M0 + PC(CI-C0)/C0 + PS(SI-S0)/S0]. Bridges and structures: VBR = 0.85 x BR x [same terms without the bitumen term PB]. Maintenance lump sum, adjusted quarterly: V = P x (WI - W0)/W0, using the all-commodities WPI |  | Cl. 19.10(iv)(d) | 108 | Price adjustment for changes in cost shall be paid in accordance with the following formulae: | The equations are images, so the extracted text has only the variable definitions (VRW, VBR, AO/AI, CO/CI and others). A tool must not invent the algebra. Corrected after viewing the page image: the equations are on PDF pages 109 and 111 (printed pages 97 and 99); the quote above is the text that introduces them. The P-terms are the component percentages in the table on page 111. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM1 | C5 | 5.3 | Components and weights | FOUND | Labour 20/20/20/15/15%; cement 5/nil/20/15/15%; steel nil/nil/nil/15/20%; bitumen nil/15/nil/nil/nil%; fuel 10% each; other materials 50/40/35/30/25%; plant 15% each (five work types) | % by work type | Cl. 19.10(iv)(e) | 110 | Labour (PL) 20% 20% 20% 15% 15% Cement (PC) 5% Nil 20% 15% 15% Steel (PS) Nil Nil Nil 15% 20% Bitumen (PB) Nil 15% Nil Nil Nil | Five columns by work type; table text is split across lines and continues on the next page (plant row). | Found on stated page | Found on stated page | Agrees
BM1 | C5 | 5.4 | Index and source | FOUND | WPI machinery; WPI cement (OPC); WPI mild steel long products; WPI all commodities; CPI-IW Bathinda (Labour Bureau); bitumen price at Bathinda (HMEL) refinery; HSD price at IOC pumps in Punjab |  | Cl. 19.10(iv)(d) definitions | 110 | SO = The WPI for Mild Steel –Long Products for the month of the Base Date. SI = The WPI for Mild Steel –Long Products for the month three months prior to the month to which the IPC relates. | Current index is for the month three months before the IPC month. Bitumen and diesel use price points, not WPI. | Found on stated page | Found on stated page | Agrees
BM1 | C5 | 5.5 | Base date | FOUND | Last day of the calendar month at least 28 days before the Bid Due Date |  | Cl. 1.1 (Base Date) | 17 | means the last date of the calendar month, which precedes the Bid Due Date by at least 28 (twenty eight) days | Index comparison point is the Base Date (not the contract signing date). | Found on stated page | Found on stated page | Agrees
BM1 | C5 | 5.6 | Threshold or cap on escalation | NOT_STATED | No threshold or ceiling stated |  |  | 0 |  | Searched Cl. 19.10 and 19.11: no deductible threshold, ceiling or percentage cap. 19.10(iii) says costs not otherwise covered are deemed included in the price. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM1 | C5 | 5.7 | Escalation after original completion date | FOUND | Payable only for stages billed within 30 days of the applicable milestone or Scheduled Completion Date (including extensions) | days | Cl. 19.11 | 111 | Price adjustment shall be due and payable only in respect of the stages of Works for which the Stage Payment Statement has been submitted by the Contractor no later than 30 (thirty) days | Late billing cuts off price adjustment after that milestone or completion date; it is not a blanket stop at original completion. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM1 | C5 | 5.8 | Escalation on employer-supplied materials | NOT_STATED | No such provision found |  |  | 0 |  | Searched for supplied by or issued by the Authority and free issue of materials: no material-supply clause tied to escalation. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM1 | C6 | 6.1 | Securities required | FOUND | Bid Security (RFP stage); Performance Security; Additional Performance Security for low bids; Retention Money; e-BG for each advance (mobilisation and equipment) |  | Cl. 7.1; 7.5; 19.2 | 48 | Within 30 (thirty) days of receipt of Letter of Acceptance, the selected Bidder shall furnish to the Authority in the form of Insurance Surety Bond | Retention and advance guarantees are not in the same clause as Performance Security. LLMs often list only the first. | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.2 | Amount and base | FOUND | Performance Security 3% of Bid Price; Additional Performance Security up to 3% of Bid Price; advance e-BG 110% of each instalment; equipment advance up to 5% of Contract Price | % | Cl. 7.1(i); 19.2 | 48 | for an amount equal to 3% (three percent) of its Bid Price | Base is Bid Price for security but Contract Price for the advance. Retention is separate (2.3). | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.3 | Accepted forms | FOUND | Insurance Surety Bond, Account Payee Demand Draft, Banker's Cheque, irrevocable e-Bank Guarantee; physical BG also acceptable till 31.12.2024 |  | Cl. 7.1(i)(A) and footnote | 48 | Account Payee Demand Draft, Banker’s Cheque or an irrevocable and unconditional e-Bank Guaranteeα from a Bank | The footnote with the 31.12.2024 date sits below the clause on the same page. The date has already passed. | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.4 | Acceptable issuers | FOUND | A bank incorporated in India and recognised by the Reserve Bank of India |  | Cl. 1.1 (Bank) | 17 | a bank incorporated in India and recognized by the Reserve Bank of India | Definition of Bank does not say scheduled or nationalised. | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.5 | Validity and extension | FOUND | Performance Security valid until 60 days after the Defects Liability Period (may be furnished for 2 years and extended 2 months before expiry); Additional Performance Security valid until 28 days after Project Completion Date | days | Cl. 7.1(i)(B); 7.2 | 48 | The Performance Security shall be valid until 60(sixty) days after the Defects Liability Period. The Additional Performance Security shall be valid until 28 (twenty eight) days after Project Completion Date. | Two validity rules: initial 2-year term with rolling extension, and the final end date. 28 vs 60 days differ by security type. | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.6 | Encashment grounds | FOUND | On Contractor Default; on termination for Contractor Default; advance guarantee if advance not recovered |  | Cl. 7.3(i); 23.6(i); 19.2(vi)(c) | 49 | Upon occurrence of a Contractor’s Default, the Authority shall, without prejudice to its other rights and remedies hereunder or in law, be entitled to encash and appropriate the relevant amounts from the Performance Security as Damages | After encashment the Contractor must replenish within 30 days or the Authority may terminate (7.3(ii)). | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.7 | When released | FOUND | Performance Security within 60 days of the end of the Maintenance Period or Defects Liability Period, whichever is later; Additional Performance Security within 28 days of Completion Certificate | days | Cl. 7.4(i) and (ii) | 50 | The Authority shall return the Performance Security to the Contractor within 60 (sixty) days of the expiry of the Maintenance Period or the Defects Liability Period, whichever is later | With a 5 or 10 year defects period, Performance Security stays for years. 9% interest applies if returned late (7.4(iii)). | Found on stated page | Found on stated page | Agrees
BM1 | C6 | 6.8 | Extra guarantee requirements | FOUND | Additional Performance Security if bid is more than 20% below estimate: 20% of the shortfall, capped at 3% of Bid Price | % of shortfall | Cl. 7.1(i)(A)(a) and (b) | 48 | If the Bid Price offered by the Selected Bidder is lower than 20% of the Estimated Project Cost/ cost put to tender, the Additional Performance Security shall be calculated @20% of the difference | Wording "lower than 20% of the Estimated Project Cost" is loose: it means a bid more than 20% below estimate. Possible misreading by an LLM. | Found on stated page | Found on stated page | Agrees
BM2 | C0 | 0.1 | Contract type and version | FOUND | CPWD-7/8 percentage-rate tender and contract for works, IIT Bombay; standard CPWD contract form GCC 2020 as modified and corrected | text | Schedule F, clause 9(ii) | 106 | 9(ii) Standard CPWD contract Form GCC 2020, CPWD Form 7/ 8 as modified & corrected upto AS INCORPORATED | Schedule F names GCC 2020, but the pack carries IITB-specific edits (Dean (IPS), IITB). The cover is only titled General Conditions of Contract. A model may wrongly say GCC 2023. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C0 | 0.2 | Employer and contractor | FOUND | Employer: Indian Institute of Technology Bombay (Director, acting through Dean (IPS)); Contractor: not named (blank form) | text | Tender form CPWD-7/8 | 4 | execution of the work specified for the Director of Indian Institute of Technology , Bombay | Contractor name and acceptance amount are blank, so contractor = NOT_STATED. A model might invent a contractor name. | Found on stated page | Found on stated page | Agrees
BM2 | C0 | 0.3 | Contract value / estimated cost | FOUND | Estimated cost Rs 2,12,27,336; earnest money Rs 4,24,547; tendered value = estimate adjusted by the quoted percentage (not fixed here) | INR | Schedule E | 105 | Estimated cost of work: Rs. ₹ 2,12,27,336/- | Percentage-rate tender: final contract value depends on the percentage quoted. Do not report the estimate as the contract price. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C0 | 0.4 | Completion period and start basis | FOUND | 9 months (activity table 'Time for assignment'); start reckoned 15 days from date of issue of letter of acceptance | months | Schedule F, clause 5 (pp.106-108) | 107 | TIME FOR ASSIGNMENT 09 (Nine) Months (From 0 to 9) – (in months) | Schedule F line Time allowed for execution of work is left blank (p.108). The only number is in an activity table headed Consultancy/Assignment, which looks pasted from a consultancy document. Start: p.106 says 15day after letter of acceptance. Clause 5: start = Schedule F period or site handover, whichever later. | Found on stated page | Found on stated page | Agrees
BM2 | C0 | 0.5 | Defect liability period | FOUND | 12 months after completion certificate (6 months if work costs Rs 10 lacs or less, except road work) | months | Clause 17 | 41 | if any defect, shrinkage or other faults appear in the work within twelve months (six months in the case of work costing Rs. Ten lacs and below except road work) | Printed Rs. Ten lacs here; the deposit refund line says Ten lakhs. At the Rs 2.12 crore estimate the 12-month limb applies. | Found on stated page | Found on stated page | Agrees
BM2 | C0 | 0.6 | Milestones | FOUND | Activity periods only: shop drawings 1 month; execution drawings 15 days; planning, procurement and execution 7 months; post-construction 15 days; total 9 months. No work-percentage or withholding amounts stated | months | Schedule F, clause 5 (pp.106-108) | 107 | C Project Planning: Preparation/Submission of CPM/PERT Chart for Procurement, Material delivery, Installation, testing & Commissioning activities 07 (Seven) months | Clause 2 says the amount shown against that milestone is withheld, but no amounts appear anywhere in Schedule F. The table is not a financial milestone table. A model may fabricate percentages. | Found on stated page | Found on stated page | Agrees
BM2 | C1 | 1.1 | Billing basis and frequency | FOUND | Monthly running account bills on measured work for works estimated above Rs 20 lac; no payment before completion for works of Rs 20 lac or less | text | Clause 7 | 24 | For works estimated to cost over Rs, Twenty lac the interim or running account bills shall be submitted by the contractor | Estimate is Rs 2.12 crore, so monthly running bills apply, on a date fixed each month by the Engineer-in-Charge. | Found on stated page | Found on stated page | Agrees
BM2 | C1 | 1.2 | Days for employer to certify or measure a bill | NOT_STATED | No separate certification period stated |  | Clause 7 | 0 |  | Searched clauses 6, 7 and 7A. The only deadline is the combined payment deadline (see 1.3). A model may split it into certification and payment periods. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM2 | C1 | 1.3 | Days to pay certified amount | FOUND | 10 working days after presentation of the bill (15 working days for works outside the Engineer-in-Charge's headquarters) | working days | Clause 7 | 25 | The amount admissible shall be paid by 10th working day after the day of presentation of the bill by the Contractor to the Engineer-in-Charge or his Authorized Engineer | The 15-working-day extension is in the following sentence. Do not confuse with the 45-day interest trigger in 1.4. | Found on stated page | Found on stated page | Agrees
BM2 | C1 | 1.4 | Interest on delayed payment | FOUND | Simple interest 5% a year on interim bills unpaid 45 days after submission (if bill in order); final bill delay also 5% simple. Delay by contractor in submitting a bill after an advance on materials: 10% a year payable to IITB | % a year | Clause 7 and clause 9 | 25 | after 45 days of submission of bill by the contractor pr ovided the bill submitted by the contractor found to be in order, a simple interest @ 5% (five percent) per annum | Text says simple interest compounded on yearly basis, which contradicts itself. The 45-day trigger is later than the 10-working-day payment date. Final bill interest 5% is on p.26. | Found on stated page | Found on stated page | Agrees
BM2 | C1 | 1.5 | Deductions from each bill | FOUND | Security deposit 5% of gross running and final bill; recovery of mobilisation advance (clause 10B); recovery of secured advance when materials are used; compensation and milestone amounts withheld (clause 2) | text | Clause 1A and others | 16 | to deduct a sum at the rate of 5 % of the gross amount of each running and final bill till the sum deducted will amount to security deposit of 5% of the tendered value of the work | GST on inputs is the contractor's cost (General Rules 13, p.9). No TDS clause found. Only the retention quote is cited; other deductions come from clauses 2 and 10B. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM2 | C1 | 1.6 | Minimum bill value or interim payment cap | FOUND | Minimum gross work Rs 30 lakhs (net of advances) before an interim payment is due | INR | Schedule F, clause 7 | 109 | Clause 7 Gross work to be done together with net payment /adjustment of advances for material collected, if any, since the last such payment for being eligible to interim payment 30 lakhs | Two thresholds: Rs 20 lac (clause 7 text) and Rs 30 lakhs (Schedule F minimum bill). A model may mix them up. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C1 | 1.7 | Final bill timeline | FOUND | Final bill within 3 months of physical completion or 1 month of final completion certificate, whichever earlier; payment within 2 / 3 / 6 months of receipt by tendered value (up to Rs 1 Cr / Rs 1-10 Cr / above Rs 10 Cr); 5% simple interest if late | months | Clause 9 | 26 | within three months of physical completion of the work or within one month of the date of the final certificate of completion furnished by the Engineer-in-Charge whichever is earlier | For a Rs 2.12 crore estimate the 3-month payment limb applies. No claims after the final bill. | Found on stated page | Found on stated page | Agrees
BM2 | C1 | 1.8 | Conditional payment (pay when paid) | NOT_STATED | No pay-when-paid or funding condition |  | Clauses 7, 9, 9A | 0 |  | Searched pay when paid and back to back. Back to back construction on p.47 is about labour hut layout, and back to back basis on p.4 is about subletting; neither is a payment condition. The composite-contract rule (main contractor pays associates within 15 days, p.25) is not pay-when-paid. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM2 | C2 | 2.1 | Is retention / security deposit deducted | FOUND | Yes, security deposit deducted from running and final bills | yes/no | Clause 1A | 16 | to deduct a sum at the rate of 5 % of the gross amount of each running and final bill | Performance guarantee (5%) is a separate item from the security deposit. | Found on stated page | Found on stated page | Agrees
BM2 | C2 | 2.2 | Percentage and base | FOUND | 5% of gross amount of each running and final bill (Schedule E: 5% of tendered value) | % | Clause 1A; Schedule E | 105 | (iii) Security Deposit : 5% of tendered value | Other CPWD documents use 2.5%; this IITB pack says 5%. Do not import the 2.5% figure. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C2 | 2.3 | Cap on total retention | FOUND | Deductions continue until total reaches 5% of tendered value | % of tendered value | Clause 1A | 16 | till the sum deducted will amount to security deposit of 5% of the tendered value of the work | Cap equals the rate in percent terms, but the rate applies to the bill and the cap to the tendered value. | Found on stated page | Found on stated page | Agrees
BM2 | C2 | 2.4 | Earnest money converted into retention | FOUND | No. Earnest money is returned after the performance guarantee is received | yes/no | Schedule E | 105 | (i) Earnest money: Rs. 4,24,547/- (to be returned after receiving performance guarantee) | Some CPWD documents let earnest money count toward the deposit; this pack does not say so. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C2 | 2.5 | Release of retention | FOUND | Not before 12 months after completion certificate (6 months for works of Rs 10 lakhs or less, except road work), or until the final bill is prepared and passed, whichever is later; labour clearance certificate also needed (clause 41) | months | Clause 17 (and clause 41) | 41 | shall not be refunded before the expiry of twelve months (six months in the case of work costing Rs. Ten lakhs and below except road work) after the issue of the certificate final or otherwise, | Quote stops before whichever is later (next words). Road works have a half-and-half release; E&M maintenance works refund within one month. | Found on stated page | Found on stated page | Agrees
BM2 | C2 | 2.6 | Replacement by bank guarantee | FOUND | Yes, on accumulations of at least Rs 5 lac; each guarantee except the last at least Rs 5 lac; validity per clause 17 and extended with time | text | Clause 1A | 16 | The security deposit as deducted above can be released against bank guarantee issued by a scheduled bank, on its accumulations to a minimum of Rs. 5 lac | The Rs 5 lac floor appears twice in the sentence. | Found on stated page | Found on stated page | Agrees
BM2 | C2 | 2.7 | Interest paid on retention | NOT_STATED | No interest on security deposit stated |  | Clause 1A, 17 | 0 |  | Searched interest near security deposit. The only mention is interest arising from deposits held in securities; clause 29A says no interest on sums withheld under lien. A model may assume interest is payable. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM2 | C3 | 3.1 | Is a mobilisation advance given | FOUND | Yes. Schedule F entry for Clause 10B(ii) reads 'Yes/No' with 'No' struck through, so the mobilisation advance clause applies (up to 10% of tendered value, 10% simple interest) | yes/no | Clause 10B(ii); Schedule F | 109 | Clause 10B(ii) Whether Clause 10 B (ii) shall be applicable Yes/No | TEXT TRAP: the strike-through is invisible in extracted text, which reads 'Yes/No'. Seen on the page image (printed page 108). | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM2 | C3 | 3.2 | Percentage and instalments | FOUND | Up to 10% of tendered value; in two or more instalments decided by the Engineer-in-Charge | % of tendered value | Clause 10B(ii) | 28 | Mobilization advance not exceeding 10% of the tendered value may be given | Not exceeding means a maximum, not an entitlement. Instalments are in the next sentence of the same clause. | Found on stated page | Found on stated page | Agrees
BM2 | C3 | 3.3 | Interest on advance | FOUND | Simple interest 10% a year from date of payment to date of recovery, on the outstanding balance | % a year | Clause 10B(iii) | 28 | bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery | Interest runs on the outstanding advance until each recovery. The sentence continues on p.29. | Found on stated page | Found on stated page | Agrees
BM2 | C3 | 3.4 | Recovery method | FOUND | Deducted from bills after the first 10% of gross work is paid, pro rata on work beyond 10%, so the entire advance plus interest is recovered by the time 80% of gross contract value is executed and paid | % of work | Clause 10B(iii) | 29 | on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the contract | Two percentages (10% start, 80% end) in one sentence. The clause starts on p.28 and carries over to p.29. | Found on stated page | Found on stated page | Agrees
BM2 | C3 | 3.5 | Security for the advance | FOUND | Bank guarantee bonds, not more than 6, from a scheduled bank for 110% of the advance, valid until recovery and renewed to cover the balance | % of advance | Clause 10B(ii) | 28 | Before any installment of advance is released, the contractor shall execute a Bank Guarantee Bonds not more than 6 in number from Scheduled Bank for the amount equal to 110% of the amount of advance | 110% applies to the advance and later to the balance amount. | Found on stated page | Found on stated page | Agrees
BM2 | C3 | 3.6 | Plant and machinery or secured advance on materials | FOUND | Secured advance on materials: up to 75% of assessed value or of material element cost, whichever is lower. No plant and machinery advance | % of material value | Clause 10B(i) | 28 | up to 75% of the assessed value of any materials or an amount not exceeding 75% of the material element cost in the tendered rate of the finished item of the work, whichever is lower | Plant and machinery advance is not provided in this pack. Headings Secured Advance on Materials and Mobilization advance are merged in extraction. | Found on stated page | Found on stated page | Agrees
BM2 | C3 | 3.7 | Conditions to receive the advance | FOUND | Written request within one month of order to commence; bank guarantee before each instalment; second and later instalments only after proof of satisfactory utilisation of the earlier one | text | Clause 10B(ii) and (iv) | 28 | if requested by the contractor in writing within one month of the order to commence the work | The Engineer-in-Charge may extend the one-month window (clause 10B(iv), p.29). | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.1 | Does contract impose delay damages | FOUND | Yes, called compensation for delay | yes/no | Clause 2 | 17 | pay as compensation the amount calculated at the rates stipulated below as the authority specified in schedule 'F' may decide on the amount of accepted Tendered Value of the work | Wording is compensation, not liquidated damages. The words liquidated damages never appear in this pack. | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.2 | Rate and base | FOUND | Maximum 1% of accepted Tendered Value per month of delay, computed per day; the actual rate is decided by the authority named in Schedule F (Deputy Director (FEA), IITB) | % per month | Clause 2; Schedule F | 17 | with maximum rate @ 1% (one percent) per month of delay to be computed on per day basis based on quantum of damage suffered due to stated delay on the part of Contractor | Schedule F does not state an actual rate, only the authority. The text gives 1% as a maximum based on quantum of damage suffered. | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.3 | Cap on damages | FOUND | 10% of accepted Tendered Value of work (or of the sectional part if a separate period applies) | % of tendered value | Clause 2 | 17 | shall not exceed 10 % (ten percent) of the accepted Tendered Value of work or of the accepted Tendered Value of the Sectional part of work | Cap is reached after about 10 months at the 1% maximum rate. | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.4 | Final completion only or milestones too | FOUND | Both: delay at completion and shortfall against progress; amounts shown against missed milestones are withheld automatically and released if the contractor catches up | text | Clause 2, Clause 5 | 18 | In case, the contractor does not achieve a particular milestone mentioned in schedule F, or the re-scheduled milestone(s) in terms of Clause 5.4, the amount shown against that milestone shall be withheld | Milestone amounts are not filled in Schedule F (see 0.6), so the mechanism exists but has no numbers. | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.5 | Extension of time | FOUND | Events: force majeure, abnormally bad weather, fire, strikes or civil commotion, delay by other contractors, other causes beyond control; Institute-caused hindrance; request within 14 days on the prescribed form; decision within 21 days; extra time for deviations per clause 12.1 | days | Clause 5.2 to 5.4 | 22 | Request for rescheduling of Mile stones or extension of time, to be eligible for consideration, shall be made by the Contractor in writing within fourteen days of the happening of the event causing delay | Events in 5.2 give extension of time only, no money. Deviation extension is clause 12.1 (p.35). | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.6 | Pre-estimate of loss or proof of loss | FOUND | Not described as a pre-estimate. Clause 22 treats the compensation as reasonable compensation without reference to the actual loss or damage sustained and whether or not any damage was sustained, so proof of loss is not required. Clause 2 wording 'based on quantum of damage suffered' points the other way | text | Clause 22 and Clause 2 | 49 | shall be considered as reasonable compensation to be applied to the use of IITB without reference to the actual loss or damage sustained and whether or not any damage shall have been sustained | Relevant to the court judgments in the source register (J1, J2). | Found on stated page | Found on stated page | Differs (Numbers differ). Blind reader found clause 22 on page 49, which was missed. Key updated.
BM2 | C4 | 4.7 | Deductible from bills, retention or guarantee | FOUND | Yes: set off against any sum payable under this or any other contract with IITB; also recoverable from the security deposit | text | Clause 2; Clause 1A | 18 | The amount of compensation may be adjusted or set -off against any sum payable to the Contractor under this or any other contract with the IITB | Cross-contract set-off is notable. Deduction from the security deposit is on p.16. | Found on stated page | Found on stated page | Agrees
BM2 | C4 | 4.8 | Other damages or penalties | FOUND | Completion plans not submitted: 0.1% of tendered value or Schedule F limit; late performance guarantee: late fee 0.1% a day of guarantee amount (Schedule F); late progress report and late revised programme: recovery per Schedule F; penalties under clauses 19C, 19D, 19G, 19K set by Dean IPS (amounts blank); technical representative shortfall: Rs 1,00,000 a month (senior) and Rs 60,000 a month | text | Clauses 1, 5.1, 5.4, 8A, 19, 32; Schedule F | 26 | he shall be liable to pay a sum of 0.1 % (zero point one percent) of accepted Tendered Value or limit prescribed in Schedule F whichever is more | Several small charges sit in different places. A model may miss the Schedule F recoveries on pp.106 and 111-112. | Found on stated page | Found on stated page | Agrees
BM2 | C5 | 5.1 | Fixed price or price variation | FOUND | Price variation clauses are present. Schedule F: clause 10CA (materials) is NOT applicable ('Applicable' struck through). Clause 10CC (general escalation) IS applicable ('Not Applicable' struck through) but only for stipulated periods over 12 months. Clause 10C (statutory changes) is part of the general conditions. The time allowed is blank in Schedule F and the only period stated is 9 months in an activity table, so 10CC probably does not trigger | text | Clauses 10C, 10CA, 10CC; Schedule F | 110 | Clause 10CC Applicable/ Not Applicable Clause 10 CC to be applicable in contracts with stipulated period of completion exceeding the period shown in next column 12 (Twelve) months | TEXT TRAP: strike-throughs are invisible in extracted text. Seen on the page image (printed page 109). | Found on stated page | Found on stated page | Differs (Status: key POINTS_ELSEWHERE, blind FOUND). Both text readers saw the Applicable/Not Applicable choices as undecided. The page image shows which words are struck through. | Corrected after viewing the page image
BM2 | C5 | 5.2 | Formula | FOUND | 10CA: V = P x Q x (CI - CIo)/CIo per material. 10CC materials: Vm = W x Xm x (MI - MIo)/MIo. 10CC labour: VL = W x Y x (LI - LIo)/LIo. W = 0.85 x cost of work done (M = C + F + I - J) | formula | Clauses 10CA and 10CC | 30 | V= P X Q X CI – CIO CIO V = Variation in material cost i.e. increase or decrease in the amount of rupees to be paid or recovered | Formulas are garbled in text extraction; the 10CC ones are on pp.32-33. Check the layout on the PDF page before copying. Formulas read on page images 32 and 33: Vm = W x (Xm/100) x (MI - MIo)/MIo; VL = W x (Y/100) x (LI - LIo)/LIo; W = N = 0.85 M. 10CA is not applicable in Schedule F. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM2 | C5 | 5.3 | Components and weights | FOUND | 10CA base prices: cement Rs 6295, steel Rs 61045, structural steel Rs 67970 (units not stated); 10CC: materials Xm 40% and labour Y 25% of value of work (balance 35% implied for 10CA materials) | % / INR | Schedule F, clauses 10CA, 10CC | 110 | Component of civil (except materials covered under clause 10CA) /Electrical construction Xm 40 % value of work. - Component of Labour - expressed as percent of total value of work. Y 25 % | Schedule F clause 10C labour component on p.109 is blank (separate from Y = 25%). The 35% balance is derived, not printed. POL has no base price listed. Base prices exist but clause 10CA is NOT applicable (page image 110), so they are unused. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM2 | C5 | 5.4 | Index and source | FOUND | Cement, steel reinforcement, structural steel and POL: price indices issued by Director General, CPWD. Other materials: All India Wholesale Price Index (Economic Adviser, Ministry of Commerce and Industry). Labour: minimum daily wage of an unskilled mazdoor under law | text | Clause 10CA, 10CC | 30 | The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices issued by the Director General, CPWD. | Two index sources, plus a wage notification for labour. A model may name only WPI. The CPWD index route belongs to 10CA, which is not applicable here. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM2 | C5 | 5.5 | Base date | FOUND | 10CC: last stipulated date of receipt of tenders including extensions. 10CA: base price and its period as indicated in Schedule F (periods not stated) | date | Clause 10CC(i) | 31 | (i) The base date for working out such escalation shall be the last stipulated date of receipt of tenders including extension, if any. | Tender due date is 27.04.2023 (p.4). Extensions are unknown. Schedule F base-price periods are blank. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM2 | C5 | 5.6 | Threshold or cap | FOUND | No payment (and no downward adjustment) if stipulated period is equal to or less than the Schedule F time (12 months); escalation computed on 85% of work value; no percentage absorbed and no cap stated | months | Clause 10CC | 31 | No such compensation shall be payable for a work for which the stipulated period of completion is equal to or less t han the time as specified in Schedule F. | The extracted text has less t han. Escalation is quarterly. The 0.85 factor comes from N = 0.85 M on p.32. | Found on stated page | Found on stated page | Agrees
BM2 | C5 | 5.7 | Escalation after original completion date | FOUND | Escalation is paid only for work done during the stipulated period including justified extensions granted without action under clause 2 | text | Clause 10CC | 31 | shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2 | If compensation for delay is levied, the extension is not justified and escalation stops. | Found on stated page | Found on stated page | Agrees
BM2 | C5 | 5.8 | Escalation on employer-supplied materials | FOUND | No: materials supplied by the department at fixed prices are excluded | yes/no | Clause 10CC | 31 | (not being materials supplied or services rendered at fixed prices by the department in accordance with clause 10 & 34 thereof) | Clause 10C and 10CA wording on employer materials was not checked in detail. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.1 | Securities required | FOUND | Earnest money Rs 4,24,547 (returned after performance guarantee); performance guarantee 5% of tendered value; security deposit 5%; bank guarantees for mobilisation advance (110%) and for replacing the deposit; Schedule F late fee on late performance guarantee | text | Schedule E; Clauses 1, 1A, 10B | 105 | (i) Earnest money: Rs. 4,24,547/- (to be returned after receiving performance guarantee) (ii) Performance Guarantee : 5% of tendered value. | No separate bid security besides earnest money. No additional performance security for low bids. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM2 | C6 | 6.2 | Amount or percentage and base | FOUND | Performance guarantee 5% of tendered amount; security deposit 5% of tendered value; earnest money Rs 4,24,547; advance guarantee 110% of the advance | % / INR | Clause 1 | 15 | The contractor shall submit an irrevocable Performance Guarantee of 5% (Five percent) of the tendered amount | Earnest money equals 2% of the estimate (Rs 4,24,547 against Rs 2,12,27,336), but the 2% rate is not stated. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.3 | Forms accepted | FOUND | Cash (under Rs 10,000), deposit at call receipt, banker's cheque, demand draft or pay order (under Rs 1,00,000), government securities, fixed deposit receipt, guarantee bonds of a scheduled bank or SBI | text | Clause 1 | 15 | This guarantee shall be in the form of Cash (in case guarantee amount is less than Rs. 10,000/-) or Deposit at Call receipt of any scheduled bank/Banker's Cheque of any scheduled bank/Demand Draft of any scheduled bank | No mention of e-bank guarantees or insurance surety bonds, which newer CPWD documents allow. A model may add them from general knowledge. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.4 | Acceptable issuers | FOUND | Any scheduled bank or the State Bank of India | text | Clause 1 | 15 | Guarantee Bonds of any Scheduled Bank or the State Bank of India | A fixed deposit receipt of any bank: loss from a failed bank falls on the contractor. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.5 | Validity and extension | FOUND | Performance guarantee valid to stipulated completion date plus 60 days (Format I) or plus 6 months (Format II), and extended if time is extended; guarantee against deposit follows clause 17 and is extended with time | days / months | Clause 1(ii) | 15 | The Performance Guarantee shall be initially valid up to the stipulated date of completion plus minimum 60 days beyond that, if the same is submitted by the agency on scheduled format I as per GCC. | Two bond formats (pp.103-104) give two different validity periods. A model may state only one. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.6 | Grounds for encashment | FOUND | Failure to extend validity (full amount claimable); failure to pay amounts due within 30 days of notice; forfeited in full if contract is determined or rescinded; forfeited if contractor fails to start work | text | Clause 1(iii), (iv); Clause 5 | 15 | (b) Failure by the contractor to pay Director of Indian Institute of Technology Bombay any amount due | Guarantee is payable on demand without regard to disputes (bond format, p.103). The 30-day notice period follows in the same sentence. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.7 | Release | FOUND | Returned without interest after completion certificate; 80% returned after provisional completion certificate (40% if the contract includes maintenance); in maintenance contracts 50% is retained as security deposit and returned year by year | % / text | Clause 1(ii), (v) | 16 | After recording of the provisional Completion Certificate for the work by the competent authority, the 80 % of performance guarantee shall be returned to the contractor, without any interest. | Page 15 says the guarantee is returned after the completion certificate; p.16 adds the 80% release at provisional completion. A model may report only one. | Found on stated page | Found on stated page | Agrees
BM2 | C6 | 6.8 | Extra guarantee requirements | NOT_STATED | No additional performance security for abnormally low bids |  | Clause 1 | 0 |  | Searched additional performance, abnormally low, below the estimated. Not found. The 0.1% a day late fee on the guarantee amount (Schedule F, p.106) is a charge, not an extra guarantee. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM3 | C0 | 0.1 | Type and version of contract | FOUND | Percentage-rate works tender, Appendix 2.10 (MP works departments), effective 23.07.2014; NIT No. 03 dated 05.08.2021 |  | Cover page | 1 | APPENDIX 2.10 For Percentage Rate only in works departments and other Departments similar to work departments (EFFECTIVE FROM 23.07.2014) OFFICE | State-government percentage-rate form with GCC, Contract Data and Annexures. Contract Data (pp. 61-65) overrides general text. | Found on stated page | Found on stated page | Agrees
BM3 | C0 | 0.2 | Employer and contractor | FOUND | Employer: Managing Director, M.P. State Agro Industries Development Corp., Bhopal; Engineer-in-Charge: Executive Engineer H.O. Bhopal; contractor: not named (blank) |  | Contract Data 1.14-1.16 | 61 | 1.14 Employer Managing Director M.P.State Agro Ind. Dev. Corpn. Bhopal 1.15 Engineer Executive Engineer | Contractor name is blank because this is the issued tender, not the signed contract. | Found on stated page | Found on stated page | Agrees
BM3 | C0 | 0.3 | Contract value | FOUND | Probable amount of contract Rs 188.65 lakh; contract amount blank | Rs lakh | Cover page | 1 | 188.65 Lacs One Crore Eighty Eight Lacs Sixty Five Thousand Only | Earnest money Rs 188,650 is a separate figure (p. 16). Do not confuse the EMD digits with the contract value. | Found on stated page | Found on stated page | Agrees
BM3 | C0 | 0.4 | Stipulated completion period and start basis | FOUND | 12 months including rainy season; time runs from date of signing the agreement | months | Contract Data 1.22; GCC 15.2 | 49 | 15.2 The time allowed for execution of the contr act shall commence from the da te of signing of the agreemen t. | Period (12 months) is on pp. 1, 4 and 61; start basis is in GCC 15.2. Two different pages. | Found on stated page | Found on stated page | Agrees
BM3 | C0 | 0.5 | Defect liability period | FOUND | Building works 3 years; new bituminous or concrete road 5 years; bridge works 3 years; building maintenance 1 year | years | Contract Data 12 | 62 | (C) FOR BUILDING WORKS — 3 (THREE) YEARS | Work mixes building and road items, so more than one period could apply. Quote gives the building period only. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM3 | C0 | 0.6 | Milestones | FOUND | Milestone 1: 1/8 of work before 1/4 of time; Milestone 2: 3/8 before 1/2 of time; Milestone 3: 3/4 before 3/4 of time; Milestone 4: complete within stipulated time |  | Contract Data 10; Annexure O | 62 | Mile Stone 1:- 1/8th of the whole work before 1/4th of the whole time allowed has elapsed, Mile Stone 2:- 3/8th of the whole work before 1/2th of the whole time allowed has elapsed Mile Stone | Annexure O says milestones are "As per Contract Data", so the real list sits on p. 62. | Found on stated page | Found on stated page | Agrees
BM3 | C1 | 1.1 | Billing basis and frequency | FOUND | Monthly statements of value of work executed, based on measurements | monthly | GCC 34(a) | 56 | (a) The Contractor shall submit to the Engineer monthly statements of the value of the work e xecuted less t he cumulative | Price adjustment would be worked out quarterly (GCC 31.2) but is not applicable here. | Found on stated page | Found on stated page | Agrees
BM3 | C1 | 1.2 | Days for employer to certify an interim bill | NOT_STATED |  | days |  | 0 |  | Searched GCC 34, Contract Data pp. 61-65, Annexure-1, Bid Data Sheet. The only time limits are for the final account (21 and 45 days) and dispute decisions. A model that supplies 30 days has invented it. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM3 | C1 | 1.3 | Days for employer to pay a certified bill | NOT_STATED |  | days |  | 0 |  | Same search as 1.2. No payment period for interim bills in the English text. Pages 87-93 hold circulars as images with no readable text, so they could not be searched. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM3 | C1 | 1.4 | Interest on delayed payment | FOUND | No interest payable on any payment due or awarded |  | GCC 23 | 52 | 23. No Interest Payable No interest shall be payable to the Contractor on any payment due or awarded by | The answer is a negative. A model may wrongly import a standard interest rate. | Found on stated page | Found on stated page | Agrees
BM3 | C1 | 1.5 | Deductions from each bill | FOUND | Advance payment recovery, security deposit, other contract recoveries, taxes deducted at source |  | GCC 34(f) | 57 | (f) All payment s shall be adjusted for d eductions for ad vance payment, security deposit, other recoveries in terms of c ontract and taxes at sou | Security deposit rate is 5% (Contract Data 17). Hindi special conditions mention GST and a 3.5% PF-related deduction (legacy font, not machine-readable). | Found on stated page | Found on stated page | Agrees
BM3 | C1 | 1.6 | Minimum bill value or cap on interim payment | FOUND | No general minimum bill value stated. For concrete (rigid) pavement works only: 75% of the work is paid once the 7-day beam and concrete strength tests pass, and the remaining 25% after 28 days when the work is found in order |  | PWD circular dated 25.10.2016 (appendix) | 93 |  | Scanned page, no text layer. Hindi read from the image by the key author; a Hindi reader should confirm. Applies to concrete pavement work only. | n/a: scanned page, no text layer | n/a: scanned page, no text layer | Differs (Status: key NOT_STATED, blind FOUND). Blind reader used the scanned page 93. Viewed on the image and added. | Corrected after viewing the page image
BM3 | C1 | 1.7 | Final bill and final payment timeline | FOUND | Contractor submits final account within 21 days of physical completion certificate; Engineer certifies payment within 45 days of receiving a correct and complete account | days | GCC 36.1 | 58 | The Engineer s hall issue a Defects Li ability Certi ficate and certify any pa yment that is due to th e Contractor within 45 d ays of r eceiving | The 21-day figure is in the sentence just before the quote. If the contractor is late, the Engineer finalises and issues a payment certificate within 28 days (36.2). | Found on stated page | Found on stated page | Agrees
BM3 | C1 | 1.8 | Conditional payment (pay when paid) | NOT_STATED |  |  |  | 0 |  | Searched GCC 34 and 23. No pay-when-paid term. GCC 34(h) says interim payments are advances against final payment, which is a different point. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM3 | C2 | 2.1 | Is retention or security deposit deducted | FOUND | Yes, security deposit deducted from each running bill |  | Annexure-1 GCC 30 | 2 | GCC Clause 30 — SECURITY DEPOSIT to be deducted from each running bill @ | Retention is called "Security Deposit" in this form. A model searching only for the word "retention" will miss it. | Found on stated page | Found on stated page | Agrees
BM3 | C2 | 2.2 | Percentage and base | FOUND | 5% of gross amount of each running bill | % of gross running bill | Contract Data 17 | 64 | 17 Security Deposit to be deducted from each running bill At the rate of 5% of Gross | Annexure-1 gives 5% too. Both agree. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C2 | 2.3 | Cap on total retention | FOUND | Up to 5% of final contract amount | % of final contract amount | Contract Data 17 | 64 | Maximum limit of deduction of Security Deposit Up to 5% of |  | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C2 | 2.4 | Earnest money converted or counted into retention | NOT_STATED |  |  |  | 0 |  | Searched ITB pp. 6-13, Bid Data Sheet, Annexure L. EMD is forfeited in some cases but nothing says it is returned or counted toward security deposit. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Differs (Status: key NOT_STATED, blind FOUND). Wording or extra detail only. Both answers are correct. Key kept.
BM3 | C2 | 2.5 | Release timing | FOUND | Refunded on completion of defect liability period |  | GCC 30.3 | 54 | 30.3 The Security deposits shall be refunded of completion of defect liability period. The | Defect liability period for buildings is 3 years, so release is late. Link to 0.5. | Found on stated page | Found on stated page | Agrees
BM3 | C2 | 2.6 | Replacement by bank guarantee | FOUND | Yes, by equivalent bank guarantee or fixed deposit receipt valid up to 3 months beyond defect liability period |  | GCC 30.2 | 54 | 30.2 The security deposit may be replaced b y equ ivalent amount o f bank guarantee or fixed deposit r eceipt assigned to the Em ployer, w ith validity up |  | Found on stated page | Found on stated page | Agrees
BM3 | C2 | 2.7 | Interest on retention | FOUND | No interest is payable. Clause 23 says no interest is payable on any payment due or awarded; retention is not mentioned separately |  | GCC 23 | 0 |  | Inference from a general clause. Nothing in the document mentions interest on the security deposit itself. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Differs (Status: key NOT_STATED, blind FOUND). Blind reader inferred this from the general no-interest clause 23.
BM3 | C3 | 3.1 | Mobilisation advance given | NOT_APPLICABLE | No mobilisation and construction machinery advance is payable |  | Contract Data 19; GCC 32.1 | 64 | Clause 32.1 Mobilization and Construction Machinery Advance Applicable No Mobilization and Construction Machinery | GCC 32 describes the advance as a general clause, then Contract Data switches it off. A model reading only GCC 32 will report an advance. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.2 | Percentage or amount and instalments | NOT_APPLICABLE | Not applicable |  | Contract Data 32.4 | 64 | Clause 32.4 If yes, Type & Amount of Advance payment that can be paid Not Applicable |  | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.3 | Interest-free or interest-bearing | NOT_APPLICABLE | Not applicable |  | Contract Data 32.3 | 64 | Clause 32.3 If yes, Rate of interest chargeable on advances Not Applicable Clause | GCC 32.2 says interest-bearing if an advance were given. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.4 | Recovery of advance | NOT_APPLICABLE | Not applicable |  | Contract Data 32.5 | 64 | Clause 32.5 If yes, Recovery of advance payment Not Applicable 20 Clause |  | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.5 | Security for advance | NOT_APPLICABLE | Not applicable. A bank guarantee form for advances is attached (Annexure S) but unused |  | Contract Data 32.2 | 64 | Clause 32.2If yes, Unconditional Bank Guarantee Not Applicable Clause | Annexure S (p. 72) is a blank guarantee form for the mobilisation advance. Its presence does not mean an advance is given. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.6 | Plant and machinery or secured advance | NOT_APPLICABLE | No secured advance; no construction machinery advance |  | Contract Data 20; Annexure-1 GCC 33 | 64 | Clause 33.1 Secured Advance Applicable Not Applicable Clause | Annexure T (secured advance indenture, 12% interest on default) is also a blank form only. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C3 | 3.7 | Conditions to receive an advance | NOT_APPLICABLE | Not applicable |  | Contract Data 33.3 | 65 | Clause 33.3 if yes, Conditions for secured advance Not Applicable Clause |  | Found on stated page | Found on stated page | Agrees
BM3 | C4 | 4.1 | LD for delay | FOUND | Yes. Contract Data points to Annexure P for the scale |  | GCC 15.4; Contract Data 10 | 49 | 15.4 Failure of the Contr actor to adhere to the tim elines and/or milestones shall attract such liquidated damages as is laid down in the Contract Data. 15.5 | GCC 15.4 alone says "as laid down in the Contract Data", which points on to Annexure P (p. 68). The rate is stated there, not missing. | Found on stated page | Found on stated page | Agrees
BM3 | C4 | 4.2 | Rate and base | FOUND | Milestone slippage: amount retained of 2.5%, 5%, 7.5% or 10% of the work remaining unexecuted (by slippage band); final delay: 0.05% of contract price per day | % per day of contract price | Annexure P | 68 | the compensation shall b e levied on the con tractor at t he rate of 0 .05% pe r day of delay limited to a maximum o f 1 0% | Extracted text splits digits ("0 .05%", "1 0%"). Confirm 0.05% and 10% on the PDF page. Two mechanisms: milestone retention and final-delay compensation. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C4 | 4.3 | Maximum cap | FOUND | 10% of contract price | % of contract price | Annexure P | 68 | the compensation shall b e levied on the con tractor at t he rate of 0 .05% pe r day of delay limited to a maximum o f 1 0% | Cap applies to the per-day compensation after the stipulated completion. Milestone retention is refundable if slippage is made good. See also 4.2. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C4 | 4.4 | Final completion only or also milestones | FOUND | Both. Milestone slippage leads to retention that is refunded if made good; delay beyond final completion leads to per-day compensation |  | Annexure P | 68 | i. Slippage up to 25% in financial target during the milestone under consideration - 2.5% of the work remained unexecuted in the related time | Termination trigger in Contract Data 14: less than 50% progress in a milestone or less than 75% in two consecutive milestones. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C4 | 4.5 | Extension of time | FOUND | Competent authority grants extension within 30 days of application; up to 30 days by Executive Engineer, beyond 30 days by Managing Director | days | GCC 14.2; Contract Data 9 | 49 | 14.2 The compet ent auth ority shall grant such extension at each such occasion within a period of 30 days of r eceipt of application from | Delays not attributable to the contractor are excluded when counting milestone slippage (Annexure P note). | Found on stated page | Found on stated page | Agrees
BM3 | C4 | 4.6 | Pre-estimate of loss or proof of loss | NOT_STATED |  |  |  | 0 |  | Searched GCC 15, Annexure P. No genuine pre-estimate wording and no requirement to prove loss. GCC 15.6 only corrects overpaid LD after an extension. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM3 | C4 | 4.7 | Deduction from bills, retention or guarantee | FOUND | Engineer retains the LD amount from the contractor bills; bankable security accepted instead; recovery from performance security and security deposit also allowed |  | GCC 15.5; GCC 24 | 49 | 15.5 In the event of delay in e xecution of the Works as per the timelines mentioned in the Contract Data the En gineer-in-charge shall r etain from the bills of the Contractor amount eq ual to the liquidated d | GCC 24 (p. 52) separately allows recovery from performance security, additional performance security and security deposit. | Found on stated page | Found on stated page | Agrees
BM3 | C4 | 4.8 | Other LD or penalties | FOUND | Field laboratory not set up: 1% of contract amount per month, max Rs 50,000 per month; technical personnel missing: Rs 30,000 a month per graduate engineer and Rs 18,000 per diploma engineer; construction programme not submitted: 1% of contract amount, max Rs 50,000; termination penalty adds 20% of value of work not completed |  | Contract Data 5, 8, 11, 15 | 62 | Penalty for not establishing field Laboratory 1% of Contract Amount per month, subject to a maximum of Rs. 50,000/- per month of | Several penalties spread over pp. 61-63. A model often reports only the delay compensation. | Found on stated page | Found on stated page | Agrees
BM3 | C5 | 5.1 | Fixed price or price variation clause | FOUND | Fixed price for this tender. Price adjustment applies only if the amount in the NIT is more than Rs 10 crore; this tender is Rs 1.89 crore |  | Annexure-1 GCC 31; Contract Data 18 | 2 | Price Adjustment shall be applicable only in case where the Amount in N.I.T. is more than Rs. 10 (Ten) Crores. This clause | Needs reasoning: the clause and formulas exist in the document but are inactive for this contract. A model that lists the formulas as active is wrong. Hindi special conditions (item 3, legacy font) also say the price escalation condition is not part of the agreement even if time is extended. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM3 | C5 | 5.2 | Formula | NOT_APPLICABLE | Cement: Vc = 0.85 x Pc/100 x R x (C1 - C0)/C0; similar formulas for steel, bitumen and POL. Inactive for this contract |  | Annexure R | 70 | Vc= 0.85 x pc/100 x R x | Formula is in the document but not applicable. The steel and POL formulas in the extracted text have character errors. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C5 | 5.3 | Components and weights | NOT_APPLICABLE | Contract Data: cement 18%, steel 13%. Annexure R: cement 20%, steel 20%. Bitumen and POL components named but no weights given | % of work | Contract Data 31.2.4; Annexure R | 64 | Clause 31.2.4 Weight ages of Component in the work Component Percentage of Component in the work Cement 18% Steel | The two places disagree (18/13 against 20/20). The Contract Data is the one the form says to use. Annexure R text is on p. 70. Only matters if price adjustment applied. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Page image viewed
BM3 | C5 | 5.4 | Index and source | NOT_APPLICABLE | Cement: all-India WPI for grey cement; steel: all-India WPI for bars and rods; bitumen: IOC depot retail price; POL: IOC retail price of high speed diesel; WPI from the Ministry of Industrial Development site (eaindustry.nic.in) |  | Annexure R | 70 | The all I ndia wholesale price i ndex for Grey cement on the date of o pening o f Bids a s published by the M inistry | Bitumen and POL use IOC retail prices, not WPI. Text in Annexure R has stray spaces. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C5 | 5.5 | Base date | NOT_APPLICABLE | Date of opening of bids |  | Annexure R | 70 | The all I ndia wholesale price i ndex for Grey cement on the date of o pening o f Bids a s published by the M inistry | Same passage as 5.4 for cement. Bitumen and POL base prices are also taken at bid opening. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C5 | 5.6 | Threshold or cap on adjustment | NOT_APPLICABLE |  | % |  | 0 |  | No percentage threshold or ceiling in GCC 31, Contract Data 18 or Annexure R. The Rs 10 crore figure is an applicability limit (see 5.1), not an absorption threshold. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Differs (Status: key NOT_STATED, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C5 | 5.7 | Escalation after original completion date | NOT_APPLICABLE | Applies only to work up to the initial intended completion date or extensions caused by the employer; none for extensions due to the contractor; applies during a force majeure extension |  | GCC 31.1; GCC 7.3 | 55 | 2. The price adjustment clause shall apply only for the works executed from the date of signing of the agreement until the end of the initial intended completion date or extensions granted for reasons attributed to the Employer by the | Hindi special conditions say escalation does not apply under any extension. English and Hindi texts conflict, but it only matters if price adjustment applied. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C5 | 5.8 | Escalation on employer-supplied materials | NOT_APPLICABLE | No. Value of material issued by the department is deducted from the work value R |  | GCC 31.2(3) | 55 | less value of material issued by the department, if any, during the | Inferred from the definition of R. Not a stated rule on employer-supplied materials. Status changed to NOT_APPLICABLE: the clause exists but is switched off for this contract. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind NOT_APPLICABLE). Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer.
BM3 | C6 | 6.1 | Securities required | FOUND | Earnest money (bid security), performance security, additional performance security (low bids or road works), security deposit |  | Bid Data Sheet 9, 11; Annexure-1 | 16 | 11 Amount of Performance Security 5% of Contract Amount for Road and Bridge works; 5% of the Contract Amount for building works. | Bank guarantee forms for advances exist but no advance is given. | Found on stated page | Found on stated page | Agrees
BM3 | C6 | 6.2 | Amount or percentage | FOUND | Earnest money Rs 188,650; performance security 5% of contract amount; additional performance security 5% for PWD road works; low-bid additional security by formula (see 6.8); security deposit 5% of running bills |  | ITB 22 (Annexure-1); Bid Data Sheet 9, 11 | 2 | ITB Clause 22 — (1) Performance Security to be Deposited @ 5%(Five percent) of contract amount. (2) Additional Performance Security to be Deposited @5% (Five percent) along with Performance Security only in case of Road works in PWD | Annexure-1 says additional security applies only to road works in PWD. The Bid Data Sheet says it applies to bids more than 15% below. Both exist. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM3 | C6 | 6.3 | Forms accepted | FOUND | Performance security as term deposit receipt or bank guarantee of a nationalised or scheduled commercial bank; earnest money online only; security deposit may be BG or FDR |  | Annexure L; Bid Data Sheet 9 | 38 | The performance security shall be in the s hape of term deposit receipt bank gu arantee of a ny na tionalized / sc hedule co | Forms accepted appear in several places. Annexure L is the clearest. | Found on stated page | Found on stated page | Agrees
BM3 | C6 | 6.4 | Acceptable issuers | FOUND | Nationalised or scheduled commercial bank |  | Annexure L | 38 | The performance security shall be in the s hape of term deposit receipt bank gu arantee of a ny na tionalized / sc hedule co | Scanned page 92 (order dated 05.10.2016) lifts an earlier restriction on accepting one named bank's instruments in PWD tenders. Hindi read from the image; confirm with a Hindi reader. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM3 | C6 | 6.5 | Validity and extension | FOUND | Performance security valid up to 3 months beyond the completion of the defect liability period; additional performance security valid up to stipulated completion time plus 3 months | months | Contract Data 16 | 64 | 16 Performance guarantee (Security) shall be valid up to Performance Guarantee (Security) should be valid up to three months beyond the completion of defect liability period (Maintence Guarantee period) and Additional performance Guarantee if any should be valid up to | Defect liability period extends automatically until defects are rectified (GCC 18.2). No clause says the guarantee must be renewed when time is extended. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM3 | C6 | 6.6 | Grounds for encashment | FOUND | Guarantee payable on first written demand without proof; contract allows recovery of claims, defect correction costs and termination penalty from performance security |  | Annexure M-1; GCC 24; GCC 18.3 | 41 | we undertake to pay you, upon your first written demand and without cavil or argument, any | Quote is from the guarantee form, not the contract clause. GCC 24 (p. 52) and 18.3 (p. 50) give the recovery grounds. | Found on stated page | Found on stated page | Agrees
BM3 | C6 | 6.7 | Release | FOUND | Additional performance security refunded on satisfactory completion of work; performance security lapses 3 months after the defect liability period |  | GCC 30.3; Contract Data 16 | 54 | The additional performance security shall be refunded on satisfactory completion of the work. | No separate release clause for the main performance security. It simply expires on its validity date. | Found on stated page | Found on stated page | Agrees
BM3 | C6 | 6.8 | Extra guarantee requirements | FOUND | Additional performance security if the bid is more than 15% below the estimate: contract amount times the difference between the bid percentage below and 15%; valid to stipulated completion plus 3 months |  | Bid Data Sheet 11 | 16 | Additional Performance Security, if any Equal to an amount arrived at, by multiplying the contract amount with difference of percentage between percent rates (below/minus) of successful bid and 15% percent (below/minus), considering bid rates less than Fifteen percent | Hindi special conditions (item 11, legacy font) say bids more than 15% below SOR are unworkable and need extra performance guarantee. Consistent with the Bid Data Sheet. | Found on stated page | Found on stated page | Agrees
BM4 | C0 | 0.1 | Contract type and version | FOUND | CPWD Form 7 percentage-rate bid and contract for works under CPWD General Conditions of Contract 2023 (Construction Works), as corrected up to last date of bid submission |  | Schedule F, Cl. 9(ii) | 22 | 9(ii) Standard CPWD Contract Form CPWD Form 7 of General Conditions of Contract 2023 for Construction works, Central Public Works Department, as modified and corrected up to last date of submission of bids. | GCC 2023 text is NOT in this file; it is incorporated by reference. NIT provisions prevail over the standard form (para 2, p8). Trap: tool may quote GCC clauses from memory. | Found on stated page | Found on stated page | Agrees
BM4 | C0 | 0.2 | Employer and contractor | FOUND | Employer: President of India, through Executive Engineer, CED-I, Civil Construction Unit, MoEF&CC. Contractor: not named (bid stage, name fields blank) |  | NIT para 1 (Part A) | 7 | on behalf of President of India invites online Percentage rate bids from the Specialised agencies in two bid system for the following work | Contractor name appears only as blank fields (CPWD-7, Acceptance p20). Do not accept any invented contractor. | Found on stated page | Found on stated page | Agrees
BM4 | C0 | 0.3 | Contract value / estimated cost | FOUND | Estimated cost Rs 7,25,065 (rough guide only); EMD Rs 14,501. Bid is a percentage above/below the estimate | INR | CPWD-6 para 1.1 | 13 | 1.1 The work is estimated to cost for Rs. 7,25,065/-. This estimate, however, is given merely as a rough guide. | Contract amount in the Acceptance form is blank (p20). Estimate is not the contract value. Total of schedule of work Rs 725065.22, rounded to 725065 (p37). Page 1 is an image printout of the CPWD e-tender portal with the same estimate and time. It also shows bid closing 11/02/2025 15:00 and bid validity 75 days. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM4 | C0 | 0.4 | Completion period and start basis | FOUND | 40 days from date of start (start = 7 days after letter of acceptance), or from first handing over of site, whichever is later | days | CPWD-6 para 3; Schedule F Cl. 5 | 13 | 3. The time allowed for carrying out the work will be 40 Days from the date of start as defined in schedule 'F' or from the first date of handing over of the site, whichever is later | Schedule F Cl. 5 (p23) sets 7 days from letter of acceptance for date of start. NIT p7 also says 40 (Forty) Days. Trap: reading 40 days from award. Page 1 is an image printout of the CPWD e-tender portal with the same estimate and time. It also shows bid closing 11/02/2025 15:00 and bid validity 75 days. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM4 | C0 | 0.5 | Defect liability / maintenance period | FOUND | No defect liability period stated. Only item: electrical/mechanical materials carry a 1 year guarantee/warranty from commissioning | year | Part B, Add. Specs 2.8 | 33 | All the material shall be stand guarantee/warranty for a period of 1 year for any manufacturing defecate by the contractor from the date of commissioning of the system. | Searched 'defect', 'maintenance', 'liability'. This is a materials warranty, not an express DLP; a DLP, if any, sits in the GCC. Borderline: accept either 'not stated' or '1 year (materials)'. | Found on stated page | Found on stated page | Agrees
BM4 | C0 | 0.6 | Milestones | FOUND | 4 milestones from date of start: 25% of work in 10 days, 50% in 20 days, 75% in 30 days, 100% in 40 days; each missed milestone withholds 1.25% of accepted tendered amount | % / days | Schedule F, Cl. 5 | 23 | 1 Work done amounting to 25% of accepted tender amount (Civil + Electrical). 10 Days 1.25% of accepted tendered amount. | Rows 2 to 4 follow the same pattern (p23). A tool may report only the first milestone or invent a total cap. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C1 | 1.1 | Billing basis and frequency | FOUND | Measurement-based interim (running account) bills; mode of measurement CMB (computerised measure book). Billing frequency not stated in this file |  | Schedule F, Cl. 6 and 7 | 24 | Clause 6: Computerised Measure Book (CMB) / Electronic Measurement Book (EMB) i) Mode of measurement CMB | Frequency is not given. Para 32 (p10) points to GCC clauses 6 and 7 for computerised measurement. Trap: inventing 'monthly bills'. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C1 | 1.2 | Days to certify/measure a bill | POINTS_ELSEWHERE | Not stated in the NIT (measurement and bill procedures). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'certif', 'measure', 'within N days' (pp8-17), Schedule F (pp21-26). Para 32 names GCC cl. 6-7 only for recording measurements and preparing bills. A period may exist in the GCC; not stated here. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C1 | 1.3 | Days to pay a certified amount | POINTS_ELSEWHERE | Not stated in the NIT (interim payment period). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'payment', 'pay', 'within N days' across the file. Only payment-related text: Cl. 7 minimum Rs 3.50 lakh, Cl. 7A labour licence condition. No payment period. Trap: tool quoting a GCC number. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C1 | 1.4 | Interest on delayed payment | POINTS_ELSEWHERE | Not stated in the NIT (interest on delayed payment). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'interest': hits on pp17 and 34 are unrelated ('in the interest of work' / safety). No interest on late payment stated. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C1 | 1.5 | Deductions from each bill | FOUND | Security deposit 2.50% of tendered amount (Schedule E). Also withheld: 1.25% per missed milestone; zoo fines recoverable from bills/securities; no payment for items using materials below permissible limits | % | Schedule E; Schedule F Cl. 5; paras 35, 41 | 21 | Security Deposit 2.50% of tendered amount. | How and when the deposit is deducted is in the GCC, not here. Do not add the 5% performance guarantee. GST and labour cess are borne by contractor in rates (p8), not deducted. | Found on stated page | Found on stated page | Agrees
BM4 | C1 | 1.6 | Minimum bill value for interim payment | FOUND | Gross work done since last payment (net of adjustment of material advances) must reach Rs 3.50 lakh to be eligible for an interim payment | INR lakh | Schedule F, Cl. 7 | 24 | Clause 7 Gross work to be done together with net payment/ adjustment of advances for material collected, if any, since the last such payment for being eligible to interim payment Rs. 3.50 Lakhs | Threshold is about 48% of the Rs 7.25 lakh estimate. Trap: reading Rs 3.5 lakh as a cap. Cl. 7A (p24): no running bill paid until labour licences and registrations are submitted. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C1 | 1.7 | Final bill timeline | POINTS_ELSEWHERE | Not stated in the NIT (final bill timing). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'final bill', 'final payment', 'completion'. Not stated here; likely in GCC 2023 (incorporated by reference, para 23 p10). | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C1 | 1.8 | Pay-when-paid / conditional payment | NOT_STATED |  |  |  | 0 |  | Searched for conditions on third-party funds; none. Government employer; no such clause in this file. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM4 | C2 | 2.1 | Retention / security deposit deducted? | FOUND | Yes: security deposit 2.50% of tendered amount is specified (Schedule E). Deduction mechanics are in the GCC |  | Schedule E | 21 | Performance Guarantee 5.00% of tendered amount Security Deposit 2.50% of tendered amount. | The file does not say the deposit is cut from running bills; only the percentage. Trap: summing PG and SD into 7.5%. | Found on stated page | Found on stated page | Agrees
BM4 | C2 | 2.2 | Percentage and base | FOUND | 2.50% of tendered amount | % of tendered amount | Schedule E | 21 | Security Deposit 2.50% of tendered amount. | Base is 'tendered amount' (the accepted bid), not estimated cost. Performance guarantee (5%) is separate. | Found on stated page | Found on stated page | Agrees
BM4 | C2 | 2.3 | Cap on total retention | FOUND | Security deposit is fixed at 2.50% of the tendered amount; no separate cap on retention is stated |  | Schedule E | 21 | Security Deposit 2.50% of tendered amount. | Schedule E gives one total percentage; no separate per-bill rate or cap stated. Any per-bill rate or cap is in the GCC. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind FOUND). Blind reader treated the 2.5% as the total. Key changed from NOT_STATED to FOUND.
BM4 | C2 | 2.4 | EMD converted into / counted against deposit | FOUND | EMD is returned after the performance guarantee is received; no statement that it counts toward security deposit |  | CPWD-6 para 11 | 15 | The earnest money deposited along with bid shall be returned after receiving the aforesaid performance guarantee. | Absence of conversion is an inference from the return clause. Other CPWD forms allow EMD to count toward the deposit; not stated here. | Found on stated page | Found on stated page | Agrees
BM4 | C2 | 2.5 | Release of retention | POINTS_ELSEWHERE | Not stated in the NIT (release of the security deposit). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'release', 'refund', 'returned'. Only EMD refund and PG-related text; no security deposit release timing. GCC likely governs. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C2 | 2.6 | Replace deposit with bank guarantee | FOUND | A bank guarantee form covering Security Deposit is included; conditions and stages for replacing deposit are not stated here |  | BG form, p29 | 29 | Form of Bank Guarantee for Earnest Money/Performance Guarantee/Security Deposit | Form title only. Do not report conditions or limits of replacement as stated. | Found on stated page | Found on stated page | Agrees
BM4 | C2 | 2.7 | Interest on retention | NOT_STATED |  |  |  | 0 |  | Searched 'interest' and deposit text; nothing on interest payable to contractor on deposit. | n/a: no quote (nothing stated) | n/a: no quote (nothing stated) | Agrees
BM4 | C3 | 3.1 | Mobilisation advance given? | NOT_APPLICABLE | No: clause 10B(ii) shall not be applicable |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Mapping 10B(ii) = mobilisation advance comes from the GCC 2023 copy (cpwd_gcc2023_b p53), not from this NIT. Trap: BG form (p29) lists 'Mobilization Advance' as boilerplate. The NIT only says Clause 10B(ii) is 'No'. That 10B(ii) is the mobilisation advance clause is known from the GCC text (BM2 and the reference GCC), not from this NIT. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Both readers saw 'Clause 10B(ii) applicable: No'. The NIT does not say 10B(ii) is the mobilisation advance clause; that comes from the GCC text. | Page image viewed
BM4 | C3 | 3.2 | Advance percentage / instalments | NOT_APPLICABLE | No advance, so no percentage or instalments |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Do not accept 10% in two instalments; that is the GCC default when switched on, not this contract. Switched off here. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C3 | 3.3 | Interest-free or interest-bearing | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Any interest rate quoted by a tool would be invented from the GCC. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C3 | 3.4 | Recovery of advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Cl. 7 mentions adjustment of advances for material collected; that is about material advances, not mobilisation. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C3 | 3.5 | Security required for advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | BG form (p29) mentions Mobilization Advance generically; no guarantee amount for an advance applies here. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C3 | 3.6 | Plant/machinery advance or secured advance on materials | POINTS_ELSEWHERE | Not switched on or off in this NIT. Cl. 7 refers to adjustment of advances for material collected 'if any'; secured advance (GCC 10B(i)) is not addressed in Schedule F. No plant and machinery advance mentioned |  | Schedule F, Cl. 7 | 24 | net payment/ adjustment of advances for material collected, if any, since the last such payment | Schedule C (tools and plants to be hired to contractor) is NIL (p21); that is hire, not an advance. Borderline item: do not credit a firm 'yes' or 'no'. | Found on stated page | Found on stated page | Differs (Status: key POINTS_ELSEWHERE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C3 | 3.7 | Conditions to receive the advance | NOT_APPLICABLE | Not applicable; no mobilisation advance |  | Schedule F, Cl. 10B(ii) | 24 | Clause 10 B Clause 10B (ii) Whether Clause 10 B (ii) shall be applicable No | Same switched-off clause. | Found on stated page | Found on stated page | Differs (Status: key NOT_APPLICABLE, blind NOT_STATED). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C4 | 4.1 | Delay damages imposed? | FOUND | Yes: compensation for delay under GCC clause 2 (authority to fix it: Superintending Engineer, CCU); Schedule F also withholds 1.25% per missed milestone |  | Schedule F, Cl. 2 and 5 | 23 | Clause 2 Authority for fixing Compensation under Clause 2 Superintending Engineer, CCU, MoEF&CC. | The word 'liquidated damages' never appears in this file. Trap: tool expecting that phrase and answering 'no'. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind POINTS_ELSEWHERE). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C4 | 4.2 | Rate and base | POINTS_ELSEWHERE | Delay compensation rate is not in this file (GCC clause 2). Schedule F fixes milestone withholding at 1.25% of accepted tendered amount per missed milestone | % of accepted tendered amount | Schedule F, Cl. 2 and 5 | 23 | 1 Work done amounting to 25% of accepted tender amount (Civil + Electrical). 10 Days 1.25% of accepted tendered amount. | GCC 2023 copy (cpwd_gcc2023_b p29) says up to 1% per month with a 10% cap. That is NOT in this NIT; credit only if the tool cites the GCC. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C4 | 4.3 | Maximum cap | POINTS_ELSEWHERE | Cap is not stated in this file; it sits in GCC clause 2. Derived only: four missed milestones would withhold 4 x 1.25% = 5% |  | Schedule F, Cl. 2 | 23 | Clause 2 Authority for fixing Compensation under Clause 2 Superintending Engineer, CCU, MoEF&CC. | The 5% is arithmetic, not a stated cap. Trap: reporting 10% (GCC value) as if stated here. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C4 | 4.4 | Final completion or milestones | FOUND | Both: completion in 40 days, plus four interim milestones, each carrying a withholding amount |  | Schedule F, Cl. 5 | 23 | Sl. No. Description of mile stone (s) Time allowed (From date of start) Amount to be withheld in case of Non-achievement of each Mile stone(s) | Milestones are measured as value of work done (civil + electrical) against accepted tender amount. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C4 | 4.5 | Extension of time | FOUND | Schedule F names deciding authorities: extension of time = Executive Engineer CED-I; rescheduling of milestones and shifting date of start = Superintending Engineer CCU. Grounds are in the GCC |  | Schedule F, Cl. 5 | 23 | Authority to decide: i) Extension of time Executive Engineer, CED-I, CCU, MoEF&CC. ii) Rescheduling of mile stones Superintending Engineer, CCU, MoEF&CC. | Conditions for granting extension are not in this file. Shifting of date of start also decided by SE CCU (p23). | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind POINTS_ELSEWHERE). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C4 | 4.6 | Pre-estimate of loss / proof of loss | POINTS_ELSEWHERE | Not stated in the NIT (whether compensation is a pre-estimate). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'loss', 'pre-estimate', 'damages'. Milestone withholding is not described as a pre-estimate of loss. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C4 | 4.7 | Deductible from bills, retention or guarantee | POINTS_ELSEWHERE | Milestone amounts are 'withheld'; the NIT does not say whether they come from bills, deposit or guarantee, and deductibility of compensation is in the GCC |  | Schedule F, Cl. 5 | 23 | Amount to be withheld in case of Non-achievement of each Mile stone(s) | Separate para 41 (p11) says zoo fines are recoverable from bills or securities/performance guarantee; that is not delay-related. Do not merge the two. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind POINTS_ELSEWHERE). Key reworded: the NIT does not say what milestone amounts are taken from. | Page image viewed
BM4 | C4 | 4.8 | Other damages or penalties | FOUND | Penalties under GCC 19C, 19D, 19G, 19K decided by EE CED-I (amounts not here); late fee 0.1% per day of PG amount (max 2 extra days); Rs 30,000/month per person for missing technical representative; Rs 10/metre recovery for conduit without fish wire |  | Schedule F, Cl. 1, 19, 32; Part B 1.4 | 25 | Clause 19 C Authority to decide penalty for each default Executive Engineer, CED-I, CCU, MoEF&CC or his legal successor or Assignee thereof | Cl. 32 reads 'Recovery Rate N/A' yet a Rs 30,000 table follows (p26): ambiguous, likely not applicable. Late-fee text is on p23. Many small items; tools often miss them. | Found on stated page | Found on stated page | Agrees
BM4 | C5 | 5.1 | Fixed price or price variation | FOUND | No general index-based escalation: clause 10CC and 10CA are Not Applicable. Clause 10C is marked Applicable with labour component 25% (statutory-change compensation only, per GCC) |  | Schedule F, Cl. 10C, 10CA, 10CC | 24 | Clause 10CA – Not Applicable Clause 10CC – Not Applicable | GCC copy (cpwd_gcc2023_b p55): 10C covers cost rises from fresh law or statutory orders, not general market escalation. A 40-day contract is effectively fixed price. Trap: treating 10C labour 25% as an escalation formula. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind POINTS_ELSEWHERE). Wording or extra detail only. Both answers are correct. Key kept. | Page image viewed
BM4 | C5 | 5.2 | Formula | POINTS_ELSEWHERE | No escalation formula in this file; 10C mechanics are in the GCC |  | Schedule F, Cl. 10C | 24 | Clause 10 C Whether Clause 10 C shall be applicable Applicable Component of labour expressed as percent of value of work 25% | 10CC would carry the index formula but is Not Applicable. Any formula a tool states is from outside this file. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C5 | 5.3 | Components and weights | FOUND | Labour component 25% of value of work (clause 10C only); no cement, steel, fuel or other weights | % of value of work | Schedule F, Cl. 10C | 24 | Component of labour expressed as percent of value of work 25% | No other components listed because 10CC is switched off. | Found on stated page | Found on stated page | Agrees | Page image viewed
BM4 | C5 | 5.4 | Index and source | POINTS_ELSEWHERE | Not stated in the NIT (escalation indices). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Searched 'index', 'WPI', 'price'. Only hit for 'price' is the bid form (p34). No index named. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C5 | 5.5 | Base date | POINTS_ELSEWHERE | Not stated in the NIT (escalation base date). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | No base date stated; 10CC (which would carry it) is Not Applicable. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C5 | 5.6 | Threshold or cap | POINTS_ELSEWHERE | Not stated in the NIT (escalation threshold or cap). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | No threshold or cap on price variation stated in this file. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C5 | 5.7 | Escalation stops after completion date | POINTS_ELSEWHERE | Not stated in the NIT (when escalation stops). The NIT incorporates CPWD GCC 2023 by reference (Schedule E), so the detail is in that document (see Reference_CPWD_GCC_2023.pdf). |  | Schedule E | 21 | General Conditions of Contract 2023 for Construction works, Central Public Works Department, as amended up to last date of submission of bids. | Not stated; no escalation clause switched on beyond 10C. | Found on stated page | Found on stated page | Differs (Status: key NOT_STATED, blind POINTS_ELSEWHERE). Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE.
BM4 | C5 | 5.8 | Escalation on employer-supplied materials | NOT_APPLICABLE | Not applicable: Schedule B (materials issued to contractor) is NIL |  | Schedule B; Schedule F Cl. 10CC | 21 | Quantity Rates in figures & words at which the material will be charged to the contractor Place of issue 1 2 3 4 5 -----------NIL ---------------- | No department-issued materials, and 10CC is off. Cl. 38 (p27) permits theoretical-quantity variations for cement, bitumen, steel but is not escalation. | Found on stated page | Found on stated page | Agrees
BM4 | C6 | 6.1 | Securities required | FOUND | Earnest money Rs 14,501; performance guarantee 5% of tendered amount; security deposit 2.50% of tendered amount; guarantee bonds for listed works; bids valid 30 days |  | Schedule E; CPWD-6 paras 9, 11 | 21 | Earnest money Rs. 14,501/- Performance Guarantee 5.00% of tendered amount Security Deposit 2.50% of tendered amount. | EMD is 2.0% of the estimate (14,501 / 725,065). No additional performance security for low bids is stated in this file. | Found on stated page | Found on stated page | Agrees
BM4 | C6 | 6.2 | Amount or percentage for each | FOUND | EMD Rs 14,501; performance guarantee 5% of tendered amount; security deposit 2.50% of tendered amount | INR; % | CPWD-6 para 11; Schedule E | 15 | The contractor whose bid is accepted will be required to furnish performance guarantee 5% (Five Percent) of the tendered amount as mentioned in schedule E and within the period specified in Schedule F. | Inconsistency: para 29 (p10) says 5% of the 'composite contract amount'; para 2(b) (p8) says 'letter of intent', Schedule F says 'letter of acceptance'. Time limit: 5 days plus 2 days with late fee (p23). Page 2 (portal printout image) confirms EMD Rs 14,501 payable by DD, FDR, BC or TC. | Found on stated page | Found on stated page | Agrees | Corrected after viewing the page image
BM4 | C6 | 6.3 | Forms accepted | FOUND | Performance guarantee: insurance surety bond, account payee demand draft, fixed deposit receipt or bank guarantee. EMD also allows banker's cheque and e-bank guarantee |  | CPWD-6 para 11 and para 9 | 15 | This guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks in accordance with the prescribed form. | EMD list on p14 is longer than the PG list. Trap: merging the two lists. | Found on stated page | Found on stated page | Agrees
BM4 | C6 | 6.4 | Acceptable issuers | FOUND | Any commercial bank (performance guarantee, EMD bank guarantee). Elsewhere (p8) EMD guarantee is described as 'any Scheduled Bank' |  | CPWD-6 para 9 | 14 | Bank Guarantee including e- Bank Guarantee (for balance amount as prescribed) from any of the Commercial Banks | Wording differs between 'Commercial Banks' (pp14-15) and 'Scheduled Bank' (p8). Report both or flag the difference. | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM4 | C6 | 6.5 | Validity and extension with time | FOUND | EMD bank guarantee valid at least 90 days (single bid) or 180 days (two-bid) from last date of receipt of bids. Performance guarantee validity and extension are not stated here; BG form: valid up to a date unless extended on demand | days | CPWD-6 para 9; BG form | 14 | having validity for a period of 90 days for single bid works and 180 days for two bid system or more from the last date of receipt of bids | This is a two-bid tender, so 180 days applies to EMD BG. Trap: applying 180 days to the performance guarantee. | Found on stated page | Found on stated page | Agrees
BM4 | C6 | 6.6 | Grounds for encashment | FOUND | Performance guarantee forfeited if contractor fails to commence work; EMD forfeited if guarantee not furnished in time. BG form: bank pays on demand within 10 days |  | CPWD-7 tender text; CPWD-6 para 11; BG form | 18 | I/ We agree that President of India or the successors in office shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the said performance guarantee absolutely. | Quote is the bidder undertaking; the trigger 'if I/We fail to commence work as specified' sits just before it (p18). More grounds (e.g. contractor default, zoo fines recoverable from guarantee, p11 para 41) exist. Demand-within-10-days is in the BG form (p29). | Found on stated page | Found on stated page | Differs (Numbers differ). Wording or extra detail only. Both answers are correct. Key kept.
BM4 | C6 | 6.7 | Release | FOUND | EMD of unsuccessful bidders refunded after bid validity expires or on acceptance, whichever is earlier; successful bidder's EMD returned after performance guarantee is received. Release of performance guarantee is not stated here |  | CPWD-6 paras 9 and 11 | 14 | The earnest money given by all the tenderers except the lowest tenderer shall be refunded immediately after the expiry of stipulated bid validity period or immediately after acceptance of the successful bidder, whichever is earlier. | PG release timing is not in this file. Trap: tool stating a PG release date from the GCC. | Found on stated page | Found on stated page | Agrees
BM4 | C6 | 6.8 | Extra guarantee requirements | FOUND | No additional performance security for low bids is stated. Separate guarantee bonds are required for stone work, water supply, sanitary and drainage, waterproofing, CPVC doors and windows, aluminium works and road works; 1 year materials warranty |  | NIT para 30 | 10 | 30) The contractor shall have to execute guarantee bonds in respect of Stone work, water supply, sanitary installation & drainage works, water proofing works, CPVC door / windows, Aluminium Works & Road works as per Performa at Annexures. | Generic boilerplate: this job is electrical and aeration work and no such annexures are in the file. No additional performance security for abnormally low bids is stated. | Found on stated page | Found on stated page | Differs (Status: key FOUND, blind POINTS_ELSEWHERE). Both readers agree on the facts. Key reworded to state both parts.

## Review Log
Contract | Q | What differed | Key before review | Blind reader | Resolution | Key
BM1 | 0.1 | Numbers differ | [FOUND] NHAI draft EPC agreement for four-laning of Makhu Town, NH-54 Punjab; cover dated July 2024 | [FOUND] Draft Engineering Procurement and Construction (EPC) Agreement of NHAI; dated July 2024; lump-sum EPC with 5/10-year maintenance | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM1 | 1.5 | Numbers differ | [FOUND] Retention 6% of every payment (cap 5% of Contract Price); advance recovery 15% of each Stage Payment Statement; withholding for unperformed or defective work (19.5(iv)) | [FOUND] Retention Money 6% of every Stage Payment (cap 5% of Contract Price); mobilisation advance recovery 15% of each Stage Payment Statement plus interest; taxes deducted at source (no % given); Damages and other contract recoveries (20 days notice); withheld value of defective/unperformed work; maintenance payment reductions per Schedule-M | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM1 | 2.4 | Status: key NOT_STATED, blind FOUND | [NOT_STATED] No link between bid security and retention | [FOUND] No link to retention: Bid Security stays in force until substituted by Performance Security (not converted into retention money) | Blind reader supplied a supporting definition on page 17. Key changed from NOT_STATED to FOUND. | Changed
BM1 | 4.8 | Numbers differ | [FOUND] 0.01% of Bid Price per day for late security; maintenance non-compliance payment cuts (Sch. M); Authority pays damages for late site handover (8.3); bid ban if >90 days late on projects of Rs 300 crore or more; early completion bonus 0.03% a day, max 5% | [FOUND] Lane closure delay 0.1% of monthly maintenance payment per 250 m per day (double for emergency/failure closure); 20% of cost as Damages for failure to rectify defects (17.4) or maintenance (14.7); Maintenance payment reduction per Schedule-M; late Performance Security 0.01% of Bid Price per day (7.1(iii)); 120% of removal cost (12.2(ii)); bar on future NHAI bids if 90 days late and contract >= Rs 300 crore (10.3(iv)). Authority-side Damages: ROW delay (8.3) aggregate capped 1% of Contract Price (3.1(v)); 1% of Contract Price if Appointed Date fails (3.4) | Blind reader listed more damages items. Three were re-checked in the text and added. One (aggregate cap on right-of-way delay) could not be re-found and was left out. | Changed
BM2 | 1.5 | Numbers differ | [FOUND] Security deposit 5% of gross running and final bill; recovery of mobilisation advance (clause 10B); recovery of secured advance when materials are used; compensation and milestone amounts withheld (clause 2) | [FOUND] Security deposit 5% of gross amount of each running and final bill (until 5% of tendered value); recovery of mobilisation advance (pro rata after first 10% of work) with 10% simple interest; recovery of secured advance on materials on incorporation; set-off of compensation/penalties/other dues; milestone amounts withheld; Schedule F recoveries (technical representatives Rs 1,00,000 and Rs 60,000 per month). No TDS or income tax deduction stated; GST and cess borne by contractor | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM2 | 4.6 | Numbers differ | [FOUND] Not described as a pre-estimate. The 1% is a maximum based on quantum of damage suffered; no express requirement for the employer to prove loss; without prejudice to other legal remedies | [FOUND] Not described as a pre-estimate of loss. Clause 22 treats all compensation as reasonable compensation payable without reference to actual loss and whether or not any damage is sustained, so no proof of loss is required; Clause 2 wording 'based on quantum of damage suffered' points the other way | Blind reader found clause 22 on page 49, which was missed. Key updated. | Changed
BM2 | 5.1 | Status: key POINTS_ELSEWHERE, blind FOUND | [POINTS_ELSEWHERE] Price variation clauses are present (10C statutory changes, 10CA materials, 10CC general escalation), but Schedule F leaves Applicable / Not Applicable unselected for 10CA and 10CC; 10CC applies only if the period exceeds 12 months | [FOUND] Price variation clauses present (not fixed price): Clause 10CA material variation for cement, steel and structural steel with Schedule F base prices; Clause 10C statutory price/wage changes; Clause 10CC escalation on other materials and labour applies only if stipulated period exceeds 12 months, which is not so for the 9-month schedule, so by Clause 10CC(ix)(b) Clauses 10C and 10CA apply | Both text readers saw the Applicable/Not Applicable choices as undecided. The page image shows which words are struck through. | Changed
BM2 | 5.5 | Numbers differ | [FOUND] 10CC: last stipulated date of receipt of tenders including extensions. 10CA: base price and its period as indicated in Schedule F (periods not stated) | [FOUND] Last stipulated date of receipt of tenders including extension (tender due 27.04.2023); Schedule F base prices: cement Rs 6295, steel Rs 61045, structural steel Rs 67970 with no corresponding period stated | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM3 | 0.5 | Numbers differ | [FOUND] Building works 3 years; new bituminous or concrete road 5 years; bridge works 3 years; building maintenance 1 year | [FOUND] Building works 3 years (36 months). Road work: new road bituminous or concrete 5 years; renewal with BT up to 30 mm 3 years, over 30 mm 5 years. Contract is composite (building plus road) and the text does not say which period governs | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM3 | 1.6 | Status: key NOT_STATED, blind FOUND | [NOT_STATED] | [FOUND] No minimum bill value stated. No general cap on interim payment. Only a scanned circular (p93) for rigid concrete pavement work: pay 75% of that work once 7-day beam and concrete strength found OK, balance 25% after 28 days | Blind reader used the scanned page 93. Viewed on the image and added. | Changed
BM3 | 2.4 | Status: key NOT_STATED, blind FOUND | [NOT_STATED] | [FOUND] No conversion stated. EMD of successful bidder is discharged when agreement signed after furnishing performance security; EMD Rs 188650 paid online | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM3 | 2.7 | Status: key NOT_STATED, blind FOUND | [NOT_STATED] | [FOUND] No interest on retention stated; general rule that no interest is payable on any payment due | Blind reader inferred this from the general no-interest clause 23. | Changed
BM3 | 5.1 | Numbers differ | [FOUND] Fixed price for this tender. Price adjustment applies only if the amount in the NIT is more than Rs 10 crore; this tender is Rs 1.89 crore | [FOUND] Effectively fixed price: price adjustment applies only where amount in NIT exceeds Rs 10 crore; this tender is Rs 1.8865 crore. Hindi SCC (b)3 also says price escalation clause is not part of contract even if time is extended | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM3 | 5.2 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] Cement: Vc = 0.85 x Pc/100 x R x (C1 - C0)/C0; similar formulas for steel, bitumen and POL. Inactive for this contract | [NOT_APPLICABLE] Not applicable here. Printed formulas: Vc = 0.85 x pc/100 x R x (C1-Co)/Co for cement; Vs = 0.85 x Ps/100 x R x (Si-So)/So for steel; Vb = 0.85 x Pb/100 x R x (Bi-Ba)/Ba for bitumen; Vf = 0.85 x Pf/100 x R x (Fi-Fo)/Fo for POL | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.3 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] Contract Data: cement 18%, steel 13%. Annexure R: cement 20%, steel 20%. Bitumen and POL components named but no weights given | [NOT_APPLICABLE] Not applicable. Components: cement, steel, bitumen, POL only. Weights conflict: Contract Data gives cement 18%, steel 13%; Annexure-R gives cement 20%, steel 20%; bitumen and POL weights blank. No labour component | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.4 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] Cement: all-India WPI for grey cement; steel: all-India WPI for bars and rods; bitumen: IOC depot retail price; POL: IOC retail price of high speed diesel; WPI from the Ministry of Industrial Development site (eaindustry.nic.in) | [NOT_APPLICABLE] Not applicable. Cement: all-India WPI Grey cement; steel: all-India WPI Bars and Rods (both Ministry of Industrial Development, eaindustry.nic.in); bitumen: IOC depot official retail price; POL: IOC HSD retail price at nearest centre | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.5 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] Date of opening of bids | [NOT_APPLICABLE] Not applicable. Base is the date of opening of bids (Co, So, Ba, Fo) | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.6 | Status: key NOT_STATED, blind NOT_APPLICABLE | [NOT_STATED] | [NOT_APPLICABLE] Not applicable. No percentage threshold or cap stated; only gate is PAC in NIT above Rs 10 crore; formulas apply 0.85 factor to component weights | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.7 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] Applies only to work up to the initial intended completion date or extensions caused by the employer; none for extensions due to the contractor; applies during a force majeure extension | [NOT_APPLICABLE] Not applicable. If it applied: only until initial completion date or extensions for Employer-caused reasons; no benefit for contractor-caused extension; applies in force majeure. Hindi SCC (b)3: no price escalation even if time extended | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 5.8 | Status: key FOUND, blind NOT_APPLICABLE | [FOUND] No. Value of material issued by the department is deducted from the work value R | [NOT_APPLICABLE] Not applicable. If it applied, value R excludes materials issued by department; Annexure-K lists no materials issued (NIL) | Convention: price adjustment is switched off for this contract (estimate under Rs 10 crore), so status is NOT_APPLICABLE. The printed terms stay in the answer. | Changed
BM3 | 6.2 | Numbers differ | [FOUND] Earnest money Rs 188,650; performance security 5% of contract amount; additional performance security 5% for PWD road works; low-bid additional security by formula (see 6.8); security deposit 5% of running bills | [FOUND] EMD Rs 188650 fixed amount (no percentage stated; equals 1% of Rs 188.65 lakh); performance security 5% of contract amount (building and road); additional performance security = contract amount x (15% minus quoted percentage below), only if bid is below 15% under PAC; security deposit 5% of gross running bill | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 1.2 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Not stated in NIT; NIT only refers to GCC 2023 Clauses 6 and 7 for computerised recording of measurement and bill preparation | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 1.3 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Payment period (days) not stated in NIT; deferred to CPWD GCC 2023 (Schedule E) | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 1.4 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Not stated in NIT; deferred to GCC 2023 (rate and base not given) | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 1.7 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Final bill timeline and conditions not stated in NIT; deferred to GCC 2023 | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 2.3 | Status: key NOT_STATED, blind FOUND | [NOT_STATED] | [FOUND] Security deposit fixed at 2.50% of tendered amount; no separate cap on retention stated | Blind reader treated the 2.5% as the total. Key changed from NOT_STATED to FOUND. | Changed
BM4 | 2.5 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Release of security deposit not stated in NIT; deferred to GCC 2023 | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 3.1 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] No: clause 10B(ii) shall not be applicable | [NOT_STATED] | Both readers saw 'Clause 10B(ii) applicable: No'. The NIT does not say 10B(ii) is the mobilisation advance clause; that comes from the GCC text. | Changed
BM4 | 3.2 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] No advance, so no percentage or instalments | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 3.3 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] Not applicable; no mobilisation advance | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 3.4 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] Not applicable; no mobilisation advance | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 3.5 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] Not applicable; no mobilisation advance | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 3.6 | Status: key POINTS_ELSEWHERE, blind NOT_STATED | [POINTS_ELSEWHERE] Not switched on or off in this NIT. Cl. 7 refers to adjustment of advances for material collected 'if any'; secured advance (GCC 10B(i)) is not addressed in Schedule F. No plant and machinery advance mentioned | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 3.7 | Status: key NOT_APPLICABLE, blind NOT_STATED | [NOT_APPLICABLE] Not applicable; no mobilisation advance | [NOT_STATED] | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 4.1 | Status: key FOUND, blind POINTS_ELSEWHERE | [FOUND] Yes: compensation for delay under GCC clause 2 (authority to fix it: Superintending Engineer, CCU); Schedule F also withholds 1.25% per missed milestone | [POINTS_ELSEWHERE] Compensation for delay is provided under GCC Clause 2 (authority to fix it is the Superintending Engineer, CCU); the NIT does not state the term LD or its rate; milestone shortfall amounts are withheld | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 4.5 | Status: key FOUND, blind POINTS_ELSEWHERE | [FOUND] Schedule F names deciding authorities: extension of time = Executive Engineer CED-I; rescheduling of milestones and shifting date of start = Superintending Engineer CCU. Grounds are in the GCC | [POINTS_ELSEWHERE] Extension of time decided by Executive Engineer, CED-I, CCU; rescheduling of milestones by Superintending Engineer, CCU; shifting date of start for late site handover by Superintending Engineer, CCU; conditions for extension not stated in NIT (GCC) | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 4.6 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Not stated in NIT whether compensation is a pre-estimate of loss or needs proof; deferred to GCC Clause 2 | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 4.7 | Status: key FOUND, blind POINTS_ELSEWHERE | [FOUND] Milestone amounts are 'withheld'; the sum they are taken from (bills, deposit or guarantee) is not stated here | [POINTS_ELSEWHERE] Not stated in NIT; milestone amounts are 'withheld'; NIT separately lets Zoo fines be recovered from bills or securities; deductibility of delay compensation deferred to GCC | Key reworded: the NIT does not say what milestone amounts are taken from. | Changed
BM4 | 5.1 | Status: key FOUND, blind POINTS_ELSEWHERE | [FOUND] No general index-based escalation: clause 10CC and 10CA are Not Applicable. Clause 10C is marked Applicable with labour component 25% (statutory-change compensation only, per GCC) | [POINTS_ELSEWHERE] Not explicitly stated as fixed or PVC; Schedule F marks Clause 10C applicable with labour component 25% of value of work, and Clauses 10CA and 10CC not applicable; clause content is in GCC | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 5.4 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Index and source not stated in NIT; deferred to GCC | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 5.5 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Base date not stated in NIT; deferred to GCC | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 5.6 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Threshold or cap on escalation not stated in NIT; deferred to GCC | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 5.7 | Status: key NOT_STATED, blind POINTS_ELSEWHERE | [NOT_STATED] | [POINTS_ELSEWHERE] Not stated in NIT; deferred to GCC | Convention fixed: when the detail lives only in the incorporated GCC 2023, status is POINTS_ELSEWHERE, not NOT_STATED. Blind reader used POINTS_ELSEWHERE. | Changed
BM4 | 6.4 | Numbers differ | [FOUND] Any commercial bank (performance guarantee, EMD bank guarantee). Elsewhere (p8) EMD guarantee is described as 'any Scheduled Bank' | [FOUND] Commercial banks (CPWD-6 paras 9 and 11); Info para 7 says bank guarantee of any Scheduled Bank towards EMD | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 6.6 | Numbers differ | [FOUND] Performance guarantee forfeited if contractor fails to commence work; EMD forfeited if guarantee not furnished in time. BG form: bank pays on demand within 10 days | [FOUND] EMD forfeited if PG not deposited in time, or on withdrawal (50% within 7 days of last bid date, 100% after); PG forfeited if contractor fails to commence work; bank pays on Government demand to meet recoveries due or likely to be due; Zoo fines recoverable from bills or securities/PG | Wording or extra detail only. Both answers are correct. Key kept. | Kept
BM4 | 6.8 | Status: key FOUND, blind POINTS_ELSEWHERE | [FOUND] Guarantee bonds for stone work, water supply, sanitary and drainage, waterproofing, CPVC doors/windows, aluminium works and road works (generic text); 1 year materials warranty | [POINTS_ELSEWHERE] No additional performance security for low bids is stated; NIT requires guarantee bonds for stone work, water supply, sanitary installation and drainage, water proofing, CPVC doors/windows, aluminium works and road works per proforma at annexures (not in document) | Both readers agree on the facts. Key reworded to state both parts. | Changed
BM1 | 4.2 | Not a blind-reader difference |  |  | Wording fixed: damages run from the Schedule J date once the milestone is missed by 30 days. They do not start after the 30 days. | Changed
BM1 | 5.2 | Not a blind-reader difference |  |  | Formulas were images in the text layer. Read from the page image and added. Confirm on PDF page 109 and 111. | Changed
BM2 | 3.1 | Not a blind-reader difference |  |  | Both text readers saw 'Yes/No' as undecided. The page image shows 'No' struck through, so the clause applies. | Changed
BM2 | 5.2 | Not a blind-reader difference |  |  | Formulas confirmed on the page image (they were garbled in text). | Changed
BM2 | 5.3 | Not a blind-reader difference |  |  | 10CA base prices are filled in but clause 10CA is switched off in Schedule F. | Changed
BM2 | 5.4 | Not a blind-reader difference |  |  | Same: 10CA is switched off. | Changed
BM3 | 6.4 | Not a blind-reader difference |  |  | Page 92 viewed on the image. | Changed
BM4 | 0.3 | Not a blind-reader difference |  |  | Page 1 image (portal printout) matches. | Changed
BM4 | 0.4 | Not a blind-reader difference |  |  | Page 1 image (portal printout) matches. | Changed
BM4 | 6.2 | Not a blind-reader difference |  |  | Page 2 image shows the same EMD. | Changed

## Eye-check Log
Contract | PDF pages viewed | What the page images showed | Effect on the key
BM1 | 109, 111 | Price-adjustment formulas are images in the PDF. Read VRW, VBR and the maintenance formula. Plant and machinery weight is 15% in every column. Matches the text answers on weights and indices. | Key 5.2 filled in
BM2 | 1 | Cover page only. | No change
BM2 | 32, 33 | Escalation formulas (clause 10CC) were garbled in the text. Clear on the page. | Key 5.2 note
BM2 | 105, 106 | Schedule E and F values match the key (performance guarantee 5%, security deposit 5%, earnest money Rs 4,24,547). No strike-throughs affecting the six clause types. | No change
BM2 | 109 | Clause 10B(ii): 'No' is struck through, so the mobilisation advance clause applies. Clause 7 minimum Rs 30 lakhs. Clauses 7A and 2A left as Yes/No. | Key 3.1 corrected
BM2 | 110 | Clause 10CA: 'Applicable' struck through, so NOT applicable. Clause 10CC: 'Not Applicable' struck through, so applicable if the period exceeds 12 months. Xm 40%, Y 25%. | Key 5.1 corrected
BM2 | 111 | No financial clause content beyond the key. | No change
BM3 | 63, 64 | Contract Data items 14 to 20 match the key: security deposit 5%, price adjustment gate Rs 10 crore, weights 18% and 13%, no advances. Item 15 also says the 20% share of unexecuted work is part of the penalty on termination. | No change
BM3 | 68 | Annexure P clean: milestone retention 2.5, 5, 7.5, 10%; compensation 0.05% a day, maximum 10% of contract price. Digits that were split in the text are clear here. | Confirms key 4.2 and 4.3
BM3 | 87 to 93 | Seven scanned Hindi circulars: lab testing of materials; manufactured sand limit; stamp duty on work contracts (three pages; 0.25%, minimum Rs 500, maximum Rs 25,000); order lifting a restriction on one bank's guarantee instruments; payment split for concrete pavement works (75% then 25%). | Key 1.6 added, 6.4 note added
BM4 | 1, 2, 3 | Image printout of the CPWD e-tender portal: estimate Rs 7,25,065, 40 days, bid closing 11/02/2025, EMD Rs 14,501, bid validity 75 days. | Notes added to 0.3, 0.4, 6.2
BM4 | 23, 24 | Schedule F milestones, clause 7 minimum Rs 3.50 lakh, 7A Yes, 10B(ii) No, 10C Applicable 25%, 10CA and 10CC Not Applicable. All match the key. | No change

## Summary
ID | Contract | Questions | Found | Not stated | Not applicable | Points elsewhere | Quotes with a text layer | Found by reader 1 | Found by reader 2 | Blind reader agreed | Blind reader differed | Rows changed after review
BM1 | NHAI Makhu Town EPC Agreement (NH-54, Punjab) | 52 | 46 | 5 | 0 | 1 | 47 | 47 | 47 | 48 | 4 | 4
BM2 | IIT Bombay tender: MEP and interior works, Chemistry Research Lab | 52 | 48 | 4 | 0 | 0 | 48 | 48 | 48 | 48 | 4 | 6
BM3 | MP Agro tender: composite building, Gwalior | 52 | 33 | 5 | 14 | 0 | 44 | 44 | 44 | 39 | 13 | 10
BM4 | MoEF&CC e-NIT: water bubbler, National Zoological Park | 52 | 28 | 2 | 7 | 15 | 50 | 50 | 50 | 27 | 25 | 17